## Notes
Notes
1. Final 2016 Annual Progress Report published on May 16, 2017. Metrics workbook "finalized" in accordance with final report on May 16, 2017 (the pre-final draft was routed to public on 2/20/17).
2. Cathy reorganized columns on All Projects Tab per December 2017 SOP. Data edits for consistency with new SOP denoted by peach shading.
3. Katie updated entries based on BAMSTAR RFI responses.
4. On 2/27/18, Cathy reviewed all entries, and updated where needed for further consistency with December 2017 SOP.
5. 072518 - Created the Access database tab, LS/WW.
6. 100318: Added entity-specific load reductions to the load reduction tabs, removed the Access database tab, and changed the name of the STAR tables tab
7. 030419 Tina added STAR 2019 stakeholder updates in Green.
8. 042319 Tina updated FDACS information.
9. 01292020 Updated projects/changes for STAR 2019 in orange
10. 021920 Bree provided an updated All Projects page which replaced the old color coded page. New page has yellow highlight for 2019 changes
11. 032620 Chris added project IDs (highlighted in blue)for new projects (blanks) inserted in the STAR 2019 process from Access import. Saved a working copy to check and added a pivot table on projects type check tab to review for any errors/missing info.
12. 051420 Chris created Lat Long Append tab for all projects with lat longs to update Access
13. Chris corrected lat long coordinates
14. Notes on FDACS reduction calc methodology in project description.
15. TMG: Updated Completed + N/A to Ongoing.
16. TMG: Checked and updated project types
17. 02182021 BR: Removed previous highlights and entered stakeholder updates from the 2020 STAR requests. Stakeholder submitted changes are highlighted in purple and my additions/edits are in blue.
18. 040221: updated missing ProjIDs. TEK

## All Projects
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile | Structural, Non-structural, or Trade | Original Project Status | Year Added | BMAP | 2019 STAR Priority Projects (1-5) | TN Reduction (kg/yr) | TP Reduction (kg/yr)
EWCO | 2326 | City of Bonita Springs | N/A | BS-01 | Fertilizer Ordinance | Ordinance. | Regulations, Ordinances, and Guidelines | Ongoing | Not provided | N/A | 696 | 0 | Imperial River | N/A | N/A | N/A | City | N/A | N/A | Not provided | Not provided | Not provided | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | 315.7 | 0
EWCO | 2325 | City of Bonita Springs | N/A | BS-02 | Florida Yards and Neighborhood (FYN) Program | Education program utilizing the FYN Program. | Education Efforts | Ongoing | 2012 | N/A | 835 | 0 | Imperial River | N/A | Not provided | 3000 | City | Not provided | N/A | Not provided | Not provided | Not provided | N/A |  | Non-structural | Ongoing | 2012 | Everglades West Coast |  | 378.7493 | 0
EWCO | 2324 | City of Bonita Springs | N/A | BS-03 | Old 41 Catch Basin Inserts | Catch basin inserts. | Catch Basin Inserts/Inlet Filter Cleanout | Canceled | N/A | N/A | N/A | N/A | Imperial River | N/A | N/A | N/A | N/A | N/A | N/A | Not provided | 26.30980393 | -81.79348238 | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | #VALUE! | 0
EWCO | 2323 | City of Bonita Springs | N/A | BS-04 | Residential Dry Detention | Dry detention. | Dry Detention Pond | Completed | Not provided | Prior to 2012 | 1 | 0 | Imperial River | 4 | Not provided | Not provided | City | Not provided | N/A | N/A | Not provided | Not provided | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | 0.45359 | 0
EWCO | 2322 | City of Bonita Springs | N/A | BS-05 | Morton Avenue Swales | Dry retention. | Grass swales with swale blocks or raised culverts | Completed | Not provided | Prior to 2012 | 212 | 0 | Imperial River | 26 | Not provided | Not provided | City | Not provided | N/A | N/A | 26.35329715 | -81.75092032 | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | 96.1615 | 0
EWCO | 2321 | City of Bonita Springs | N/A | BS-06 | Marni Fields | Dry detention. | Dry Detention Pond | Completed | Not provided | Prior to 2012 | 6 | 0 | Imperial River | 16 | Not provided | Not provided | City | Not provided | N/A | N/A | 26.35014829 | -81.75538095 | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | 2.7216 | 0
EWCO | 2320 | City of Bonita Springs | N/A | BS-07 | Felts Avenue Stormwater Treatment | Dry detention. | Dry Detention Pond | Completed | Not provided | Prior to 2012 | 258 | 0 | Imperial River | 31 | Not provided | Not provided | City | Not provided | N/A | N/A | 26.34206819 | -81.77807294 | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | 117.0267 | 0
EWCO | 2319 | City of Bonita Springs | N/A | BS-08 | Street Sweeping | Monthly street sweeping. | Street Sweeping | Ongoing | 2010 | N/A | 161 | 103 | Imperial River | N/A | Not provided | 22000 | City | Not provided | N/A | Not provided | Not provided | Not provided | N/A |  | Non-structural | Ongoing | 2012 | Everglades West Coast |  | 73 | 47
EWCO | 2341 | City of Bonita Springs | DEP/ SFWMD | BS-09 | Felts Avenue Bio-Reactor Project | Utilize woodchips in an anaerobic environment to strip nitrogen from incoming stormwater. The 40-acre watershed will be treated on a 2-acre site on Felts Ave. | BMP Treatment Train | Completed | 2017 | 2017 | TBD | TBD | Imperial River | 40 | 623389 | Not provided | DEP/ SFWMD/ City | Not provided | SO772 | Not provided | 26.3382 | -81.7773 | N/A |  | Structural | Ongoing | 2015 | Everglades West Coast |  | TBD | TBD
EWCO | 2333 | City of Bonita Springs | Lee County | BS-10 | Pine Lake Preserve Rehydration Project | Joint project with Lee County that will rehydrate and reestablish hydraulic connectivity between the Imperial River and the undisturbed Corkscrew Regional Ecosystem Watershed (CREW) wetlands to the east of the preserve on the Corkscrew Swamp. | Hydrologic Restoration | Underway | 2017 | TBD | TBD | TBD | Imperial River | 173 | Not provided | Not provided | City | Not provided | N/A | Not provided | 26.343 | -81.7425 | N/A |  | Structural | Ongoing | 2015 | Everglades West Coast | 3 | TBD | TBD
EWCO | 2334 | City of Bonita Springs | N/A | BS-11 | Downtown Redevelopment Drainage Project | Created two miles of interconnected drainage infrastructure to improve water quality through the use of exfiltration trenches. A total of 8.84 acre feet of exfiltration storage is provided by the project. | BMP Treatment Train | Completed | 2016 | 2016 | Not provided | Not provided | Imperial River | 83.29 | 6330000 | Not provided | City | Not provided | N/A | N/A | 26.339 | -81.7785 | N/A |  | Structural |  | 2016 | Everglades West Coast |  | TBD | TBD
EWCO | 2335 | City of Bonita Springs | N/A | BS-12 | Septic System Removal | Conversion of septic systems to central sewer. | OSTDS Phase Out | Completed | 2001 | 2016 | 912 | Not provided | Imperial River | N/A | 17205 | Not provided | City | Not provided | N/A | N/A | 26.3388 | -81.766 | N/A |  | Structural |  | 2016 | Everglades West Coast |  | TBD | TBD
EWCO | 2336 | FDACS | Agricultural Producers | FDACS-01 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on FDEP spreadsheet loading model. Acres treated based on FDACS OAWP December 2020 Enrollment and FSAID VII. | Agricultural BMPs | Completed | N/A | N/A | 0 | N/A | Hendry Creek | 0 | N/A | N/A | FDACS | TBD | N/A | N/A | Not provided | Not provided | N/A | Y | Non-structural | Ongoing | 2016 | Everglades West Coast |  | 0 | -
EWCO | 2337 | FDACS | Agricultural Producers | FDACS-02 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on FDEP spreadsheet loading model. Acres treated based on FDACS OAWP December 2020 Enrollment and FSAID VII. | Agricultural BMPs | Completed | N/A | N/A | 10893 | N/A | Imperial River | 5571.9322 | N/A | N/A | FDACS | TBD | N/A | N/A | Not provided | Not provided | N/A | Y | Non-structural | Ongoing | 2016 | Everglades West Coast |  | 4940.9777 | -
EWCO | 2338 | FDOT District 1 | N/A | HC-FDOT-01 | Wet Detention Ponds (1, 2, and 3) Facility ID: 12010-3561-01 | Wet detention. | Wet Detention Pond | Completed | 1999 | Prior to 2012 | 22 | 6 | Hendry Creek | 29 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.520472 | -81.866328 | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | 9.979 | 0
EWCO | 2240 | FDOT District 1 | N/A | HC-FDOT-01b | Wet Detention Ponds (1, 2, and 3) Facility ID: 12010-3561-02 | Wet detention. | Wet Detention Pond | Completed | 1999 | Prior to 2012 | 41 | 10 | Hendry Creek | 30 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.525118 | -81.874415 | N/A |  | Structural | Completed | 2012 | Everglades West Coast
EWCO | 2244 | FDOT District 1 | N/A | HC-FDOT-01c | Wet Detention Ponds (1, 2, and 3) Facility ID: 12010-3561-03 | Wet detention. | Wet Detention Pond | Completed | 1999 | Prior to 2012 | 41 | 11 | Hendry Creek | 30 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.538196 | -81.874039 | N/A |  | Structural | Completed | 2012 | Everglades West Coast
EWCO | 2245 | FDOT District 1 | N/A | HC-FDOT-02 | Roadside Swales | Swale with ditch blocks. | Grass swales with swale blocks or raised culverts | Completed | N/A | Prior to 2012 | Not provided | Not provided | Hendry Creek | Not provided | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | Not provided | Not provided | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | TBD | TBD
EWCO | 2246 | FDOT District 1 | N/A | HC-FDOT-03 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | 2002 | N/A | 91 | 49 | Hendry Creek | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Not provided | Not provided | Not provided | N/A |  | Non-structural | Ongoing | 2012 | Everglades West Coast |  | 41.2769 | 22.226
EWCO | 2242 | FDOT District 1 | N/A | HC-FDOT-04 | Education Efforts | Pamphlets, PSAs, Illicit Discharge Program. | Education Efforts | Ongoing | 2004 | N/A | 3 | 0 | Hendry Creek | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Not provided | Not provided | Not provided | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | 1.3608 | 0
EWCO | 2247 | FDOT District 1 | N/A | IR-FDOT-01 | Wet Detention Ponds (Pond 5D) Facility ID: 12075-3500-02 | Wet detention. | Wet Detention Pond | Completed | 2010 | 2010 | 3 | 0 | Imperial River | 96 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.334811 | -81.748673 | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | 1.3608 | 0
EWCO | 2248 | FDOT District 1 | N/A | IR-FDOT-01b | Wet Detention Ponds (Pond 7C) Facility ID: 12075-3500-03 | Wet detention. | Wet Detention Pond | Completed | 2010 | 2010 | 6 | 0 | Imperial River | 96 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.334832 | -81.748518 | N/A |  | Structural | Completed | 2012 | Everglades West Coast
EWCO | 2254 | FDOT District 1 | N/A | IR-FDOT-01c | Wet Detention Ponds Pond 9B) Facility ID: 12075-3500-04 | Wet detention. | Wet Detention Pond | Completed | 2010 | 2010 | 9 | 0 | Imperial River | 96 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.352331 | -81.753769 | N/A |  | Structural | Completed | 2012 | Everglades West Coast
EWCO | 2253 | FDOT District 1 | N/A | IR-FDOT-02 | Roadside Swales | Swale with ditch blocks. | Grass swales with swale blocks or raised culverts | Completed | Not provided | Prior to 2012 | Not provided | Not provided | Imperial River | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | Not provided | Not provided | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | TBD | TBD
EWCO | 2251 | FDOT District 1 | N/A | IR-FDOT-03 | Education Efforts | Pamphlets, PSAs, Illicit Discharge Program. | Education Efforts | Ongoing | 2004 | N/A | 3 | 0 | Imperial River | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Not provided | Not provided | Not provided | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | 1.3608 | 0
EWCO | 2241 | Lee County | DEP/ SFWMD | HC-LC-01 | Lakes Park Water Quality Restoration | Retrofit Lakes Park to improve water quality of stormwater runoff by routing flows through a created filter marsh system. | Constructed Wetland Treatment | Completed | Prior to 2012 | 2016 | 4533 | 0 | Hendry Creek | 1749 | 3500000 | 59535 | County/ DEP/ SFWMD | DEP - $510,000/ SFWMD - $1,389,659 | S0604 | 4600002529 | 26.52899611 | -81.87968159 | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | 2056.1325 | 0
EWCO | 2250 | Lee County | N/A | HC-LC-02 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | Prior to 2012 | N/A | 167 | 29 | Hendry Creek | N/A | 694176 | 248572.3 | County | N/A | N/A | N/A | Not provided | Not provided | N/A |  | Non-structural | Ongoing | 2012 | Everglades West Coast |  | 76 | 0
EWCO | 2256 | Lee County | N/A | HC-LC-03 | Education/Fertilizer Ordinance | Public education on implementation of adopted fertilizer ordinance. | Education Efforts | Ongoing | Prior to 2012 | N/A | 1980 | 0 | Hendry Creek | N/A | 392441 | 125000 | County | County - $12,000 | NF060 | N/A | Not provided | Not provided | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | 898.1122 | 0
EWCO | 2249 | Lee County | N/A | HC-LC-04 | Island Park Filter Marsh | Wetland creation and enhancement that included exotic removal, filter marsh creation, and native replanting. | Constructed Wetland Treatment | Completed | Prior to 2012 | Prior to 2012 | TBD | TBD | Hendry Creek | 160 | 925000 | N/A | N/A | N/A | N/A | N/A | 26.483954 | -81.863409 | N/A |  | Structural | Completed | 2012 | Everglades West Coast |  | TBD | TBD
EWCO | 2266 | Lee County | N/A | HC-LC-05 | Lakes Park Littoral Zone Project | Creation of littoral shelves with native plantings for nutrient uptake. | Constructed Wetland Treatment | Completed | 2017 | 2018 | 79.3 | N/A | Hendry Creek | 39.4 | 1200000 | 29338 | County | County - $1,200,000 | N/A | N/A | 26.52899611 | -81.87968159 | N/A |  | Structural | Future | 2015 | Everglades West Coast |  | TBD | TBD
EWCO | 2306 | Lee County | N/A | HC-LC-06 | Hendry Creek West Branch Restoration | Create filter marsh on 11-acre site. | Constructed Wetland Treatment | Canceled | 2020 | 2021 | N/A | N/A | Hendry Creek | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26.52330366 | -81.87895739 | N/A |  | Structural | Future | 2015 | Everglades West Coast |  | #VALUE! | 0
EWCO | 5241 | Lee County | DEP | HC-LC-07 | Lakes Park Phase III | Filter marsh. | Constructed Wetland Treatment | Planned | 2021 | 2022 | TBD | TBD | Hendry Creek | 9.3 | 1700000 | TBD | County/ DEP | DEP - $475,000 | LP36022 | N/A | 26.52330366 | -81.87895739 | N/A |  | Structural | Future | 2015 | Everglades West Coast
EWCO | 5242 | Lee County | N/A | HC-LC-08 | Microbial Source Tracking in Lee County Waterways | Watershed study to investigate interactions between OSTDS and surface water in the Everglades West Coast BMAP. | Study | Underway | 2021 | 2021 | N/A | N/A | Hendry Creek | N/A | 645000 | N/A | County | N/A | N/A | N/A | 26.4884 | -81.8629 | N/A |  | Non-structural | Underway | 2019 | Everglades West Coast | 2
EWCO | 5757 | Lee County | N/A | HC-LC-09 | Master Wastewater Treatment Feasibility Analysis | Study to support the development of a County-wide Septic Conversion Master Plan (SCMP). | Study | Planned | 2021 | 2023 | N/A | N/A | Hendry Creek | N/A | TBD | N/A | County | N/A | N/A | N/A | TBD | TBD | N/A |  | Non-structural |  | 2020 | Everglades West Coast
EWCO | 2349 | Lee County | SFWMD/ FWC/ CREW Land and Water Trust | IR-LC-01 | CREW | Land purchase and conversion to conservation land use. | Land Use Change | Completed | Prior to 2012 | 2020 | 0 | 0 | Imperial River | 15 | 208818 | TBD | County | County - $208,818 | N/A | N/A | 26.381847 | -81.720250 | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | 0 | 0
EWCO | 2350 | Lee County | N/A | IR-LC-02 | Pine Lake Preserve | Land purchase and conversion to conservation land use. | Land Use Change | Completed | Prior to 2012 | Prior to 2012 | 1 | 0 | Imperial River | 129 | 2366273 | 42454 | County | County - $2,366,273 | N/A | N/A | 26.34288154 | -81.7409264 | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | 0.45359 | 0
EWCO | 2351 | Lee County | N/A | IR-LC-03 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | Prior to 2012 | N/A | 150 | 50 | Imperial River | N/A | 694176 | 248572.3 | County | N/A | N/A | N/A | Not provided | Not provided | N/A |  | Non-structural | Ongoing | 2012 | Everglades West Coast |  | 111 | 22.6796
EWCO | 2365 | Lee County | N/A | IR-LC-04 | Imperial Marsh Preserve | Land purchase and conversion to conservation land use. | Land Use Change | Completed | Prior to 2012 | 2020 | 1294 | N/A | Imperial River | 481.3 | 14640676 | N/A | County | $825,331 | N/A | N/A | 26.49027685 | -81.65320744 | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | 586.948 | 0
EWCO | 2353 | Lee County | N/A | IR-LC-05 | Education/Fertilizer Ordinance | Public education on implementation of adopted fertilizer ordinance. | Education Efforts | Ongoing | Prior to 2012 | N/A | 6 | 0 | Imperial River | N/A | 392441 | 125000 | County | County - $12,000 | NF060 | N/A | Not provided | Not provided | N/A |  | Non-structural | Completed | 2012 | Everglades West Coast |  | 2.7216 | 0
EWCO | 2342 | Lee County | City of Bonita Springs | IR-LC-06 | Pine Lake Preserve Rehydration Project | Joint project with Bonita Springs that will rehydrate and reestablish hydraulic connectivity between the Imperial River and the undisturbed CREW wetlands which lay to the east of the preserve on the Corkscrew Swamp. | Hydrologic Restoration | Underway | 2017 | 2022 | TBD | TBD | Imperial River | 173 | 900000 | TBD | County/ City of Bonita Springs | TBD | N/A | N/A | 26.34288154 | -81.7409264 | N/A |  | Structural | Ongoing | 2016 | Everglades West Coast | 1 | TBD | TBD
EWCO | 2355 | Lee County | N/A | IR-LC-07 | Larry Kiker Preserve | Land purchase and conversion to conservation land use. | Land Use Change | Completed | 2017 | 2017 | 149 | N/A | Imperial River | N/A | 42435000 | TBD | County | County - $42,435,000 | N/A | N/A | 26.40829073 | -81.7308365 | N/A |  | Non-structural | N/A | 2017 | Everglades West Coast
EWCO | 5243 | FDOT District 1 | N/A | IR-FDOT-04 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | Not provided | N/A | 34 | 19 | Imperial River | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Not provided | Not provided | Not provided | N/A |  | Non-structural | Completed | 2019 | Everglades West Coast
EWCO | 5758 | City of Bonita Springs | DEP | BS-13 | Felts Avenue Bio-Reactor Project Phase II | Continuous Withdrawal and Treatment of water from the Imperial River. Project will connect Felts Ave Bio-Reactor Phase I Project via pump and piping system to create a continuous flow treatment system. | Regional Stormwater Treatment | Underway | 2020 | 2022 | TBD | TBD | Imperial River | TBD | 800000 | TBD | City/ DEP | City of Bonita Springs - $400,000/ DEP - $400,000 | INV005 | N/A | 26.3332 | -81.6763 | N/A |  | Structural |  | 2020 | Everglades West Coast
EWCO | 5759 | Lee County | N/A | IR-LC-08 | Master Wastewater Treatment Feasibility Analysis | Study to support the development of a County-wide Septic Conversion Master Plan (SCMP). | Study | Planned | 2021 | 2023 | N/A | N/A | Imperial River | N/A | TBD | N/A | County | N/A | N/A | N/A | TBD | TBD | N/A |  | Non-structural |  | 2020 | Everglades West Coast
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Late submittal, will not be included this year. Need to follow-up w/COBS for verification materials

## Append Existing
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile
EWCO | 2326 | City of Bonita Springs | N/A | BS-01 | Fertilizer Ordinance | Ordinance. | Regulations, Ordinances, and Guidelines | Ongoing | Not provided | N/A | 696 | 0 | Imperial River | N/A | N/A | N/A | City | N/A | N/A | Not provided | N/A | N/A | N/A
EWCO | 2325 | City of Bonita Springs | N/A | BS-02 | Florida Yards and Neighborhood (FYN) Program | Education program utilizing the FYN Program. | Education Efforts | Ongoing | 2012 | N/A | 835 | 0 | Imperial River | N/A | Not provided | 3000 | City | Not provided | N/A | Not provided | N/A | N/A | N/A
EWCO | 2324 | City of Bonita Springs | N/A | BS-03 | Old 41 Catch Basin Inserts | Catch basin inserts. | Catch Basin Inserts/Inlet Filter Cleanout | Canceled | N/A | N/A | N/A | N/A | Imperial River | N/A | N/A | N/A | N/A | N/A | N/A | Not provided | 26.30980393 | -81.79348238 | N/A
EWCO | 2323 | City of Bonita Springs | N/A | BS-04 | Residential Dry Detention | Dry detention. | Dry Detention Pond | Completed | Not provided | Prior to 2012 | 1 | 0 | Imperial River | 4 | Not provided | Not provided | City | Not provided | N/A | N/A | Not provided | Not provided | N/A
EWCO | 2322 | City of Bonita Springs | N/A | BS-05 | Morton Avenue Swales | Dry retention. | Grass swales with swale blocks or raised culverts | Completed | Not provided | Prior to 2012 | 212 | 0 | Imperial River | 26 | Not provided | Not provided | City | Not provided | N/A | N/A | 26.35329715 | -81.75092032 | N/A
EWCO | 2321 | City of Bonita Springs | N/A | BS-06 | Marni Fields | Dry detention. | Dry Detention Pond | Completed | Not provided | Prior to 2012 | 6 | 0 | Imperial River | 16 | Not provided | Not provided | City | Not provided | N/A | N/A | 26.35014829 | -81.75538095 | N/A
EWCO | 2320 | City of Bonita Springs | N/A | BS-07 | Felts Avenue Stormwater Treatment | Dry detention. | Dry Detention Pond | Completed | Not provided | Prior to 2012 | 258 | 0 | Imperial River | 31 | Not provided | Not provided | City | Not provided | N/A | N/A | 26.34206819 | -81.77807294 | N/A
EWCO | 2319 | City of Bonita Springs | N/A | BS-08 | Street Sweeping | Monthly street sweeping. | Street Sweeping | Ongoing | 2010 | N/A | 161 | 103 | Imperial River | N/A | Not provided | 22000 | City | Not provided | N/A | Not provided | N/A | N/A | N/A
EWCO | 2341 | City of Bonita Springs | DEP/ SFWMD | BS-09 | Felts Avenue Bio-Reactor Project | Utilize woodchips in an anaerobic environment to strip nitrogen from incoming stormwater. The 40-acre watershed will be treated on a 2-acre site on Felts Ave. | BMP Treatment Train | Completed | 2017 | 2017 | TBD | TBD | Imperial River | 40 | 623389 | Not provided | DEP/ SFWMD/ City | Not provided | SO772 | Not provided | Not provided | Not provided | N/A
EWCO | 2333 | City of Bonita Springs | Lee County | BS-10 | Pine Lake Preserve Rehydration Project | Joint project with Lee County that will rehydrate and reestablish hydraulic connectivity between the Imperial River and the undisturbed Corkscrew Regional Ecosystem Watershed (CREW) wetlands to the east of the preserve on the Corkscrew Swamp. | Hydrologic Restoration | Underway | 2017 | TBD | TBD | TBD | Imperial River | 173 | Not provided | Not provided | City | Not provided | N/A | Not provided | Not provided | Not provided | N/A
EWCO | 2334 | City of Bonita Springs | N/A | BS-11 | Downtown Redevelopment Drainage Project | Created two miles of interconnected drainage infrastructure to improve water quality through the use of exfiltration trenches. A total of 8.84 acre feet of exfiltration storage is provided by the project. | BMP Treatment Train | Completed | 2016 | 2016 | Not provided | Not provided | Imperial River | 83.29 | 6330000 | Not provided | City | Not provided | N/A | N/A | Not provided | Not provided | N/A
EWCO | 2335 | City of Bonita Springs | N/A | BS-12 | Septic System Removal | Conversion of septic systems to central sewer. | OSTDS Phase Out | Completed | 2001 | 2016 | 912 | Not provided | Imperial River | N/A | 17205 | Not provided | City | Not provided | N/A | N/A | Not provided | Not provided | N/A
EWCO | 2336 | FDACS | Agricultural Producers | FDACS-01 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on FDEP spreadsheet loading model. Acres treated based on FDACS OAWP December 2020 Enrollment and FSAID VII. | Agricultural BMPs | Completed | N/A | N/A | 0 | N/A | Hendry Creek | 0 | N/A | N/A | FDACS | TBD | N/A | N/A | N/A | N/A | N/A | Y
EWCO | 2337 | FDACS | Agricultural Producers | FDACS-02 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on FDEP spreadsheet loading model. Acres treated based on FDACS OAWP December 2020 Enrollment and FSAID VII. | Agricultural BMPs | Completed | N/A | N/A | 10893 | N/A | Imperial River | 5571.9322 | N/A | N/A | FDACS | TBD | N/A | N/A | N/A | N/A | N/A | Y
EWCO | 2338 | FDOT District 1 | N/A | HC-FDOT-01 | Wet Detention Ponds (1, 2, and 3) Facility ID: 12010-3561-01 | Wet detention. | Wet Detention Pond | Completed | 1999 | Prior to 2012 | 22 | 6 | Hendry Creek | 29 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.520472 | -81.866328 | N/A
EWCO | 2240 | FDOT District 1 | N/A | HC-FDOT-01b | Wet Detention Ponds (1, 2, and 3) Facility ID: 12010-3561-02 | Wet detention. | Wet Detention Pond | Completed | 1999 | Prior to 2012 | 41 | 10 | Hendry Creek | 30 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.525118 | -81.874415 | N/A
EWCO | 2244 | FDOT District 1 | N/A | HC-FDOT-01c | Wet Detention Ponds (1, 2, and 3) Facility ID: 12010-3561-03 | Wet detention. | Wet Detention Pond | Completed | 1999 | Prior to 2012 | 41 | 11 | Hendry Creek | 30 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.538196 | -81.874039 | N/A
EWCO | 2245 | FDOT District 1 | N/A | HC-FDOT-02 | Roadside Swales | Swale with ditch blocks. | Grass swales with swale blocks or raised culverts | Completed | N/A | Prior to 2012 | Not provided | Not provided | Hendry Creek | Not provided | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | Not provided | Not provided | N/A
EWCO | 2246 | FDOT District 1 | N/A | HC-FDOT-03 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | 2002 | N/A | 91 | 49 | Hendry Creek | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Not provided | N/A | N/A | N/A
EWCO | 2242 | FDOT District 1 | N/A | HC-FDOT-04 | Education Efforts | Pamphlets, PSAs, Illicit Discharge Program. | Education Efforts | Ongoing | 2004 | N/A | 3 | 0 | Hendry Creek | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Not provided | N/A | N/A | N/A
EWCO | 2247 | FDOT District 1 | N/A | IR-FDOT-01 | Wet Detention Ponds (Pond 5D) Facility ID: 12075-3500-02 | Wet detention. | Wet Detention Pond | Completed | 2010 | 2010 | 3 | 0 | Imperial River | 96 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.334811 | -81.748673 | N/A
EWCO | 2248 | FDOT District 1 | N/A | IR-FDOT-01b | Wet Detention Ponds (Pond 7C) Facility ID: 12075-3500-03 | Wet detention. | Wet Detention Pond | Completed | 2010 | 2010 | 6 | 0 | Imperial River | 96 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.334832 | -81.748518 | N/A
EWCO | 2254 | FDOT District 1 | N/A | IR-FDOT-01c | Wet Detention Ponds Pond 9B) Facility ID: 12075-3500-04 | Wet detention. | Wet Detention Pond | Completed | 2010 | 2010 | 9 | 0 | Imperial River | 96 | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | 26.352331 | -81.753769 | N/A
EWCO | 2253 | FDOT District 1 | N/A | IR-FDOT-02 | Roadside Swales | Swale with ditch blocks. | Grass swales with swale blocks or raised culverts | Completed | Not provided | Prior to 2012 | Not provided | Not provided | Imperial River | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | N/A | Not provided | Not provided | N/A
EWCO | 2251 | FDOT District 1 | N/A | IR-FDOT-03 | Education Efforts | Pamphlets, PSAs, Illicit Discharge Program. | Education Efforts | Ongoing | 2004 | N/A | 3 | 0 | Imperial River | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Not provided | N/A | N/A | N/A
EWCO | 2241 | Lee County | DEP/ SFWMD | HC-LC-01 | Lakes Park Water Quality Restoration | Retrofit Lakes Park to improve water quality of stormwater runoff by routing flows through a created filter marsh system. | Constructed Wetland Treatment | Completed | Prior to 2012 | 2016 | 4533 | 0 | Hendry Creek | 1749 | 3500000 | 59535 | County/ DEP/ SFWMD | DEP - $510,000/ SFWMD - $1,389,659 | S0604 | 4600002529 | 26.52899611 | -81.87968159 | N/A
EWCO | 2250 | Lee County | N/A | HC-LC-02 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | Prior to 2012 | N/A | 167 | 29 | Hendry Creek | N/A | 694176 | 248572.3 | County | N/A | N/A | N/A | N/A | N/A | N/A
EWCO | 2256 | Lee County | N/A | HC-LC-03 | Education/Fertilizer Ordinance | Public education on implementation of adopted fertilizer ordinance. | Education Efforts | Ongoing | Prior to 2012 | N/A | 1980 | 0 | Hendry Creek | N/A | 392441 | 125000 | County | County - $12,000 | NF060 | N/A | N/A | N/A | N/A
EWCO | 2249 | Lee County | N/A | HC-LC-04 | Island Park Filter Marsh | Wetland creation and enhancement that included exotic removal, filter marsh creation, and native replanting. | Constructed Wetland Treatment | Completed | Prior to 2012 | Prior to 2012 | TBD | TBD | Hendry Creek | 160 | 925000 | N/A | N/A | N/A | N/A | N/A | 26.483954 | -81.863409 | N/A
EWCO | 2266 | Lee County | N/A | HC-LC-05 | Lakes Park Littoral Zone Project | Creation of littoral shelves with native plantings for nutrient uptake. | Constructed Wetland Treatment | Completed | 2017 | 2018 | 79.3 | N/A | Hendry Creek | 39.4 | 1200000 | 29338 | County | County - $1,200,000 | N/A | N/A | 26.52899611 | -81.87968159 | N/A
EWCO | 2306 | Lee County | N/A | HC-LC-06 | Hendry Creek West Branch Restoration | Create filter marsh on 11-acre site. | Constructed Wetland Treatment | Canceled | 2020 | 2021 | N/A | N/A | Hendry Creek | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26.52330366 | -81.87895739 | N/A
EWCO | 5241 | Lee County | DEP | HC-LC-07 | Lakes Park Phase III | Filter marsh. | Constructed Wetland Treatment | Planned | 2021 | 2022 | TBD | TBD | Hendry Creek | 9.3 | 1700000 | TBD | County/ DEP | DEP - $475,000 | LP36022 | N/A | 26.52330366 | -81.87895739 | N/A
EWCO | 5242 | Lee County | N/A | HC-LC-08 | Microbial Source Tracking in Lee County Waterways | Watershed study to investigate interactions between OSTDS and surface water in the Everglades West Coast BMAP. | Study | Underway | 2021 | 2021 | N/A | N/A | Hendry Creek | N/A | 645000 | N/A | County | N/A | N/A | N/A | 26.47822 | -81.81365 | N/A
EWCO | 2349 | Lee County | SFWMD/ FWC/ CREW Land and Water Trust | IR-LC-01 | CREW | Land purchase and conversion to conservation land use. | Land Use Change | Completed | Prior to 2012 | 2020 | 0 | 0 | Imperial River | 15 | 208818 | TBD | County | County - $208,818 | N/A | N/A | 26.381847 | -81.720250 | N/A
EWCO | 2350 | Lee County | N/A | IR-LC-02 | Pine Lake Preserve | Land purchase and conversion to conservation land use. | Land Use Change | Completed | Prior to 2012 | Prior to 2012 | 1 | 0 | Imperial River | 129 | 2366273 | 42454 | County | County - $2,366,273 | N/A | N/A | 26.34288154 | -81.7409264 | N/A
EWCO | 2351 | Lee County | N/A | IR-LC-03 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | Prior to 2012 | N/A | 150 | 50 | Imperial River | N/A | 694176 | 248572.3 | County | N/A | N/A | N/A | N/A | N/A | N/A
EWCO | 2365 | Lee County | N/A | IR-LC-04 | Imperial Marsh Preserve | Land purchase and conversion to conservation land use. | Land Use Change | Completed | Prior to 2012 | 2020 | 1294 | N/A | Imperial River | 481.3 | 14640676 | N/A | County | $825,331 | N/A | N/A | 26.49027685 | -81.65320744 | N/A
EWCO | 2353 | Lee County | N/A | IR-LC-05 | Education/Fertilizer Ordinance | Public education on implementation of adopted fertilizer ordinance. | Education Efforts | Ongoing | Prior to 2012 | N/A | 6 | 0 | Imperial River | N/A | 392441 | 125000 | County | County - $12,000 | NF060 | N/A | N/A | N/A | N/A
EWCO | 2342 | Lee County | City of Bonita Springs | IR-LC-06 | Pine Lake Preserve Rehydration Project | Joint project with Bonita Springs that will rehydrate and reestablish hydraulic connectivity between the Imperial River and the undisturbed CREW wetlands which lay to the east of the preserve on the Corkscrew Swamp. | Hydrologic Restoration | Underway | 2017 | 2022 | TBD | TBD | Imperial River | 173 | 900000 | TBD | County/ City of Bonita Springs | TBD | N/A | N/A | 26.34288154 | -81.7409264 | N/A
EWCO | 2355 | Lee County | N/A | IR-LC-07 | Larry Kiker Preserve | Land purchase and conversion to conservation land use. | Land Use Change | Completed | 2017 | 2017 | 149 | N/A | Imperial River | N/A | 42435000 | TBD | County | County - $42,435,000 | N/A | N/A | 26.40829073 | -81.7308365 | N/A
EWCO | 5243 | FDOT District 1 | N/A | IR-FDOT-04 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | Not provided | N/A | 34 | 19 | Imperial River | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Not provided | N/A | N/A | N/A
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Late submittal, will not be included this year. Need to follow-up w/COBS for verification materials

## Load Reductions
Entity-Specific Load Reductions
ProjectStatus | (Multiple Items)
Row Labels | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr) | Total TN Required Reduction (lbs/yr) | TN Reductions Still Needed (lbs/yr) | Total TN Required Reductions Achieved (%)
Hendry Creek | 6957.3 | 105 | 10320 | 3362.7 | 67.42%
FDACS | 0 | 0 | 173 | 173 | 0%
FDOT District 1 | 198 | 76 | 63 | -135 | 314.3% | Count of ProjectStatus | Column Labels
Lee County | 6759.3 | 29 | 10084 | 3324.7 | 67.03% | Row Labels | Canceled | Completed | Planned | Underway | Ongoing | Grand Total
Imperial River | 15629 | 172 | 60124 | 44495 | 25.99% | Hendry Creek | 1 | 8 | 2 | 1 | 4 | 16
City of Bonita Springs | 3081 | 103 | 9903 | 6822 | 31.11% | Imperial River | 1 | 16 | 1 | 3 | 7 | 28
FDACS | 10893 | 0 | 48570 | 37677 | 22.43% | Grand Total | 2 | 24 | 3 | 4 | 11 | 44
FDOT District 1 | 55 | 19 | 95 | 40 | 57.89%
Lee County | 1600 | 50 | 1556 | -44 | 102.8%
Grand Total | 22586.3 | 277 | 70444 | 47857.7 | 32.06%

## TN Progress Chart
ProjectStatus | (Multiple Items)
Hendry Creek
Row Labels | Sum of TNReduction(lbs/yr) | Year | Cumulative TN Reductions (lbs/yr) | 5-Year Milestone | 10-Year Milestone | Total Reductions Required
Hendry Creek | 6957.3 | 2012 | 2345 |  |  | 10320
2016 | 4533 | 2013 | 2345 |  |  | 10320
2018 | 79.3 | 2014 | 2345 |  |  | 10320
N/A | 2241 | 2015 | 2345 |  |  | 10320
Prior to 2012 | 104 | 2016 | 6878 |  |  | 10320
Imperial River | 15629 | 2017 | 6878 |  |  | 10320
2010 | 18 | 2018 | 6957.3 |  |  | 10320
2016 | 912 | 2019 | 6957.3 |  |  | 10320
2017 | 149 | 2020 |  |  |  | 10320
2020 | 1294 | 2021 |  |  |  | 10320
N/A | 12778 | 2022 |  |  |  | 10320
Prior to 2012 | 478 | 2023 |  |  |  | 10320
Grand Total | 22586.3 | 2024 |  |  |  | 10320
|  | 2025 |  |  |  | 10320
|  | 2026 |  |  |  | 10320
|  | 2027 |  |  |  | 10320
|  | 2028 |  |  |  | 10320
|  | 2029 |  |  |  | 10320
|  | 2030 |  |  |  | 10320
|  | 2031 |  |  |  | 10320
|  | 2032 |  |  |  | 10320
Imperial River
|  | Year | Cumulative TN Reductions (lbs/yr) | 5-Year Milestone | 10-Year Milestone | Total Reductions Required
|  | 2012 | 13274 |  |  | 60124
|  | 2013 | 13274 |  |  | 60124
|  | 2014 | 13274 |  |  | 60124
|  | 2015 | 13274 |  |  | 60124
|  | 2016 | 14186 |  |  | 60124
|  | 2017 | 14335 |  |  | 60124
|  | 2018 | 14335 |  |  | 60124
|  | 2019 | 14335 |  |  | 60124
|  | 2020 | 15629 |  |  | 60124
|  | 2021 |  |  |  | 60124
|  | 2022 |  |  |  | 60124
|  | 2023 |  |  |  | 60124
|  | 2024 |  |  |  | 60124
|  | 2025 |  |  |  | 60124
|  | 2026 |  |  |  | 60124
|  | 2027 |  |  |  | 60124
|  | 2028 |  |  |  | 60124
|  | 2029 |  |  |  | 60124
|  | 2030 |  |  |  | 60124
|  | 2031 |  |  |  | 60124
|  | 2032 |  |  |  | 60124

## Summary Info
ProjectStatus | (Multiple Items) |  |  |  |  | ProjectStatus | (Multiple Items)
Row Labels | Sum of CostEstimate | Sum of CostAnnualO&M | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr) | Count of ProjectStatus | Row Labels | Sum of CostEstimate | Sum of CostAnnualO&M | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr)
Hendry Creek | 6711617 | 462445.3 | 6957.3 | 105 | 12 | Hendry Creek | 2345000 | 0 | 0 | 0
Imperial River | 67707978 | 441026.3 | 15629 | 172 | 23 | Imperial River | 1700000 | 0 | 0 | 0
Grand Total | 74419595 | 903471.6 | 22586.3 | 277 | 35 | Grand Total | 4045000 | 0 | 0 | 0
Row Labels | Count of Year Added |  | Row Labels | Count of ProjectStatus
2012 | 28 |  | Canceled | 2
Hendry Creek | 10 |  | Completed | 24
Imperial River | 18 |  | Planned | 3
2015 | 5 |  | Underway | 4
Hendry Creek | 3 |  | Ongoing | 11
Imperial River | 2 |  | Grand Total | 44
2016 | 5
Hendry Creek | 1
Imperial River | 4
2017 | 1
Imperial River | 1
2019 | 2
Hendry Creek | 1
Imperial River | 1
2020 | 3
Hendry Creek | 1
Imperial River | 2
Grand Total | 44

## Project Type Check 031021
ProjectType | Structural/Non Structural | Project Type | Structural/Non Structural | Min/Max of Project IDs | Sum of ProjID | Count of ProjID
Regulations, Ordinances, and Guidelines | Non-structural | 100% On-site Retention | Structural | 2240 | 103163 | 41
Education Efforts | Non-structural | Agricultural BMPs | Use Past Designation | 5758
Catch Basin Inserts/Inlet Filter Cleanout | Non-structural | Aquatic Vegetation Harvesting | Non-structural
Dry Detention Pond | Structural | Baffle Boxes- First Generation | Structural
Grass swales with swale blocks or raised culverts | Structural | Baffle Boxes- Second Generation | Structural
Street Sweeping | Non-structural | Baffle Boxes- Second Generation with Media | Structural
BMP Treatment Train | Structural | Biosorption Activated Media (BAM) | Structural
Hydrologic Restoration | Structural | Bioswales | Structural
OSTDS Phase Out | Structural | BMP Cleanout | Non-structural
Agricultural BMPs | Use Past Designation | BMP Missing from Model | Use Past Designation
Wet Detention Pond | Structural | BMP Treatment Train | Structural
Constructed Wetland Treatment | Structural | Catch Basin Inserts/Inlet Filter Cleanout | Non-structural
Study | Non-structural | Constructed Wetland Treatment | Structural
Land Use Change | Non-structural | Control Structure | Structural
Regional Stormwater Treatment | Structural | Creating/ Enhancing Living Shoreline | Structural
|  | Creating/ Enhancing Oyster Reefs | Structural
|  | Credit Trade | Trade
|  | Dairy Remediation | Structural
|  | Decommission/ Abandonment | Structural
|  | Denitrification Walls | Structural
|  | Dispersed Water Management (DWM) | Structural
|  | Dry Detention Pond | Structural
|  | Education Efforts | Non-structural
|  | Enhanced Public Education | Non-structural
|  | Exfiltration Trench | Structural
|  | Exotic Vegetation Removal | Non-structural
|  | Fertilizer Cessation | Non-structural
|  | Fertilizer Reduction | Non-structural
|  | Fish Harvesting | Non-structural
|  | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Structural
|  | Golf Course or Sports Field BMPs | Non-structural
|  | Grass swales with swale blocks or raised culverts | Structural
|  | Grass swales without swale blocks or raised culverts | Structural
|  | Hybrid wetland treatment technology (HWTT) | Structural
|  | Hydrodynamic Separators | Structural
|  | Hydrologic Restoration | Structural
|  | Impoundment | Structural
|  | In Waterbody - Alum Injection System | Structural
|  | In Waterbody - Biological/ Bacteria Treatment | Non-structural
|  | Industrial Facility Upgrades | Structural
|  | Land Acquisition | Non-structural
|  | Land Preservation | Non-structural
|  | Land Use Change | Non-structural
|  | LID- Green Roofs | Structural
|  | LID- Other | Structural
|  | LID- Rain Gardens | Structural
|  | LID- Tree Boxes/Tree Wells | Structural
|  | Macroalgal Harvesting | Non-structural
|  | Monitoring/Data Collection | Non-structural
|  | Muck Removal/Restoration Dredging | Non-structural
|  | Natural Wetlands as Filters | Non-structural
|  | Non-contributing Basin | Non-structural
|  | Off-line Retention BMPs | Structural
|  | On-line Retention BMPs | Structural
|  | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Structural
|  | OSTDS Phase Out | Structural
|  | Pervious Pavement Systems | Structural
|  | Plugging Artesian Wells | Structural
|  | Regional Stormwater Treatment | Structural
|  | Regulations, Ordinances, and Guidelines | Non-structural
|  | Retention/Detention BMP Retrofit with Nutrient Reducing Media | Structural
|  | Retention/Detention BMP with Nutrient Reducing Media | Structural
|  | Sanitary Sewer - Alum Injection System | Structural
|  | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Structural
|  | Sanitary Sewer Inspections | Non-structural
|  | SAV Planting | Structural
|  | Shoreline Stabilization | Structural
|  | Stormwater - Alum Injection System | Structural
|  | Stormwater - Biological/ Bacteria Treatment | Non-structural
|  | Stormwater - Deep Injection Well | Structural
|  | Stormwater Aeration System | Structural
|  | Stormwater Reuse | Structural
|  | Stormwater System Rehabilitation | Structural
|  | Stormwater System Upgrade | Structural
|  | Stormwater Treatment Areas (STAs) | Structural
|  | Street Sweeping | Non-structural
|  | Study | Non-structural
|  | Turbidity Reducing Polymers (e.g., Floc logs ®) | Non-structural
|  | Vegetated Buffers | Structural
|  | Wastewater - Deep Injection Well | Structural
|  | Wastewater Service Area Expansion | Structural
|  | Wet Detention Pond | Structural
|  | Wetland Restoration | Structural
|  | WWTF Disposal Site | Structural
|  | WWTF Diversion to Reuse | Structural
|  | WWTF Nutrient Reduction | Structural
|  | WWTF Upgrade | Structural
|  | FIB- OSTDS | Use Past Designation
|  | FIB- Sanitary Sewer | Use Past Designation
|  | FIB- Source Identification Activities | Use Past Designation
|  | FIB- Stormwater | Use Past Designation
|  | FIB- Trash Cleanup of Impaired Waterbody | Use Past Designation
Note on D64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cocoa NIRL,

## Storymap Table
[7 empty] | LeadEntity | Completed | Ongoing | Planned | Underway | Total
[7 empty] | City of Bonita Springs | 7 | 3 | 0 | 2 | 12
Count of ProjectNumber |  | ProjectStatus |  |  |  |  | FDACS | 2 | 0 | 0 | 0 | 2
Location | LeadEntity | Completed | Ongoing | Planned | Underway | Grand Total | FDOT District 1 | 8 | 4 | 0 | 0 | 12
Hendry Creek | FDACS | 1 |  |  |  | 1 | Lee County | 7 | 4 | 3 | 2 | 16
| FDOT District 1 | 4 | 2 |  |  | 6 | Grand Total | 24 | 11 | 3 | 4 | 42
| Lee County | 3 | 2 | 2 | 1 | 8
Imperial River | City of Bonita Springs | 7 | 3 |  | 2 | 12 | Location | LeadEntity | Completed | Ongoing | Planned | Underway | Grand Total
| FDACS | 1 |  |  |  | 1 | Hendry Creek | FDACS | 1 | 0 | 0 | 0 | 1
| FDOT District 1 | 4 | 2 |  |  | 6 |  | FDOT District 1 | 4 | 2 | 0 | 0 | 6
| Lee County | 4 | 2 | 1 | 1 | 8 |  | Lee County | 3 | 2 | 2 | 1 | 8
Grand Total |  | 24 | 11 | 3 | 4 | 42 | Imperial River | City of Bonita Springs | 7 | 3 | 0 | 2 | 12
[8 empty] | FDACS | 1 | 0 | 0 | 0 | 1
[8 empty] | FDOT District 1 | 4 | 2 | 0 | 0 | 6
[8 empty] | Lee County | 4 | 2 | 1 | 1 | 8
[7 empty] | Grand Total |  | 24 | 11 | 3 | 4 | 42