## Sheet1
Facility | App Due Date | Primary Permitter | Lab Data | OMPR Inspection | OMPR Report | Application | Check | Table 14 Data | Application Submitted | RAI | Draft Permit | Final Permit Issued | Final Permit Effective | Permit Matrix | Stakeholder Meeting | DMR
Ponte Vedra | 2018-03-29 | Ed | Done | Done | Done | Done | Done | Done | Yes | No | Issued | 2018-08-15 | 2018-09-26 | Done | Done
Aggregate | 2018-09-11 | Ed | N/A | N/A | N/A | Done | Done | N/A | Yes | No | Issued | 2018-09-25 | 2019-03-11 |  | N/A
Nassau | 2018-09-24 | Katie | Done | Done | Done | Done | Done | Done | Yes | Responded | Issued | 2019-07-31 | 2019-07-31
Buckman | 2018-10-22 | Ed | Done | Done | Done | Done | Done | Done | Yes | Responded | Issued | 2019-06-13 | 2019-06-13
Monterey | 2018-10-25 | Ed | Done | Done | Done | Done | Done | Done | Yes | Responded | Issued | 2019-05-31 | 2019-05-31
Arlington East | 2018-11-06 | Ed | Done | Done | Done | Done | Done | Done | Yes | Responded | Issued | 2019-07-01 | 2019-07-01
District II | 2018-11-11 | Katie | Done | Done | Done | Done | Done | Done | Yes | Responded | Issued | 2019-06-12 | 2019-06-12
Mandarin | 2018-11-11 | Katie | Done | Done | Done | Done | Done | Done | Yes | Responded | Issued | 2019-07-01 | 2019-07-01
JCP | 2018-11-12 | Jaclyn | Done | Done | Done | Done | Done | Done | Yes | Responded | Issued | 2019-06-12 | 2019-06-12
Southwest | 2018-11-22 | Ed | Done | Done | Done | Done | Done | Done | Yes | No | Issued | 2019-04-29 | 2019-05-21 | Done | N/A
Ponce de Leon | 2019-05-19 | Ed | Done | Done | Done | Done | Done | N/A | Yes | Yes | Issued | 2019-09-16 | 2019-11-16

## Sheet2
Facility | Permit | Expiration Date | Status | Renewal Dates | TP Limits | TN Limits
Aggregate | FL0620564 | 2024-03-10 | In Renewal | 2023-09-10 | 463.5 Tons TP/yr | 683.2 Tons TN/yr | agg=plant discharge loadings are aggregated as part of aggregate permit
Arlington East | FL0026441 | 2024-06-30 | Active | 2024-01-02 | agg | agg
Blacks Ford | FL017441 |  |  |  | 1/1.25/1.5/2.0 + 8,823 lbs/yr | 3/3.75/4.5/6 + 26,467 lbs/yr | Annual Avg./monthly avg. /weekly avg./Single sample max (mg/l)
Buckman | FL0026000 | 2024-06-12 | In Renewal | 2023-12-15 | agg | agg
District II | FL0026450 | 2024-06-11 | In Renewal | 2023-12-14 | agg | agg
Greenland | FL0A00023 | 2027-02-09 | Active | 2026-08-13 | 1/1.25/1.5/2.0 + agg | 3/3.75/4.5/6 +agg | Annual Avg./monthly avg. /weekly avg./Single sample max (mg/l)
JCP | FL0043591 | 2024-06-11 | In Renewal | 2023-12-14 | 3.0 mg/l max + agg | 6/7.5/9.0/12.0 + agg | Annual Avg./monthly avg. /weekly avg./Single sample max (mg/l)
Mandarin | FL0023493 | 2024-06-30 | Active | 2024-01-02 | agg | 5.34/6.68/8.01/10.68 + agg | Annual Avg./monthly avg. /weekly avg./Single sample max (mg/l)
Monterey | FL0023604 | 2024-05-30 | In Renewal | 2023-12-02 | agg | agg
Nassau | FL0116793 | 2024-07-30 | Active | 2024-02-01 | 1/1.25/1.5/2.0 | 3/3.75/4.5/6 | Annual Avg./monthly avg. /weekly avg./Single sample max (mg/l)
Ponce de Leon | FLA011773 | 2024-11-15 | Active | 2024-05-19 | n/a | n/a
Ponte Vedra | FL0117951 | 2023-09-25 | In Renewal | 2023-03-25 | 3445 lbs/yr | 7920 lbs/yr
Southwest | FL0026468 | 2024-05-20 | In Renewal | 2023-11-22 | agg | agg
Shaded selections are St. Johns or Nassau Co. Plants
Formulas:
Renewal Dates = [Expiration Date]-180