## 2017
NA
NA | [11 empty] | 2017 - Sample Requirements |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  | SEP |  |  | OCT |  |  |  | NOV |  |  |  | DEC
Group | Group Name | waterSegmentName | County | Group Responsible for Sample Collection | WBID | ENR | Body | Class | Sampling Requirements | Original n | Adjusted n | Sample Size/Frequency Notes (Minimum) | Sample Before June 30, 2017 | Sampling Notes | Priority | [45 empty] | Total Samples Collected | Remaining Samples To Be Collected | Notes
Group 1 | Everglades West Coast | C-139 | Hendry | SD | 3255 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 17 | [7 empty] | 1 | [19 empty] | 1 |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  | 5 | 0
Group 1 | Everglades West Coast | Hendry Creek | Lee | SD | 3258B2 | ENRDA | ESTUARY | 3M | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRDA | 100 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 1 | Everglades West Coast | Hendry Creek | Lee | SD | 3258B2 | ENRDA | ESTUARY | 3M | Bacteria Class 3M Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRDA | 100 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 1 | Everglades West Coast | Hendry Creek | Lee | SD | 3258B2 | ENRDA | ESTUARY | 3M | Tracers | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRDA | 100 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0 | 3/28/17 samples uploaded to storet 6/19/17 SO-DIST-2017-03-29-01
Group 1 | Everglades West Coast | Hendry Creek | Lee | SD | 3258B2 | ENRDA | ESTUARY | 3M | Markers | 5 | 5 | PCR-FILTER |  | ENRDA | 100 | [21 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  | 1 |  | 5 | 0 | No markers taken 3/28/17
Group 1 | Everglades West Coast | Mullock Creek | Lee | SD | 3258C2 |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 69 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 1 | Everglades West Coast | Imperial River | Lee | SD | 3258EA |  | STREAM | 3F | Kit A | 1 | 3 | Kit With Biology |  | Pick a site with macrophytes if possible. | 40 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 | [15 empty] | 3 | 0
Group 1 | Everglades West Coast | Imperial River | Lee | SD | 3258EA |  | STREAM | 3F | RPS | 1 | 1 | Kit With Biology |  | Pick a site with macrophytes if possible. | 40 | [11 empty] | 1 | [33 empty] | 1 | 0
Group 1 | Everglades West Coast | Imperial River | Lee | SD | 3258EA |  | STREAM | 3F | LVS | 1 | 1 | Kit With Biology |  | Pick a site with macrophytes if possible. | 40 | [11 empty] | 1 | [33 empty] | 1 | 0
Group 1 | Everglades West Coast | Imperial River | Lee | SD | 3258EA |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  | Pick a site with macrophytes if possible. | 40 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 | [11 empty] | 1 |  | 1 |  | 5 | 0
Group 1 | Everglades West Coast | Imperial River | Lee | SD | 3258EA |  | STREAM | 3F | Tracers | 5 | 5 | n=5, weeks=5, quarters=3 |  | Pick a site with macrophytes if possible. | 40 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 | [11 empty] | 1 |  | 1 |  | 5 | 0 | 3/28/17 samples uploaded to storet 6/19/17 SO-DIST-2017-03-29-01
Group 1 | Everglades West Coast | Imperial River | Lee | SD | 3258EA |  | STREAM | 3F | Markers | 5 | 4 | PCR-FILTER |  | Pick a site with macrophytes if possible. | 40 | [11 empty] | 0 | [9 empty] | 1 | [7 empty] | 1 | [11 empty] | 1 |  | 1 |  | 4 | 0 | No markers taken 3/28/17
Group 1 | Everglades West Coast | Imperial River (marine Segment) | Lee | SD | 3258EB | ENRDA | ESTUARY | 3M | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRDA | 100 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 1 | Everglades West Coast | Imperial River (marine Segment) | Lee | SD | 3258EB | ENRDA | ESTUARY | 3M | Bacteria Class 3M Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRDA | 100 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 1 | Everglades West Coast | Imperial River (marine Segment) | Lee | SD | 3258EB | ENRDA | ESTUARY | 3M | Tracers | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRDA | 100 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0 | 3/28/17 samples uploaded to storet 6/19/17 SO-DIST-2017-03-29-01
Group 1 | Everglades West Coast | Imperial River (marine Segment) | Lee | SD | 3258EB | ENRDA | ESTUARY | 3M | Markers | 5 | 5 | PCR-FILTER |  | ENRDA | 100 | [21 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | 1 |  |  | 5 | 0 | No markers taken 3/28/17
Group 1 | Everglades West Coast | Oak Creek | Collier, Lee | SD | 3258F |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 58 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 1 | Everglades West Coast | Oak Creek | Collier, Lee | SD | 3258F |  | STREAM | 3F | SCI | 1 | 1 | Kit With Biology |  |  | 58 | [45 empty] | 0 | 1 | Too low for biology 3/28/17
Group 1 | Everglades West Coast | Oak Creek | Collier, Lee | SD | 3258F |  | STREAM | 3F | RPS | 1 | 1 | Kit With Biology |  |  | 58 | [45 empty] | 0 | 1 | Too low for biology 3/28/17
Group 1 | Everglades West Coast | Oak Creek | Collier, Lee | SD | 3258F |  | STREAM | 3F | LVS | 1 | 1 | Kit With Biology |  |  | 58 | [45 empty] | 0 | 1 | Too low for biology 3/28/17
Group 1 | Everglades West Coast | Oak Creek | Collier, Lee | SD | 3258F |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 58 | [11 empty] | 1 | [9 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 1 | Everglades West Coast | Ten Mile Canal | Lee | SD | 3258G1 |  | STREAM | 3F | Kit A | 2 | 2 | Kit with Biology |  |  | 21 |  |  | 1 | [26 empty] | 1 | [15 empty] | 2 | 0
Group 1 | Everglades West Coast | Ten Mile Canal | Lee | SD | 3258G1 |  | STREAM | 3F | RPS | 2 | 2 | Kit With Biology |  |  | 21 |  |  | 1 | [26 empty] | 1 | [15 empty] | 2 | 0
Group 1 | Everglades West Coast | Ten Mile Canal | Lee | SD | 3258G1 |  | STREAM | 3F | LVS | 2 | 2 | Kit With Biology |  |  | 21 |  |  | 1 | [26 empty] | 1 | [15 empty] | 2 | 0
Group 1 | Everglades West Coast | COCOHATCHEE RIVER | Collier | SD | 3259A | ENRDB | ESTUARY | 2 | Tracers | 5 | 7 | n=5, weeks=5, quarters=3 |  | ENRDB | 50 | [12 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 1 | [7 empty] | 7 | 0 | Other Agency: Collected by Collier County. Bact analyses by county lab
Group 1 | Everglades West Coast | COCOHATCHEE RIVER | Collier | SD | 3259A | ENRDB | ESTUARY | 2 | Markers | 5 | 7 | PCR-FILTER |  | ENRDB | 50 | [12 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 1 | [7 empty] | 7 | 0 | Other Agency: Collected by Collier County. Bact analyses by county lab
Group 1 | Everglades West Coast | Drainage To Corkscrew Swamp | Lee | SD | 3259B1 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 7 | [7 empty] | 1 | [19 empty] | 1 |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  | 5 | 0
Group 1 | Everglades West Coast | Drainage To Corkscrew Swamp | Lee | SD | 3259B1 |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 7 | [7 empty] | 1 | [19 empty] | 1 |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  | 5 | 0
Group 1 | Everglades West Coast | Ten Thousand Islands | Collier | SD | 3259M | ENRE8 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 12 |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 | [26 empty] | 5 | 0
Group 1 | Everglades West Coast | Ten Thousand Islands | Collier | SD | 3259M | ENRE9 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 12 |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 | [26 empty] | 5 | 0
Group 1 | Everglades West Coast | Ten Thousand Islands | Collier | SD | 3259M | ENRE10 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 12 |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 | [26 empty] | 5 | 0
Group 1 | Everglades West Coast | C-139 Annex Basin (l3 Canal) | Hendry | SD | 3266A |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 15 | [7 empty] | 1 | [19 empty] | 1 |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  | 5 | 0
Group 1 | Everglades West Coast | Cocohatchee Golf Course Discharge | Collier | SD | 3278C |  | STREAM | 3F | Kit C | 2 | 2 | n=2, weeks=1 |  |  | 14 | [45 empty] | 0 | 2 | Other Agency: Collected by Collier County collects this as part of their regular sampling and upload to STORET
Group 1 | Everglades West Coast | Cow Slough | Collier | SD | 3278E |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 40 | [22 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [10 empty] | 3 | 2 | Other Agency: Collected by Collier County
Group 1 | Everglades West Coast | Cow Slough | Collier | SD | 3278E |  | STREAM | 3F | Tracers | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 40 | [22 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [10 empty] | 3 | 2 | Other Agency: Collected by Collier County
Group 1 | Everglades West Coast | Cow Slough | Collier | SD | 3278E |  | STREAM | 3F | Markers | 5 | 5 | PCR-FILTER |  |  | 40 | [22 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [10 empty] | 3 | 2 | Other Agency: Collected by Collier County
Group 1 | Everglades West Coast | Immokalee Basin | Collier | SD | 3278L |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 40 | [22 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [10 empty] | 3 | 2 | Other Agency: Collected by Collier County
Group 1 | Everglades West Coast | Immokalee Basin | Collier | SD | 3278L |  | STREAM | 3F | Tracers | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 40 | [22 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [10 empty] | 3 | 2 | Other Agency: Collected by Collier County
Group 1 | Everglades West Coast | Immokalee Basin | Collier | SD | 3278L |  | STREAM | 3F | Markers | 5 | 5 | PCR-FILTER |  |  | 40 | [22 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [10 empty] | 3 | 2 | Other Agency: Collected by Collier County
Group 1 | Everglades West Coast | L-28 Tieback | Collier | SD | 3278M |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 71 | [7 empty] | 1 | [19 empty] | 1 |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  | 5 | 0
Group 1 | Everglades West Coast | Marco Island (south Segment) | Collier | SD | 3278P | ENRE3 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRE3 | 119 |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 | [26 empty] | 5 | 0
Group 1 | Everglades West Coast | Clam Bay | Collier | SD | 3278Q1 | ENRJ1 | ESTUARY | 2 | Kit B | 5 | 2 | Removed |  | ENRJ1 | 7 | [9 empty] | 1 | [7 empty] | 1 | [27 empty] | 2 | 0 | Removed, Not rep Hurricane restoration activities. CM, CC 11/2/2017
Group 1 | Everglades West Coast | Clam Bay | Collier | SD | 3278Q1 | ENRJ1 | ESTUARY | 2 | Bacteria Class 2 Suite | 5 | 2 | Removed |  | ENRJ1 | 7 | [9 empty] | 1 | [7 empty] | 1 | [27 empty] | 2 | 0 | Removed, Not rep Hurricane restoration activities. CM, CC 11/2/2017
Group 1 | Everglades West Coast | Rookery Bay (coastal Segment) | Collier | SD | 3278U | ENRE3 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, quarters=3 |  | ENRE3 | 9 | [45 empty] | 0 | 5
Group 1 | Everglades West Coast | Rookery Bay (coastal Segment) | Collier | SD | 3278U | ENRE3 | ESTUARY | 2 | Bacteria Class 2 Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  | ENRE3 | 9 | [45 empty] | 0 | 5
Group 1 | Everglades West Coast | Gulf Of Mexico (collier County; Rookery Bay-naples) | Collier | SD | 8063 | ENRE2 | COASTAL | 3M | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRE2 | 12 | [9 empty] | 1 | [7 empty] | 1 | [18 empty] | 1 |  |  | 1 | [5 empty] | 4 | 1
Group 1 | Everglades West Coast | Gulf Of Mexico (monroe County; Collier County) | Collier, Monroe | SD | 8065 | ENRE6 | COASTAL | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRE6 | 12 |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 | [26 empty] | 5 | 0
Group 2 | Charlotte Harbor | Upper Lemon Bay | Sarasota | SD | 1983A | ENRD2 | ESTUARY | 2 | Kit B | 0 | 2 | n=0 |  | ENRD2 | 0 | [9 empty] | 1 | [28 empty] | 1 | [6 empty] | 2 | 0
Group 2 | Charlotte Harbor | Upper Lemon Bay | Sarasota | SD | 1983A | ENRD2 | ESTUARY | 2 | Bacteria Class 2 Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  | ENRD2 | 40 | [9 empty] | 1 | [16 empty] | 1 | [9 empty] | 1 | [8 empty] | 3 | 2
Group 2 | Charlotte Harbor | Upper Lemon Bay | Sarasota | SD | 1983A | ENRD2 | ESTUARY | 2 | Tracers | 5 | 5 | n=5, weeks=5, quarters=3 |  | ENRD2 | 40 | [18 empty] | 1 | [7 empty] | 1 | [9 empty] | 1 | [8 empty] | 3 | 2 | 3/13/17 samples uplaoded to storet 6/19/17 SO-DIST-2017-03-14-01
Group 2 | Charlotte Harbor | Upper Lemon Bay | Sarasota | SD | 1983A | ENRD2 | ESTUARY | 2 | Markers | 5 | 5 | PCR-FILTER |  | ENRD2 | 40 | [26 empty] | 1 | [9 empty] | 1 | [8 empty] | 2 | 3 | 3/13/17 samples uplaoded to storet 6/19/17 SO-DIST-2017-03-14-01
Group 2 | Charlotte Harbor | Alligator Creek (tidal Segment) | Sarasota | SD | 2030 |  | ESTUARY | 3M | Kit B | 5 | 0 | Removed | [48 empty] | 0 | 0 | Removed, collected by Sarasota County. CM 2/21/17
Group 2 | Charlotte Harbor | Alligator Creek (tidal Segment) | Sarasota | SD | 2030 |  | ESTUARY | 3M | Bacteria Class 3M Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 100 | [11 empty] | 1 | [10 empty] | 1 | [11 empty] | 1 | [6 empty] | 1 |  | 1 |  | 5 | 0 | Sample location is fresh; E.Coli needed, not Entero
Group 2 | Charlotte Harbor | Alligator Creek (tidal Segment) | Sarasota | SD | 2030 |  | ESTUARY | 3M | Tracers | 5 | 4 | n=5, weeks=5, quarters=3 |  |  | 100 | [22 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  | 4 | 0 | Sample location is fresh; E.Coli needed, not Entero
Group 2 | Charlotte Harbor | Alligator Creek (tidal Segment) | Sarasota | SD | 2030 |  | ESTUARY | 3M | Markers | 5 | 4 | PCR-FILTER & PCR-HF183 |  |  | 100 | [22 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  | 4 | 0 | Sample location is fresh; E.Coli needed, not Entero
Group 2 | Charlotte Harbor | Alligator Creek | Sarasota | SD | 2030A |  | STREAM | 3F | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 11 | [11 empty] | 1 | [10 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  | 5 | 0 | Added in September by Curtis
Group 2 | Charlotte Harbor | Alligator Creek | Sarasota | SD | 2030A |  | STREAM | 3F | Bacteria Freshwater Suite | 0 | 2 | n=2 | [30 empty] | 1 | [6 empty] | 1 | [10 empty] | 2 | 0 | Added in September by Curtis; wrong "alligator" sampled for entero
Group 2 | Charlotte Harbor | Alligator Creek | Sarasota | SD | 2030A |  | STREAM | 3F | Markers | 0 | 2 | PCR-FILTER & PCR-HF183 | [37 empty] | 1 | [6 empty] | 1 |  |  |  | 2 | 0 | Added in September by Curtis
Group 2 | Charlotte Harbor | Alligator Creek | Sarasota | SD | 2030A |  | STREAM | 3F | Pesticides | 5 | 5 | n=5, weeks=5, seasons=2 | [14 empty] | 1 | [10 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Woodmere Creek | Sarasota | SD | 2042 |  | ESTUARY | 3M | Bacteria Class 3M Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 40 | [11 empty] | 1 | [10 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Woodmere Creek | Sarasota | SD | 2042 |  | ESTUARY | 3M | Tracers | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 40 | [22 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  | 1 |  | 5 | 0
Group 2 | Charlotte Harbor | Woodmere Creek | Sarasota | SD | 2042 |  | ESTUARY | 3M | Markers | 5 | 5 | PCR-FILTER & PCR-HF183 |  |  | 40 | [22 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  | 1 |  | 5 | 0
Group 2 | Charlotte Harbor | Gottfried Creek | Sarasota | SD | 2049 |  | ESTUARY | 3M | Bacteria Class 3M Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 40 | [11 empty] | 1 | [10 empty] | 1 | [11 empty] | 1 | [6 empty] | 1 |  | 1 |  | 5 | 0
Group 2 | Charlotte Harbor | Gottfried Creek | Sarasota | SD | 2049 |  | ESTUARY | 3M | Tracers | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 40 | [22 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  | 1 |  | 5 | 0
Group 2 | Charlotte Harbor | Gottfried Creek | Sarasota | SD | 2049 |  | ESTUARY | 3M | Markers | 5 | 5 | PCR-FILTER & PCR-HF183 |  |  | 40 | [22 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  | 1 |  | 5 | 0
Group 2 | Charlotte Harbor | Unnamed Ditch | Sarasota | SD | 2050 |  | STREAM | 3F | Kit A | 2 | 2 | Kit with Biology |  |  | 19 | [45 empty] | 0 | 2
Group 2 | Charlotte Harbor | Unnamed Ditch | Sarasota | SD | 2050 |  | STREAM | 3F | SCI | 2 | 2 | Kit With Biology |  |  | 19 | [45 empty] | 0 | 2
Group 2 | Charlotte Harbor | Unnamed Ditch | Sarasota | SD | 2050 |  | STREAM | 3F | RPS | 2 | 2 | Kit With Biology |  |  | 19 | [45 empty] | 0 | 2
Group 2 | Charlotte Harbor | Unnamed Ditch | Sarasota | SD | 2050 |  | STREAM | 3F | LVS | 2 | 2 | Kit With Biology |  |  | 19 | [45 empty] | 0 | 2
Group 2 | Charlotte Harbor | Alligator Creek (north Prong) | Charlotte | SD | 2071 |  | STREAM | 1 | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 40 | [14 empty] | 1 | [12 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Alligator Creek (north Prong) | Charlotte | SD | 2071 |  | STREAM | 1 | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 40 | [14 empty] | 1 | [12 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Alligator Creek (north Prong) | Charlotte | SD | 2071 |  | STREAM | 1 | Tracers | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 40 | [14 empty] | 1 | [12 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Alligator Creek (north Prong) | Charlotte | SD | 2071 |  | STREAM | 1 | Markers | 5 | 5 | PCR-FILTER & PCR-GULL2 |  |  | 40 | [14 empty] | 1 | [12 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2074 |  | STREAM | 1 | Kit C | 5 | 6 | n=5, weeks=5, seasons=2 |  |  | 60 | [14 empty] | 1 | [12 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  | 6 | 0
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2074 |  | STREAM | 1 | SCI | 2 | 0 | Removed |  |  | 0 | [14 empty] | X | [30 empty] | 0 | 0 | Removed: Unsuitable, HA score 73 SD, CM 8/17/17
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2074 |  | STREAM | 1 | RPS | 2 | 2 | Kit With Biology |  |  | 60 | [14 empty] | 1 | [30 empty] | 1 | 1
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2074 |  | STREAM | 1 | LVS | 2 | 2 | Kit With Biology |  |  | 60 | [14 empty] | 1 | [30 empty] | 1 | 1
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2074 |  | STREAM | 1 | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 60 | [14 empty] | 1 | [12 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2074 |  | STREAM | 1 | Tracers | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 60 | [14 empty] | 1 | [12 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2074 |  | STREAM | 1 | Markers | 5 | 5 | PCR-FILTER |  |  | 60 | [14 empty] | 1 | [12 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 5 | 0
Group 2 | Charlotte Harbor | Whidden Creek | Charlotte | SD | 2079 | ENRD4 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 |  | ENRD4 | 14 | [9 empty] | 1 | [7 empty] | 1 | [8 empty] | 1 | [11 empty] | 1 | [6 empty] | 4 | 1
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2081 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 58 | [27 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  | 5 | 0 | Creek bed dry 4/19/2017
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2081 |  | STREAM | 3F | SCI | 2 | 2 | Kit With Biology |  |  | 58 | [45 empty] | 0 | 2 | Creek bed dry 4/19/2017
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2081 |  | STREAM | 3F | RPS | 2 | 2 | Kit With Biology |  |  | 58 | [40 empty] | 1 |  |  |  |  | 1 | 1 | Creek bed dry 4/19/2017
Group 2 | Charlotte Harbor | Alligator Creek | Charlotte | SD | 2081 |  | STREAM | 3F | LVS | 2 | 2 | Kit With Biology |  |  | 58 | [40 empty] | 1 |  |  |  |  | 1 | 1 | Creek bed dry 4/19/2017
Group 2 | Charlotte Harbor | Pirate Canal | Charlotte | SD | 2082A |  | STREAM | 3F | Kit A | 2 | 1 | Kit with Biology |  |  | 24 | [29 empty] | 1 | [15 empty] | 1 | 0
Group 2 | Charlotte Harbor | Pirate Canal | Charlotte | SD | 2082A |  | STREAM | 3F | SCI | 1 | 1 | Kit With Biology |  |  | 24 | [45 empty] | 0 | 1
Group 2 | Charlotte Harbor | Pirate Canal | Charlotte | SD | 2082A |  | STREAM | 3F | RPS | 2 | 1 | Kit With Biology |  |  | 24 | [29 empty] | 1 | [15 empty] | 1 | 0
Group 2 | Charlotte Harbor | Pirate Canal | Charlotte | SD | 2082A |  | STREAM | 3F | LVS | 2 | 1 | Kit With Biology |  |  | 24 | [29 empty] | 1 | [15 empty] | 1 | 0
Group 2 | Charlotte Harbor | Yucca Pen Creek | Lee | SD | 2082B |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 59 | [14 empty] | X | [12 empty] | 2 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 5 | 0 | flows fresh only during rainy season; otherwise marine
Group 2 | Charlotte Harbor | Yucca Pen Creek | Lee | SD | 2082B |  | STREAM | 3F | SCI | 2 | 2 | Kit With Biology |  |  | 59 | [14 empty] | X | [30 empty] | 0 | 2 | flows fresh only during rainy season; otherwise marine
Group 2 | Charlotte Harbor | Yucca Pen Creek | Lee | SD | 2082B |  | STREAM | 3F | RPS | 2 | 2 | Kit With Biology |  |  | 59 | [14 empty] | X | [30 empty] | 0 | 2 | flows fresh only during rainy season; otherwise marine
Group 2 | Charlotte Harbor | Yucca Pen Creek | Lee | SD | 2082B |  | STREAM | 3F | LVS | 2 | 2 | Kit With Biology |  |  | 59 | [14 empty] | X | [30 empty] | 0 | 2 | flows fresh only during rainy season; otherwise marine
Group 2 | Charlotte Harbor | Gator Slough Canal | Lee | SD | 2082C |  | STREAM | 3F | Kit A | 1 | 1 | Kit with Biology |  |  | 21 | [45 empty] | 0 | 1
Group 2 | Charlotte Harbor | Gator Slough Canal | Lee | SD | 2082C |  | STREAM | 3F | SCI | 1 | 1 | Kit With Biology |  |  | 21 | [45 empty] | 0 | 1
Group 2 | Charlotte Harbor | Gator Slough Canal | Lee | SD | 2082C |  | STREAM | 3F | RPS | 1 | 1 | Kit With Biology |  |  | 21 | [45 empty] | 0 | 1
Group 2 | Charlotte Harbor | Gator Slough Canal | Lee | SD | 2082C |  | STREAM | 3F | LVS | 1 | 1 | Kit With Biology |  |  | 21 | [45 empty] | 0 | 1
Group 2 | Charlotte Harbor | Sanibel Dune Lakes | Lee | SD | 2092H |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 64 | [33 empty] | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 5 | 0
Group 2 | Charlotte Harbor | Horseshoe Hermosa Canals | Lee | SD | 3240A3 |  | STREAM | 3F | Kit A | 1 | 0 | Removed | [48 empty] | 0 | 0 | Removed. Sufficiendt data in SBIO. CM 4/25/2017
Group 2 | Charlotte Harbor | Horseshoe Hermosa Canals | Lee | SD | 3240A3 |  | STREAM | 3F | RPS | 1 | 0 | Removed | [48 empty] | 0 | 0 | Removed. Sufficiendt data in SBIO. CM 4/25/2017
Group 2 | Charlotte Harbor | Horseshoe Hermosa Canals | Lee | SD | 3240A3 |  | STREAM | 3F | LVS | 1 | 0 | Removed | [48 empty] | 0 | 0 | Removed. Sufficiendt data in SBIO. CM 4/25/2017
Group 3 | Sarasota Bay - Peace - Myakka | Little Charlie Bowlegs | Highlands | SD | 1857 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 16 |  |  |  | 1 |  |  |  |  | 1 | [18 empty] | 1 | [9 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Walker Creek | Sarasota | SD | 1936A |  | STREAM | 3F | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 55 | [10 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 | 5 | 0 | October sample qualified
Group 3 | Sarasota Bay - Peace - Myakka | Walker Creek | Sarasota | SD | 1936A |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 55 | [10 empty] | X | [15 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | 1 | [6 empty] | 4 | 1 | bacteria was collected but not analyzed
Group 3 | Sarasota Bay - Peace - Myakka | Walker Creek | Sarasota | SD | 1936A |  | STREAM | 3F | Pesticides | 5 | 5 | n=5, weeks=5, seasons=2 | [13 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Indian Creek | Sarasota | SD | 1943 |  | STREAM | 3F | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 52 | [10 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Indian Creek | Sarasota | SD | 1943 |  | STREAM | 3F | Pesticides | 5 | 5 | n=5, weeks=5, seasons=2 | [13 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Howard Creek (northeast Branch) | Sarasota | SD | 1949 |  | STREAM | 3F | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 54 | [10 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Howard Creek (northeast Branch) | Sarasota | SD | 1949 |  | STREAM | 3F | Pesticides | 5 | 5 | n=5, weeks=5, seasons=2 | [13 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | North Creek | Sarasota | SD | 1984AB |  | STREAM | 3F | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 54 | [10 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | North Creek | Sarasota | SD | 1984AB |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 54 | [10 empty] | X | [15 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | 1 | [6 empty] | 4 | 1 | bacteria was collected but not analyzed
Group 3 | Sarasota Bay - Peace - Myakka | North Creek | Sarasota | SD | 1984AB |  | STREAM | 3F | Pesticides | 5 | 5 | n=5, weeks=5, seasons=2 | [13 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Myrtle Slough | DeSoto | SD | 1995 |  | STREAM | 1 | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 54 | [11 empty] | 1 | [11 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 | 1 |  | 5 | 0 | Dry on 3/28/2017 dry May 9th.
Group 3 | Sarasota Bay - Peace - Myakka | Myrtle Slough | DeSoto | SD | 1995 |  | STREAM | 1 | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 54 | [11 empty] | 1 | [11 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 | 1 |  | 5 | 0 | Dry on 3/28/2017 dry May 9th.
Group 3 | Sarasota Bay - Peace - Myakka | Myrtle Slough | DeSoto | SD | 1995 |  | STREAM | 1 | Tracers | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 54 | [11 empty] | 1 | [11 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 | 1 |  | 5 | 0 | Dry on 3/28/2017 dry May 9th.
Group 3 | Sarasota Bay - Peace - Myakka | Myrtle Slough | DeSoto | SD | 1995 |  | STREAM | 1 | Markers | 5 | 5 | PCR-FILTER |  |  | 54 | [11 empty] | 1 | [11 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 | 1 |  | 5 | 0 | Dry on 3/28/2017 dry May 9th.
Group 3 | Sarasota Bay - Peace - Myakka | Hawthorne Creek | DeSoto | SD | 1997 |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 3 | [10 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 |  |  | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Hawthorne Creek | DeSoto | SD | 1997 |  | STREAM | 3F | Tracers | 5 | 5 | n=5, weeks=5, quarters=3 |  |  | 3 | [17 empty] | 1 | [5 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 | 1 |  | 5 | 0 | No tracers taken 3/28/17
Group 3 | Sarasota Bay - Peace - Myakka | Hawthorne Creek | DeSoto | SD | 1997 |  | STREAM | 3F | Markers | 5 | 5 | PCR-FILTER & PCR-HF183 |  |  | 3 | [17 empty] | 1 | [5 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 | 1 |  | 5 | 0 | No markers taken 3/28/17
Group 3 | Sarasota Bay - Peace - Myakka | Hog Bay | DeSoto | SD | 2001 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 59 | [10 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 |  |  | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Runoff To Peace River | DeSoto | SD | 2028 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 54 | [10 empty] | X | [12 empty] | 0 | [6 empty] | 1 | [14 empty] | 1 | 4 | Always dry; only time site was samplable was right after hurricane
Group 3 | Sarasota Bay - Peace - Myakka | Bobcat Creek | DeSoto | SD | 2033 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 54 | [10 empty] | 1 | [12 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 5 | 0 | not flowing on May 9th
Group 3 | Sarasota Bay - Peace - Myakka | Myrtle Slough | Charlotte | SD | 2040 |  | STREAM | 1 | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 55 | [10 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 |  |  | 5 | 0
Group 3 | Sarasota Bay - Peace - Myakka | Shell Creek | Charlotte | SD | 2041 |  | STREAM | 1 | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 55 | [10 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 |  |  | 5 | 0
Group 3 | Caloosahatchee | Pollywog Creek | Glades | SD | 3235F |  | STREAM | 3F | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 53 | [14 empty] | 1 | [10 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 5 | 0
Group 3 | Caloosahatchee | Pollywog Creek | Glades | SD | 3235F |  | STREAM | 3F | Bacteria Freshwater Suite | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 53 | [14 empty] | 1 | [10 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 5 | 0
Group 3 | Caloosahatchee | Pollywog Creek | Glades | SD | 3235F |  | STREAM | 3F | Tracers | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 53 | [14 empty] | 1 | [10 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 5 | 0
Group 3 | Caloosahatchee | Pollywog Creek | Glades | SD | 3235F |  | STREAM | 3F | Markers | 5 | 5 | PCR-FILTER |  |  | 53 | [14 empty] | 1 | [10 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 5 | 0
Group 3 | Caloosahatchee | Roberts Canal | Hendry | SD | 3235N |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 53 | [14 empty] | 1 | [10 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 5 | 0
Group 3 | Caloosahatchee | Okaloacoochee Branch | Hendry | SD | 3235O |  | STREAM | 3F | Kit C | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 53 | [14 empty] | 1 | [10 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 5 | 0
Group 3 | Caloosahatchee | Telegraph Swamp | Charlotte | SD | 3236 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 55 | [14 empty] | X | [10 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 5 | 0 | Dry on 4/24/2017.
Group 4 | Kissimmee River | Lake Pythias | Highlands | SD | 1758G |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 75 | [6 empty] | 1 | [16 empty] | 1 | [21 empty] | 2 | 3 | Other Agency: Collected by Highlands County
Group 4 | Kissimmee River | Arbuckle Branch | Highlands | SD | 1761C |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 52 |  |  |  | 1 |  |  |  |  | 1 | [18 empty] | 1 | [9 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 4 | Kissimmee River | SILVER LAKE | Highlands | SD | 1813K |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 | [8 empty] | 1 | [9 empty] | 1 | [12 empty] | 1 | [11 empty] | 1 |  | 1 |  |  | 5 | 0 | 8/3/2017--failed DO, 11/28/2017---failed DO
Group 4 | Kissimmee River | Josephine Creek | Highlands | SD | 1860A |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 61 |  |  |  | 1 |  |  |  |  | 1 | [18 empty] | 1 | [9 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 4 | Kissimmee River | Hill Lake | Highlands | SD | 1860E |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 58 | [6 empty] | 1 | [8 empty] | 1 | [7 empty] | 1 | [21 empty] | 3 | 2 | Other Agency: Collected by Highlands County
Group 4 | Kissimmee River | Huckleberry Lake | Highlands | SD | 1893 |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 3 | [6 empty] | 1 | [8 empty] | 1 | [7 empty] | 1 | [21 empty] | 3 | 2 | Other Agency: Collected by Highlands County
Group 4 | Kissimmee River | Grassy Creek | Highlands | SD | 1932 |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 4 |  |  |  | 1 |  |  |  |  | 1 | [18 empty] | 1 | [9 empty] | 1 | 1 | [6 empty] | 5 | 0
Group 4 | Kissimmee River | Lale Sirena | Highlands | SD | 1932C |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 40 | [6 empty] | 1 | [8 empty] | 1 | [7 empty] | 1 | [21 empty] | 3 | 2 | Other Agency: Collected by Highlands County
Group 4 | Kissimmee River | Pearl Lake | Highlands | SD | 1932D |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 40 | [6 empty] | 1 | [8 empty] | 1 | [7 empty] | 1 | [21 empty] | 3 | 2 | Other Agency: Collected by Highlands County
Group 4 | Kissimmee River | Buck Lake | Highlands | SD | 1932I |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 57 | [5 empty] | 1 | [9 empty] | 1 | [12 empty] | 1 | [11 empty] | 1 |  | 1 |  |  | 5 | 0 | 8/3/2017--failed DO, 11/28/2017---failed DO
Group 4 | Kissimmee River | Blue Lake | Highlands | SD | 1932M |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 55 | [5 empty] | 1 | [9 empty] | 1 | [12 empty] | 1 | [11 empty] | 1 |  | 1 |  |  | 5 | 0 | 8/3/2017--failed DO, 11/28/2017---failed DO
Group 4 | Kissimmee River | Lake Henry | Highlands | SD | 1938 |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 56 | [6 empty] | 1 | [8 empty] | 1 | [7 empty] | 1 | [21 empty] | 3 | 2 | Other Agency: Collected by Highlands County
Group 4 | Kissimmee River | Lake Lachard | Highlands | SD | 1938I |  | LAKE | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 58 | [5 empty] | 1 | [9 empty] | 1 | [12 empty] | 1 | [11 empty] | 1 |  | 1 |  |  | 5 | 0 | 8/3/2017--failed DO, 11/28/2017---failed DO
Group 4 | Fisheating Creek | Fence Line Drain | Highlands | SD | 3201K |  | STREAM | 3F | Kit A | 5 | 5 | n=5, weeks=5, seasons=2 |  |  | 70 |  |  |  | 1 | [26 empty] | 1 | [6 empty] | 1 | 1 |  | 1 |  |  |  |  | 5 | 0
Group 5 | Everglades | Huston River | Monroe | SD | 3289B | ENRE9 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes | ENRE9 | 162 |  | 0 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 | [7 empty] | 1 |  |  |  | 1 | [18 empty] | 5 | 0
Group 5 | Everglades | Last Huston Bay | Monroe | SD | 3289C | ENREB | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes | ENREB | 162 |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  | 1 | [27 empty] | 5 | 0
Group 5 | Everglades | Chatham River | Monroe | SD | 3289D | ENRE9 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes | ENRE9 | 162 | [5 empty] | 1 |  |  |  |  | 1 |  |  |  | 1 | [7 empty] | 1 |  |  |  | 1 | [18 empty] | 5 | 0
Group 5 | Everglades | Chevelier Bay | Monroe | SD | 3289E | ENREB | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes | ENREB | 162 |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  | 1 | [27 empty] | 5 | 0
Group 5 | Everglades | Cannon Bay | Monroe | SD | 3289G | ENREB | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes | ENREB | 162 |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  | 1 | [27 empty] | 5 | 0
Group 5 | Everglades | Lostmans Bay (everglades National Park) | Monroe | SD | 3289H | ENRE9 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes | ENRE9 | 162 | [6 empty] | 1 |  |  |  | 1 |  |  |  | 1 | [7 empty] | 1 | 1 | [21 empty] | 5 | 0
Group 5 | Everglades | Lostmans Bay (everglades National Park) | Monroe | SD | 3289H | ENRE12 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes | ENRE12 | 162 | [6 empty] | 1 |  |  |  | 1 |  |  |  | 1 | [7 empty] | 1 | 1 | [21 empty] | 5 | 0
Group 5 | Everglades | Alligator Bay | Monroe | SD | 3289L | ENREB | ESTUARY | 3M | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes | ENREB | 162 |  |  | 1 |  |  | 1 | [11 empty] | 1 |  |  |  |  | 1 |  |  |  | 1 | [18 empty] | 5 | 0
Group 5 | Everglades | Dads Bay | Monroe | SD | 3289M | ENREB | ESTUARY | 3M | Kit B | 5 | 6 | n=5, weeks=5, seasons=2 | Yes | ENREB | 162 |  |  | 1 |  |  | 1 | [11 empty] | 1 |  |  |  |  | 1 | 1 |  |  | 1 | [18 empty] | 6 | 0 | last sample arrived late -UPS
Group 5 | Everglades | SHARK SLOUGH A (EVERGLADES NATIONAL PARK) | Monroe | SD | 3289R | ENRE9 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 100 | [6 empty] | 1 |  |  |  | 1 |  |  |  | 1 | [7 empty] | 1 | 1 | [21 empty] | 5 | 0
Group 5 | Everglades | SHARK SLOUGH A (EVERGLADES NATIONAL PARK) | Monroe | SD | 3289R | ENRE14 | ESTUARY | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 100 | [6 empty] | 1 |  |  |  | 1 |  |  |  | 1 | [7 empty] | 1 | 1 | [21 empty] | 5 | 0
Group 5 | Florida Keys | Grassy Key | Monroe | SD | 6011C |  | COASTAL | 3M | Kit D | 5 | 6 | n=5, weeks=5, seasons=2 | Yes |  | 162 |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 | [5 empty] | 1 | [21 empty] | 6 | 0 | 4/11/2017--pH failed postcal
Group 5 | Florida Keys | Grassy Key | Monroe | SD | 6011C |  | COASTAL | 3M | Additional Field Measurements | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 162 |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 | [9 empty] | 1 | [21 empty] | 5 | 0
Group 5 | Florida Keys | No Name Key | Monroe | SD | 6012C |  | COASTAL | 3M | Kit D | 5 | 7 | n=5, weeks=5, seasons=2 | Yes |  | 157 |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  | 1 | [21 empty] | 7 | 0
Group 5 | Florida Keys | No Name Key | Monroe | SD | 6012C |  | COASTAL | 3M | Additional Field Measurements | 5 | 7 | n=5, weeks=5, seasons=2 | Yes |  | 157 |  | 1 |  |  | 1 |  |  |  |  | 1 | [7 empty] | 1 |  |  |  | 1 |  | 1 | [21 empty] | 6 | 1
Group 5 | Florida Keys | Lower Matecumbe Key | Monroe | SD | 6019 |  | COASTAL | 3M | Kit B | 5 | 6 | n=5, weeks=5, seasons=2 | Yes |  | 157 |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 | [5 empty] | 1 | [21 empty] | 6 | 0
Group 5 | Florida Keys | Lower Matecumbe Key | Monroe | SD | 6019 |  | COASTAL | 3M | Additional Field Measurements | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 157 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 | [5 empty] | 1 | [21 empty] | 5 | 0
Group 5 | Everglades | Gulf Of Mexico (everglades National Park) | Monroe | SD | 8066 | ENRE5 | COASTAL | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 162 |  |  |  | 1 |  |  | n |  |  |  | n |  |  |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 | [15 empty] | 5 | 0
Group 5 | Everglades | Gulf Of Mexico (everglades National Park) | Monroe | SD | 8066 | ENRE10 | COASTAL | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 162 |  |  |  | 1 |  |  | n |  |  |  | n | [8 empty] | 1 |  |  |  | 1 | [5 empty] | 2 | [15 empty] | 5 | 0
Group 5 | Everglades | Gulf Of Mexico (everglades National Park) | Monroe | SD | 8067 | ENRE5 | COASTAL | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 162 |  |  |  | 1 |  |  | n |  |  |  | n |  |  |  | 1 |  | 1 |  | 1 | [11 empty] | 1 | [14 empty] | 5 | 0
Group 5 | Everglades | Gulf Of Mexico (everglades National Park) | Monroe | SD | 8068 | ENRE5 | COASTAL | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 162 |  |  |  | 1 |  |  | n |  |  |  | n |  |  |  | 1 |  | 1 | [13 empty] | 1 | [14 empty] | 4 | 1
Group 5 | Everglades | Gulf Of Mexico (everglades National Park; Cape Sable) | Monroe | SD | 8069 | ENRE5 | COASTAL | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 162 |  |  |  | 1 | [12 empty] | 1 | [5 empty] | 1 | [22 empty] | 3 | 2
Group 5 | Everglades | Gulf Of Mexico (everglades National Park; Cape Sable) | Monroe | SD | 8069 | ENR13 | COASTAL | 2 | Kit B | 5 | 5 | n=5, weeks=5, seasons=2 | Yes |  | 162 |  |  |  | 1 |  |  | 1 |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 | [22 empty] | 5 | 0
Group 5 | Everglades | Gulf Of Mexico (everglades National Park; Cape Sable) | Monroe | SD | 8070 | ENRE5 | COASTAL | 2 | Kit B | 5 | 6 | n=5, weeks=5, seasons=2 | Yes | ENRE5 | 162 |  |  |  | 1 |  |  | n |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | [6 empty] | 1 | [14 empty] | 6 | 0
Group 5 | Florida Keys | Key West And Outlying Islands | Monroe | SD | 8073 | ENRG1 | COASTAL | 3M | Kit D | 5 | 6 | n=5, weeks=5, seasons=2 | Yes |  | 61 |  | 1 | [7 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  | 1 | [21 empty] | 6 | 0 | 4/12/2017--DO and conductance failed postcal
Group 5 | Florida Keys | Atlantic Ocean (monroe County; Cudjoe Key-key West) | Monroe | SD | 8079 | ENRG3 | COASTAL | 3M | Kit D | 5 | 9 | n=5, weeks=5, seasons=2 | Yes |  | 62 | [5 empty] | 1 | [11 empty] | 1 |  | 2 |  | 2 |  | 1 | [7 empty] | 2 | [13 empty] | 9 | 0
Group 5 | Florida Keys | Atlantic Ocean (monroe County; Cudjoe Key-key West) | Monroe | SD | 8079 | ENRG6 | COASTAL | 3M | Kit D | 5 | 9 | n=5, weeks=5, seasons=2 | Yes |  | 62 | [5 empty] | 1 | [13 empty] | 2 |  | 2 |  | 2 | [7 empty] | 2 | [13 empty] | 9 | 0
Group 5 | Florida Keys | Atlantic Ocean (monroe County; Bahia Honda-cudjoe Key) | Monroe | SD | 8080 | ENRG3 | COASTAL | 3M | Kit D | 5 | 8 | n=5, weeks=5, seasons=2 | Yes |  | 61 | [5 empty] | 1 |  |  |  | 1 | [7 empty] | 1 |  | 2 |  |  | 2 | 1 | [21 empty] | 8 | 0
Group 5 | Florida Keys | Atlantic Ocean (monroe County; Bahia Honda-cudjoe Key) | Monroe | SD | 8080 | ENRG6 | COASTAL | 3M | Kit D | 5 | 8 | n=5, weeks=5, seasons=2 | Yes |  | 61 | [5 empty] | 1 | [11 empty] | 2 |  | 2 |  |  | 2 | 1 | [21 empty] | 8 | 0
Group 3 | Caloosahatchee | Telegraph Creek | Charlotte | SD | 3236A |  | STREAM | 3F | Markers | 5 | 6 | PCR-FILTER & PCR-BACR | [17 empty] | 1 |  | 1 | [8 empty] | 1 | [5 empty] | 1 |  | 1 | [8 empty] | 1 |  |  | 6 | 0 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | Telegraph Creek | Charlotte | SD | 3236A |  | STREAM | 3F | Tracers | 5 | 6 | n=5, weeks=5, seasons=2 | [17 empty] | 1 |  | 1 | [8 empty] | 1 | [5 empty] | 1 |  | 1 | [8 empty] | 1 |  |  | 6 | 0 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | POWELL CREEK | Lee | SD | 3240L |  | STREAM | 3F | Tracers | 0 | 6 | n=5, weeks=5, quarters=3 | [15 empty] | 1 |  |  |  | 1 | [8 empty] | 1 |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  |  | 6 | 0 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | POWELL CREEK | Lee | SD | 3240L |  | STREAM | 3F | Markers | 0 | 6 | PCR-FILTER & PCR-HF183 | [15 empty] | 1 |  |  |  | 1 | [8 empty] | 1 |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  |  | 6 | 0 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | Cypress Creek | Lee | SD | 3235C |  | STREAM | 3F | Tracers | 5 | 5 | n=5, weeks=5, quarters=3 | [19 empty] | 1 |  |  |  |  | 1 | [9 empty] | 1 |  | 1 | [11 empty] | 4 | 1 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | Cypress Creek | Lee | SD | 3235C |  | STREAM | 3F | Markers | 5 | 5 | PCR-FILTER | [19 empty] | 1 |  |  |  |  | 1 | [9 empty] | 1 |  | 1 | [11 empty] | 4 | 1 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | Trout Creek | Lee | SD | 3240G |  | STREAM | 3F | Markers | 5 | 6 | PCR-FILTER | [18 empty] | 1 | 1 | [8 empty] | 1 | [5 empty] | 1 |  | 1 | [8 empty] | 1 |  |  | 6 | 0 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | Trout Creek | Lee | SD | 3240G |  | STREAM | 3F | Tracers | 5 | 6 | n=5, weeks=5, seasons=2 | [18 empty] | 1 | 1 | [8 empty] | 1 | [5 empty] | 1 |  | 1 | [8 empty] | 1 |  |  | 6 | 0 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | Whiskey Creek (wyoua Creek) | Lee | SD | 3240H |  | STREAM | 3F | Markers | 5 | 5 | PCR-FILTER | [19 empty] | 1 | [8 empty] | 1 |  |  |  |  | 1 |  |  |  | 1 | [10 empty] | 4 | 1 | Sampled by Lee County Env Lab
Group 3 | Caloosahatchee | Whiskey Creek (wyoua Creek) | Lee | SD | 3240H |  | STREAM | 3F | Tracers | 5 | 5 | n=5, weeks=5, seasons=2 | [19 empty] | 1 | [8 empty] | 1 |  |  |  |  | 1 |  |  |  | 1 | [10 empty] | 4 | 1 | Sampled by Lee County Env Lab
Group 5 | Florida Keys | Key West And Outlying Islands | Monroe | SD | 8073 | ENRG2 | COASTAL | 3M | Kit D | 5 | 8 | n=5, weeks=5, seasons=2 | Yes |  | 61 |  | 1 | [7 empty] | 1 | [7 empty] | 1 |  | 2 |  | 2 |  | 1 | [21 empty] | 8 | 0
Group 5 | Florida Keys | Key West And Outlying Islands | Monroe | SD | 8073 | ENRG3 | COASTAL | 3M | Kit D | 5 | 7 | n=5, weeks=5, seasons=2 | Yes |  | 61 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 | [21 empty] | 7 | 0 | 4/12/2017--DO and conductance failed postcal
Group 5 | Florida Keys | Key West And Outlying Islands | Monroe | SD | 8073 | ENRG4 | COASTAL | 3M | Kit D | 5 | 10 | n=5, weeks=5, seasons=2 | Yes |  | 61 | [5 empty] | 1 | [7 empty] | 2 |  |  |  | 1 |  | 2 |  | 2 |  | 1 | [7 empty] | 1 | [13 empty] | 10 | 0 | 4/12/2017--DO and conductance failed postcal
Group 5 | Florida Keys | Key West And Outlying Islands | Monroe | SD | 8073 | ENRG6 | COASTAL | 3M | Kit D | 5 | 7 | n=5, weeks=5, seasons=2 | Yes |  | 61 | [5 empty] | 1 | [13 empty] | 2 |  | 1 |  | 1 | [7 empty] | 2 | [13 empty] | 7 | 0
Season 1
Season 2
Season 1

## Summary
|  | Samples Requested | Samples Collected | Samples Remaining | Percent Collected
| 2017 | 841 | 753 | 88 | 89.54%
| By June 30, 2017 | 200 | 196 | 4 | 98%
| 2017 | Total Number of Samples Collected | Total Number of Samples Requested | % Complete | % Total of Samples Collected
| Water Chemistry | 554 | 595 | 93.11% | 89.54%
| Kits (A,B,C,D) | 417 | 449 | 92.87%
| Additional Field Measurements | 16 | 17 | 94.12%
| Pesticides | 25 | 25 | 100%
| Tracers | 96 | 104 | 92.31%
| Microbiology | 91 | 104 | 87.5%
| Bacteria Freshwater Suite | 61 | 67 | 91.04%
| Bacteria Class 2 Suite | 5 | 12 | 41.67%
| Bacteria Class 3M Suite | 25 | 25 | 100%
| Molecular (Markers) | 96 | 105 | 91.43%
| Bioassessments | 12 | 37 | 32.43%
| LVI | 0 | 0 | na
| SCI | 0 | 9 | 0%
| RPS | 6 | 14 | 42.86%
| LVS | 6 | 14 | 42.86%
| By June 30, 2017 | Total Number of Samples Collected | Total Number of Samples Requested | % Complete | % Total of Samples Collected
| Water Chemistry | 196 | 200 | 98% | 98%
| Kits (A,B,C,D) | 180 | 183 | 98.36%
| Additional Field Measurements | 16 | 17 | 94.12%
| Pesticides | 0 | 0 | na
| Tracers | 0 | 0 | na
| Microbiology | 0 | 0 | na
| Bacteria Freshwater Suite | 0 | 0 | na
| Bacteria Class 2 Suite | 0 | 0 | na
| Bacteria Class 3M Suite | 0 | 0 | na
| Molecular (Markers) | 0 | 0 | na
| Biological Assessments | 0 | 0 | na
| LVI | 0 | 0 | na
| SCI | 0 | 0 | na
| RPS | 0 | 0 | na
| LVS | 0 | 0 | na
| Kit | # Requested | 5% for QC | Number of QC Samples Collected- BLANKS | [11 empty] | Total QC Collected | # QC To Collect
|  |  |  | January | February | March | April | May | June | July | August | September | October | November | December
F | Kit A | 149 | 7.45 | 1 | 2 | 2 |  |  | 2 | 2 | 4 | 1 |  |  |  | 14 | -6.55 | 187.9%
S | Kit B | 152 | 7.6 | 1 |  |  | 1 | 1 | 1 | 1 |  |  | 1 | 2 |  | 8 | -0.4 | 105.3%
F+N | Kit C | 63 | 3.15 |  |  | 1 | 1 |  |  | 2 | 2 | 1 |  |  |  | 7 | -3.85 | 222.2%
S+N | Kit D | 85 | 4.25 |  | 1 | [10 empty] | 1 | 3.25 | 23.53%
| Kit | # Requested | 5% for QC | Number of QC Samples Collected- DUPLICATES | [11 empty] | Total QC Collected | # QC To Collect
|  |  |  | January | February | March | April | May | June | July | August | September | October | November | December
F | Kit A | 149 | 7.45 | 1 | 2 |  | 4 |  |  | 1 | 2 |  |  |  |  | 10 | -2.55 | 134.2%
S | Kit B | 152 | 7.6 | 2 | 2 |  | 1 | 1 | 2 | [6 empty] | 8 | -0.4 | 105.3%
F+N | Kit C | 63 | 3.15 |  |  | 1 | [6 empty] | 2 |  |  | 3 | 0.15 | 95.24%
S+N | Kit D | 85 | 4.25 |  | 1 | [5 empty] | 1 |  |  |  |  | 2 | 2.25 | 47.06%
| Tracers | 104 | 5.2 | [12 empty] | 0 | 5.2 | 0%
| Pesticides | 25 | 1.25 | [12 empty] | 0 | 1.25 | 0%

## SD_Group_1&5
WBID | ENR | Name | Station | Event 1 | Event 2 | Event 3 | Event 4 | Event 5 | Event 6 | Notes
6011C |  | Grassy Key | FLKEYS0022FTM | 2017-01-10 | 2017-02-08 | 2017-03-07 | 2017-04-11 | 2017-05-09 | 2017-06-29 | 4/11/17 event Q qualified
6011C |  | Grassy Key | G5SD0002 | 2017-01-10 | 2017-02-08 | 2017-03-07 | 2017-04-11 | 2017-06-29
6012C |  | No Name Key | G5SD0071 | 2017-01-10 | 2017-02-08 | 2017-03-07 | 2017-04-11 | 2017-05-09 | 2017-06-13 | 2017-06-27 | 4/11/17 event Q qualified
6012C |  | No Name Key | G5SD0072 | 2017-01-10 | 2017-02-08 | 2017-03-07 | 2017-05-09 | 2017-06-13 | 2017-06-27
6019 |  | Lower Matecumbe | G5SD0073 | 2017-01-10 | 2017-02-08 | 2017-03-07 | 2017-04-11 | 2017-05-09 | 2017-06-29 | 4/11/17 event Q qualified
6019 |  | Lower Matecumbe | G5SD0074 | 2017-02-08 | 2017-03-07 | 2017-04-11 | 2017-05-09 | 2017-06-29 | 2017-06-29 | 4/12/17 event had DO and Cond fail
8080 | ENRG3 | (inshore) | G5SD0070 | 2017-02-08 | 2017-03-08 | 2017-05-10 | 2017-05-30 | 2017-06-15 | 2017-06-27 | 5/30/17 had no field data Sonde was malfunctioning
8080 | ENRG3 | (inshore) | G5SD0087 | 2017-05-30 | 2017-06-15 |  |  |  |  | 5/30/17 had no field data Sonde was malfunctioning
8080 | ENRG6 | (by reef) | G5SD0086 | 2017-05-11 | 2017-05-30 | 2017-06-15 | 2017-06-29 |  |  | 5/30/17 had no field data Sonde was malfunctioning
8080 | ENRG6 | (by reef) | G5SD0069 | 2017-02-08 | 2017-05-10 | 2017-05-30 | 2017-06-15 | 2017-06-27 |  | 5/30/17 had no field data Sonde was malfunctioning
8073 | ENRG1 | (bay side) | G5SD0066 | 2017-01-11 | 2017-03-08 | 2017-04-12 | 2017-05-10 | 2017-06-14 | 2017-06-28 | 1/11/17 event field readings qualified, 4/12/17 event had DO and Cond fail
8073 | ENRG2 | (bay side) | G5SD0065 | 2017-01-11 | 2017-03-08 | 2017-05-10 | 2017-05-31 | 2017-06-14 | 2017-06-28 | 1/11/17 event field readings qualified, 4/12/17 event had DO and Cond fail, 5/31/17 had no field data Sonde was malfunctioning
8073 | ENRG2 | (bay side) | G5SD0082 | 2017-05-31 | 2017-06-14 |  |  |  |  | 5/31/17 had no field data Sonde was malfunctioning
8073 | ENRG3 | (by shoals) | G5SD0062 | 2017-02-08 | 2017-03-08 | 2017-04-12 | 2017-05-10 | 2017-05-31 | 2017-06-14 | 2017-06-28 | 4/12/17 event had DO and Cond fail, 5/31/17 had no field data Sonde was malfunctioning
8073 | ENRG3 | (by shoals) | G5SD0081 | 2017-04-12 | 2017-05-31 | 2017-06-14 | 2017-08-30 |  |  | 4/12/17 event had DO and Cond fail, 5/31/17 had no field data Sonde was malfunctioning
8073 | ENRG4 | (inshore) | G5SD0063 | 2017-02-08 | 2017-04-12 | 2017-05-10 | 2017-05-31 | 2017-06-14 | 2017-06-28 | 5/31/17 had no field data Sonde was malfunctioning
8073 | ENRG6 | (by reef) | G5SD0064 | 2017-02-08 | 2017-05-31 | 2017-06-28 | 2017-08-30 |  |  | 5/31/17 had no field data Sonde was malfunctioning, 8/30/2017 failed DO post calibration
8073 | ENRG6 | (by reef) | G5SD0083 | 2017-05-31 | 2017-06-14 | 2017-08-30 |  |  |  | 5/31/17 had no field data Sonde was malfunctioning, 8/30/2017 failed DO post calibration
8079 | ENRG3 | (inshore) | G5SD0067 | 2017-02-08 | 2017-05-10 | 2017-05-31 | 2017-06-14 | 2017-06-28 | 2017-08-30 | 5/31/17 had no field data Sonde was malfunctioning, 8/30/2017 failed DO post calibration
8079 | ENRG3 | (inshore) | G5SD0084 | 2017-05-31 | 2017-06-14 | 2017-08-30 |  |  |  | 5/31/17 had no field data Sonde was malfunctioning, 8/30/2017 failed DO post calibration
8079 | ENRG6 | (by reef) | G5SD0068 | 2017-02-08 | 2017-05-11 | 2017-05-31 | 2017-06-14 | 2017-06-28 | 2017-08-30 | 5/31/17 had no field data Sonde was malfunctioning, 8/30/2017 failed DO post calibration
8079 | ENRG6 | (by reef) | G5SD0085 | 2017-05-31 | 2017-06-14 | 2017-06-28 | 2017-08-30 |  |  | 5/31/17 had no field data Sonde was malfunctioning, 8/30/2017 failed DO post calibration
3289H | ENRE9 | Lostmans Bay | G5SD0041 | 2017-02-21 | 2017-03-20 | 2017-04-19 | 2017-06-20 | 2017-06-26
3289H | ENRE12 | Lostmans Bay | G5SD0078 | 2017-02-21 | 2017-03-20 | 2017-04-19 | 2017-06-20 | 2017-06-26
3289R | ENRE9 | Shark Slough A | G5SD0040 | 2017-02-21 | 2017-03-20 | 2017-04-19 | 2017-06-20 | 2017-06-26
3289R | ENRE14 | Shark Slough A | G5SD0077 | 2017-02-21 | 2017-03-20 | 2017-04-19 | 2017-06-20 | 2017-06-26
8066 | ENRE5 | Gulf of Mexico | G5SD0039 | 2017-01-31 | 2017-04-19 | 2017-05-02 | 2017-05-22 | 2017-08-14
8066 | ENRE10 | Gulf of Mexico | G5SD0079 | 2017-01-31 | 2017-05-22 | 2017-06-26 | 2017-08-14
8066 | ENRE10 | Gulf of Mexico | G5SD0089 | 2017-08-14
8067 | ENRE5 | Gulf of Mexico | G5SD0038 | 2017-01-31 | 2017-04-19 | 2017-05-02 | 2017-05-22 | 2017-08-14
8068 | ENRE5 | Gulf of Mexico | G5SD0037 | 2017-01-31 | 2017-04-19 | 2017-05-02 | 2017-08-14
8068 | ENRE5 | Gulf of Mexico | G5SD0088 | 2017-08-14
8069 | ENRE5 | Gulf of Mexico | G5SD0036 | 2017-01-31 | 2017-05-02 | 2017-06-20
8069 | ENR13 | Gulf of Mexico | G5SD0076 | 2017-01-31 | 2017-02-21 | 2017-03-20 | 2017-05-02 | 2017-05-22 | 2017-06-20
8070 | ENRE5 | Gulf of Mexico | G5SD0075 | 2017-01-31 | 2017-03-20 | 2017-05-02 | 2017-06-20 | 2017-06-26
3289B | ENRE9 | Huston River | G5SD0043 | 2017-02-15 | 2017-03-20 | 2017-04-17 | 2017-06-21 | 2017-07-24
3289C |  | Last Huston Bay | G5SD0026 | 2017-01-18 | 2017-02-15 | 2017-03-20 | 2017-04-17 | 2017-05-16
3289D |  | Chatham River | G5SD0042 | 2017-02-15 | 2017-03-20 | 2017-04-17 | 2017-06-21 | 2017-07-24
3289E |  | Chevelier Bay | G5SD0027 | 2017-01-18 | 2017-02-15 | 2017-03-20 | 2017-04-17 | 2017-05-16
3289G | ENRE11 | Cannon Bay | G5SD0028 | 2017-01-18 | 2017-02-15 | 2017-03-20 | 2017-04-17 | 2017-05-16
3289L | ENRE11 | Alligator Bay | G5SD0029 | 2017-01-18 | 2017-02-15 | 2017-05-16 | 2017-06-21 | 2017-07-24
3289M | ENRE11 | Dads Bay | G5SD0030 | 2017-01-18 | 2017-02-15 | 2017-05-16 | 2017-06-21 | 2017-06-27 | 2017-07-24 | 6/27/2017 sample was qualified due to late sample
Group 1
WBID | ENR | Name | Station | Event 1 | Event 2 | Event 3 | Event 4 | Event 5 | Event 6 | Notes
3259M | ENRE9 | Copeland Bridge | EVRGWC0001FTM | 2017-02-15 | 2017-04-17
3259M | ENRE9 |  | G1SD0058 | 2017-01-30 | 2017-02-27 | 2017-03-21 | 2017-04-26 | 2017-05-22
3259M | ENRE10 |  | G1SD0053 | 2017-01-30 | 2017-02-27 | 2017-03-21 | 2017-04-26 | 2017-05-22
3259M | ENRE8 |  | G1SD0054 | 2017-01-30 | 2017-02-27 | 2017-03-21 | 2017-04-26 | 2017-05-23
3278P | ENRE3 |  | G1SD0037 | 2017-01-30 | 2017-02-27 | 2017-03-21 | 2017-04-26 | 2017-05-23
8065 | ENRE6 |  | G1SD0055 | 2017-01-30 | 2017-02-27 | 2017-03-21 | 2017-04-26 | 2017-05-23 |  | 3/21/17 bottles late, Q qualified
3278U | ENRE3 | Rookery Bay | [7 empty] | Rookery Bay Sampling here ?

## SD_QAQC_Tracker
N:\S ROC\Projects and Data\SMP\SAMPLING\SMP 2017\2017_File_Tracking.xlsx