Schedule of Deliverables and Invoice Amounts

| Deliverable | Due Date | Invoice Amount |
| --- | --- | --- |
| Objective 1) Compile available ballast mgmt. records from 1/1/2008 for ships entering and leaving the GoM. | 4 weeks after contract approval |  |
| Objective 2) Review literature of risk analyses studies for HAB species introduction by ballast water. | 8 weeks after contract approval |  |
| Objective 3) ID potential hot spot or high risk areas of the Gulf of Mexico based on information gathered during obj. 1 and 2 | 12 weeks after contract approval | $ 6,000.00 |
| Objective 4) Provide a written report that presents the findings from obj. 1-3, as well as recommended next steps. | 16 weeks after contract approval | $ 2,024.24. |
| TOTAL: |  | $ 8,024.24 |