ATTACHMENT A

GRANT WORK PLAN

| ## PROJECT: Pansy avenue stormwater exfiltration system |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Funding: | 144,000.00 |  | FY11 319 | 96,000.00 |  | Match |
| LEAD ORGANIZATION: | City of Winter Park, Florida 401 Park Avenue, South Winter Park, FL 32789 |  |  |  |  |  |
| CONTact person: (Name, Address, Phone) | Lena O. Petersen Asst. Mgr. Projects/Construction 401 Park Avenue, South Winter Park, FL 32789 407-599-3225 phone 407-599-3417 fax lpetersen@cityofwinterpark.org |  |  |  |  |  |
| cooperating organizations: City of Winter Park, Florida |  |  |  |  |  |  |
| Project ABSTRACT: Pansy Avenue project is a 10.4 acre basin draining to Lake Maitland which is connected to the Winter Park chain of lakes located within the Lake Jesup Plan Unit of the Middle St. Johns River. This basin is primarily a residential development, and the purpose of this project is to provide treatment for a mean annual storm event by the installation of an underground exfiltration system designed to handle a volume capacity of one-inch of stormwater runoff from this 10.4 acre residential basin via collection inlets along Pansy Avenue, Oaks Boulevard, and Kenwood Avenue. |  |  |  |  |  |  |
| Project location and watershed characteristics: This project is along Pansy Avenue between Oaks Boulevard, and Kenwood Avenue, draining into the west side of Lake Maitland via an outfall at the east end of Summerland Avenue. |  |  |  |  |  |  |
| Watershed Name: |  | Howell Branch Creek/Lake Jesup/Middle St. Johns River |  |  |  |  |
| Latitude: |  | 28.61 |  |  |  |  |
| Longitude: |  | 81.36 |  |  |  |  |
| Hydrologic Unit Code(HUC): |  | 3080101 |  |  |  |  |
| Land Uses within the Watershed (acres and percentages of total): |  |  |  |  |  |  |
| Land Use; Acres; %. Residential; 10.4; 100. Land Use Totals (Acreage and %). |
| POLLUTION REDUCTION STRATEGY: The pollution reduction strategy of this project is to treat stormwater runoff from this residential basin by collection and retention in an underground exfiltration system prior to discharge into Lake Maitland. Installation of this retention system is in concert with the Middle St. Johns River Basin SWIM plan initiative to enhance water quality, emphasizing nutrient loading reduction and lake protection. |  |  |  |  |  |  |
| Project Objective(s): Improved means of collection of stormwater runoff along Pansy Avenue and the reduction of roadway surface pollutants into Lake Maitland by the construction of an underground exfiltration collection system. |  |  |  |  |  |  |
| Project Description: This project will begin with an alternative analysis of various BMP’s to determine practical site locations, overflow system connection, and the best size and inlet locations considering elements such as grade and flow rate. The City will then finalize plans and specifications to implement construction of the underground exfiltration system. |  |  |  |  |  |  |

ESTIMATED POLLUTANT LOAD REDUCTION:

BMPs Installed; TSS kg/yr; TP kg/yr; TN kg/yr; Sediment kg/yr; BOD kg/yr; Other kg/yr; Other kg/yr. TZN; TPB. Pollutant Loads; Pre-Project; 583.44; 6.18; 48.67; 522; 148.72; 1.27; 0.86. Post-Project; 29.17; 0.99; 7.3; 104; 14.87; 0.11; 0.11. Load Reduction; 554.27; 5.19; 41.37; 418; 133.85; 1.15; 0.61. % Reduction; 95; 84; 85; 80; 90; 91; 71.

Model used: Loading rates were estimated using the BMP Efficiency Values for the Lake Jesup BMAP, January 2009.

land ownership status: city of winter park, florida, public roadway and right-of-way

Outputs/Deliverables: 1) Design Report and Construction Plans 2) Construction 3) Quarterly Progress Reports and Final Report

| Project milestones: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Task | Activity | Start | Complete |  |
|  | 1 | Contract with FDEP Executed | Month 1 | Month 1 |  |
|  | 2 | Quarterly Progress Reports & Final Report | Month 3 | Month 14 |  |
|  | 3 | Final Design | Month 2 | Month 7 |  |
|  | 4 | Construction | Month 8 | Month 13 |  |
|  | 5 | Final Report | Month 14 | Month 15 |  |

Project Budget:

Project Funding Activity; 319 (h) Amount; Matching Contribution; Match Source *. Staff; 12,000.00; In-kind services. Contractual. BMP Implementation; 144,000.00; 84,000.00; Stormwater Utility Fee.

Total:; 144,000.00; 96,000.00. Total Project Cost:; 240,000.00. Percentage Match:; 60%; 40%.

*If a stormwater utility or other dedicated recurring fee is contributing, put that information in the following table.

Match source information:

Match Source Name; Description; ERU/Fee. Winter Park Stormwater Fund; Stormwater Utility Fee; SEE SCHEDULE BELOW Fee based upon square feet of impervious area.

CITY OF WINTER PARK - FEE SCHEDULE

Effective: May 1, 2010

STORMWATER UTILITY FEES

Monthly Stormwater Utility Fees:

Single family residential property: (based on square feet of impervious area:

Class 1 (1,099 and smaller) ..................................................................... 6.25

Class 2 (1,100 and 1,699) ........................................................................ 7.81

Class 3 (1,700 and 2,299) ........................................................................ 9.37

Class 4 (2,300 and 2,899) ...................................................................... 10.95

Class 5 (2,900 and 3,499) ...................................................................... 12.52

Class 6 (3,500 and 4,099) ...................................................................... 14.08

Class 7 (4,100 and 4,699) ...................................................................... 15.65

Class 8 (4,700 and 5,299) ...................................................................... 17.21

Class 9 (5,300 and 5,899) ...................................................................... 18.77

Class 10 (5,900 and 6,499) .................................................................... 20.53

Class 11 (6,500 and 7,099) .................................................................... 21.92

Class 12 (7,100 and 7,699) .................................................................... 23.48

Class 13 (7,700 and 8,299) .................................................................... 25.03

Class 14 (8,300 and 8,899) .................................................................... 26.61

Class 15 (8,900 and higher) ................................................................... 28.17

Multi-family residential property:

Apartment unit - per dwelling unit ........................................................... 7.81

Condominium unit - per dwelling unit ..................................................... 7.81

Duplex - per dwelling unit ........................................................................ 7.81

Non-residential/commercial property (per ERU)

(ERU = Equivalent Residential Unit of 2,324 sq. ft.) ............................. 10.95

Budget by task:

Project Funding Activity; 319 (h) Amount; Matching Contribution; Match Source. Survey, design; 6,000.00; In-kind services, Stormwater Utility Fee. Project Administration; 6,000.00; In-kind Services. Construction; 144,000.00; 84,000.00; Stormwater Utility Fee.

Total:; 240,000.00. Total Project Cost:. Percentage Match:; 60%; 40%.

| OTHER FUNDING (Not Match – such as land acquisition or other federal grants): |  |  |  |
| --- | --- | --- | --- |
| Agency; Activity; Amount. N/A. Total:. |
| OTHER INFORMATION: If this is a multi-year project, have you requested sufficient funds to complete the project (assuming funds requested herein are provided)? (State yes or no, and, if no, provide an explanation): Yes: X No: The Lead Organization, as listed on the first page of this form, agrees to comply with all requirements specified in the guidance package and in the federal grant regulations. Checking “no” or “yes, except” will cause the project to have a lower ranking than similar projects by lead organizations that agree to the requirements: |  |  |  |
| Yes: X | No: | Yes, except: | (Note: List exceptions below.) |
| Exceptions: |  |  |  |

References cited:

REMAINDER OF PAGE INTENTIONALLY LEFT BLANK

APPENDIX A: MONITORING PLAN

PANSY AVENUE STORMWATER EXFILTRATION SYSTEM

Sampling Locations: inflow and outflow

Frequency of Monitoring: seven to ten storm events

Storm Events: Discrete rainfall events of generally greater than 0.2 inches and less than 1.5 inches.  Daily rainfall (to nearest 0.01 inch) measured at the sampling location with verification from the local weather station.  Rainfall data should be provided for at least the week proceeding monitoring and day(s) of monitoring.

Flow Measurements: Flow is measured using flow activated flow meters.

Parameters to be Monitored:

| Parameter |  | Detection Limit |  | Method |
| --- | --- | --- | --- | --- |
| Total Cadmium |  | 1 ug/l |  | Composite* |
| Total Chromium |  | 5 ug/l |  | Composite* |
| Total Copper |  | 5 ug/l |  | Composite* |
| Total Zinc |  | 10 ug/l |  | Composite* |
| NO2+NO3 |  | 0.1mg/l |  | Composite* |
| TNK |  | 0.3 mg/l |  | Composite* |
| Total Ammonia or Total N |  | 0.05 mg/l |  | Composite* |
| Total Phosphorus |  | 0.05 mg/l |  | Composite* |
| Ortho Phosphate |  | 0.05 mg/l |  | Composite* |
| TSS |  | 1 mg/l |  | Composite* |
| Oil/Grease |  | 1 mg/l |  | Composite* |
| Fecal coliform |  | N/A |  | Grab if Possible** |

*Flow weighted composite samples will be taken over the storm hydrograph.  Typically the samples will be composited over the inflow hydrograph at the inflow and for up to a 36 hour period at the outflow station.  Rainfall that does not result in at least a six-hour discharge from the stormwater BMP shall not be considered a completed monitoring event.  Each composite will include at least six evenly distributed sub-samples.

**Grab samples to be collected within the drainage area time of concentration at influent and effluent stations described above.

APPENDIX B:

FIGURE 3: TREATMENT AREA MAP

FIGURE 4: DETAILED SITE MAP  N