## Sheet1
Broward Soil and Water Conservation District
Florida Department of Environmental Protection
Beach Management Funding Assistance Program
Request for Payment - Part III
Reimbursement Detail
[7 empty] | Dep Contract Number: O7B01 |  |  |  |  | Invoice Adjustments ( To be completed by DEP
|  |  |  | Billing #: 1 |  |  | Billing Period: December 2006 - December 2008 |  |  |  |  | Reasons for Changes noted below)
|  | Item # | Invoice Date | Invoice Number | Amount Paid (1) | Amount Pertaining to this Contract, this item | Eligible Project Item (2) | SOW/BID # (3) | Vendor Name | Check or Debit # | Class | Total Amount Eligible for State Share (4) | Changes per BBCS Project Manager (5.6) | Changes Per BBCS Accountant (5.6) | Approved Eligible Cost (5)
7000 · Project Expense
70-102 · Work w/Volunteers
| & Trainers | 1 | 2007-06-19 | 060407 | 870 | 870 | 3.1 |  | Richard Naedele | 1607 | FDEP - City of Hallandale Beach | 870 | OK | ok | 870
|  | 2 | 2007-08-01 | 073007 | 2205 | 705 | 3.1 |  | Richard Naedele | 1639 | FDEP - City of Hallandale Beach | 705 | provide cost breakdown and approval signature |  | 0
|  | 3 | 2007-12-19 | 121907 | 2500 | 2500 | 3.1 |  | Kids Ecology Corp. | 1767 | FDEP - City of Hallandale Beach | 2500 | Provide invoice |  | 0
| Total 70-102 |  |  |  | 5575 | 4075 | [5 empty] | 4075
70-103 · Administrate Volunteer
| Program | 4 | 2007-07-10 | 070907 | 2000 | 2000 | 3.1 |  | Kids Ecology Corp. | 1618 | FDEP - City of Hallandale Beach | 2000 | Provide invoice |  | 0
|  | 5 | 2007-07-16 | 071507cam | 2000 | 500 | 3.1 |  | Canute A. Malcolm | 1619 | FDEP - City of Hallandale Beach | 500 | District employee, not eligible |  | 0
|  | 6 | 2007-08-27 | 083007 | 2000 | 1000 | 3.1 |  | Canute A. Malcolm | 1664 | FDEP - City of Hallandale Beach | 1000 | District employee, not eligible |  | 0
|  | 7 | 2007-09-04 | 090407 | 500 | 500 | 3.1 |  | Canute A. Malcolm | 1674 | FDEP - City of Hallandale Beach | 500 | District employee, not eligible |  | 0
|  | 8 | 2007-09-11 | 091107 | 2000 | 1000 | 3.1 |  | Canute A. Malcolm | 1681 | FDEP - City of Hallandale Beach | 1000 | District employee, not eligible |  | 0
|  | 9 | 2007-12-15 | 121507 | 1800 | 600 | 3.1 |  | Canute A. Malcolm | 1733 | FDEP - City of Hallandale Beach | 600 | District employee, not eligible |  | 0
| Total 70-103 |  |  |  | 10300 | 5600 | [5 empty] | 5600
70-107 Prepare Site Plans & Specs
|  | 87 | 2007-12-31 |  | 34211.09 | 2225.02 | 3.1 |  | City of Hallandale Beach | In Kind Credit |  | 2225.02 | OK | ok | 2225.02
| Total 70-107 |  |  |  | 34211.09 | 2225.02 | [5 empty] | 2225.02
70-108 · Project Mgmt On & Off Site
|  | 10 | 2007-10-25 | 102507 | 2000 | 800 | 3.1 |  | Canute A. Malcolm | 1714 | FDEP - City of Hallandale Beach | 800 | District employee, not eligible |  | 0
|  | 11 | 2007-11-14 | 111507 | 2000 | 800 | 3.1 |  | Canute A. Malcolm | 1725 | FDEP - City of Hallandale Beach | 800 | District employee, not eligible |  | 0
|  | 89 | 2008-12-31 | 08-1231 | 50000 | 50000 | 3.1 |  | Russell M. Setti | 2005 |  | 50000 | District employee, not eligible |  | 0
| Total 70-108 |  |  |  | 54000 | 51600 | [5 empty] | 51600
70-109 · Secretarial
|  | 12 | 2007-03-09 | 031507cm | 2000 | 400 | 3.1 |  | Canute A. Malcolm | 1519 | FDEP - City of Hallandale Beach | 400 | District employee, not eligible |  | 0
|  | 13 | 2007-03-22 | 031507 | 56 | 56 | 3.1 |  | Camille Stokes | 1537 | FDEP - City of Hallandale Beach | 56 | Needs documentation for project costs |  | 0
|  | 14 | 2007-03-29 | 032907 | 2000 | 1000 | 3.1 |  | Canute A. Malcolm | 1540 | FDEP - City of Hallandale Beach | 1000 | District employee, not eligible |  | 0
|  | 15 | 2007-06-15 | 061507 | 2000 | 1000 | 3.1 |  | Canute A. Malcolm | 1596 |  | 1000 | District employee, not eligible |  | 0
|  | 16 | 2007-06-28 | 063007cam | 2000 | 2000 | 3.1 |  | Canute A. Malcolm | 1610 | FDEP - City of Hallandale Beach | 2000 | District employee, not eligible |  | 0
|  | 17 | 2007-07-26 | 073007cam | 2000 | 2000 | 3.1 |  | Canute A. Malcolm | 1629 | FDEP - City of Hallandale Beach | 2000 | District employee, not eligible |  | 0
|  | 6 | 2007-08-27 | 083007 | 2000 | 1000 | 3.1 |  | Canute A. Malcolm | 1664 | FDEP - City of Hallandale Beach | 1000 | District employee, not eligible |  | 0
|  | 8 | 2007-09-11 | 091507 | 2000 | 1000 | 3.1 |  | Canute A. Malcolm | 1681 | FDEP - City of Hallandale Beach | 1000 | District employee, not eligible |  | 0
|  | 18 | 2007-09-27 | 101507 | 2000 | 2000 | 3.1 |  | Canute A. Malcolm | 1685 | FDEP - City of Hallandale Beach | 2000 | District employee, not eligible |  | 0
|  | 10 | 2007-10-25 | 103007 | 2000 | 1200 | 3.1 |  | Canute A. Malcolm | 1714 | FDEP - City of Hallandale Beach | 1200 | District employee, not eligible |  | 0
|  | 11 | 2007-11-14 | 111507 | 2000 | 1200 | 3.1 |  | Canute A. Malcolm | 1725 | FDEP - City of Hallandale Beach | 1200 | District employee, not eligible |  | 0
|  | 9 | 2007-12-15 | 121507 | 1800 | 1200 | 3.1 |  | Canute A. Malcolm | 1733 | FDEP - City of Hallandale Beach | 1200 | District employee, not eligible |  | 0
|  | 19 | 2008-12-15 | 107 | 679.5 | 49.5 | 3.1 |  | Kelly Kuntze | 1984 | FDEP - City of Hallandale Beach | 49.5 | OK | OK | 49.5
|  | 20 | 2008-12-19 | 108 | 778.5 | 243 | 3.1 |  | Kelly Kuntze | 1995 | FDEP - City of Hallandale Beach | 243 | OK | OK | 243
|  | 21 | 2008-12-31 | 110 | 643.5 | 144 | 3.1 |  | Kelly Kuntze | 1999 | FDEP - City of Hallandale Beach | 144 | OK | OK | 144
|  | 22 | 2009-01-09 | 111 | 769.5 | 54 | 3.1 |  | Kelly Kuntze | 2016 | FDEP - City of Hallandale Beach | 54 | OK | OK | 54
| Total 70-109 · |  |  |  | 24727 | 14546.5 | [5 empty] | 14546.5
70-110 · Contract Labor
|  | 23 | 2007-08-13 | 081307 | 60 | 60 | 3.1 |  | Donald Adams | 1648 | FDEP - City of Hallandale Beach | 60 | Need a time sheet to justify payment |  | 0
|  | 24 | 2007-08-13 | 081307 | 10 | 10 | 3.1 |  | Dorian Carter | 1649 | FDEP - City of Hallandale Beach | 10 | Need a time sheet to justify payment |  | 0
|  | 25 | 2007-08-13 | 081307 | 30 | 30 | 3.1 |  | Mark Francis | 1652 | FDEP - City of Hallandale Beach | 30 | Need a time sheet to justify payment |  | 0
|  | 26 | 2007-08-13 | 081307 | 20 | 20 | 3.1 |  | Tara Simpson | 1653 | FDEP - City of Hallandale Beach | 20 | Need a time sheet to justify payment |  | 0
|  | 27 | 2007-08-13 | 081307 | 50 | 50 | 3.1 |  | Alton Turner | 1654 | FDEP - City of Hallandale Beach | 50 | Need a time sheet to justify payment |  | 0
|  | 28 | 2007-08-14 | 081407 | 50 | 50 | 3.1 |  | Mark Cranston | 1655 | FDEP - City of Hallandale Beach | 50 | Need a time sheet to justify payment |  | 0
|  | 29 | 2007-08-15 | 081507 | 30 | 30 | 3.1 |  | Dorian Carter | 1656 | FDEP - City of Hallandale Beach | 30 | Need a time sheet to justify payment |  | 0
|  | 30 | 2007-08-15 | 081507 | 10 | 10 | 3.1 |  | Mark Francis | 1658 | FDEP - City of Hallandale Beach | 10 | Need a time sheet to justify payment |  | 0
|  | 31 | 2007-08-15 | 081507 | 20 | 20 | 3.1 |  | Tara Simpson | 1659 | FDEP - City of Hallandale Beach | 20 | Need a time sheet to justify payment |  | 0
|  | 32 | 2007-08-27 | 082707 | 50 | 50 | 3.1 |  | Alton Turner | 1663 | FDEP - City of Hallandale Beach | 50 | Need a time sheet to justify payment |  | 0
|  | 33 | 2007-08-27 | 082707 | 40 | 40 | 3.1 |  | Dorian Carter | 1665 | FDEP - City of Hallandale Beach | 40 | Need a time sheet to justify payment |  | 0
|  | 34 | 2007-08-27 | 082707 | 40 | 40 | 3.1 |  | Mark Francis | 1667 | FDEP - City of Hallandale Beach | 40 | Need a time sheet to justify payment |  | 0
|  | 35 | 2007-08-27 | 082707 | 40 | 40 | 3.1 |  | Mark Cranston | 1668 | FDEP - City of Hallandale Beach | 40 | Need a time sheet to justify payment |  | 0
|  | 36 | 2007-08-27 | 082707 | 40 | 40 | 3.1 |  | Tara Simpson | 1669 | FDEP - City of Hallandale Beach | 40 | Need a time sheet to justify payment |  | 0
|  | 37 | 2007-03-02 | 030207-5 | 6945.88 | 6945.88 | 3.1 |  | SECRITS Resource and Help Center | 1511 | FDEP - City of Hallandale Beach | 6945.88 | Provide travel reimbursement form, bonus ineligible |  | 6682.93
|  | 38 | 2007-03-09 | 030907-5 | 6878.03 | 6878.03 | 3.1 |  | SECRITS Resource and Help Center | 1518 | FDEP - City of Hallandale Beach | 6878.03 | Provide travel reimbursement form, bonus ineligible |  | 6636.37
|  | 39 | 2007-03-15 | 6 | 4867.7 | 4867.7 | 3.1 |  | SECRITS Resource and Help Center | 1530 | FDEP - City of Hallandale Beach | 4867.7 | Provide travel reimbursement form, bonus ineligible |  | 4618.91
|  | 40 | 2007-03-20 | 030207 | 1029.08 | 952.5 | 3.1 |  | Richard Naedele | 1534 | FDEP - City of Hallandale Beach | 952.5 | OK |  | 952.5
|  | 41 | 2007-03-22 | 032207 | 2029 | 2029 | 3.1 |  | SECRITS Resource and Help Center | 1539 | FDEP - City of Hallandale Beach | 2029 | Provide travel reimbursement form, bonus ineligible |  | 1750.66
|  | 42 | 2007-03-29 | 7 | 273.7 | 273.7 | 3.1 |  | SECRITS Resource and Help Center | 1545 | FDEP - City of Hallandale Beach | 273.7 | OK |  | 273.7
|  | 43 | 2007-07-24 | 072407 | 303.9 | 293.4 | 3.1 |  | Ernest Statkus | 1627 | FDEP - City of Hallandale Beach | 293.4 | OK |  | 293.4
|  | 44 | 2007-07-26 | 11-2-3138 | 3093.97 | 3093.97 | 3.1 |  | Labor Finders | 1635 | FDEP - City of Hallandale Beach | 3093.97 | OK | OK | 3093.97
|  | 2 | 2007-08-01 | 073007 | 2205 | 465 | 3.1 |  | Richard Naedele | 1639 | FDEP - City of Hallandale Beach | 465 | OK | OK | 465
|  | 45 | 2007-08-03 | 80307 | 203.79 | 179.79 | 3.1 |  | Ernest Statkus | 1642 |  | 179.79 | Invoice needs to be signed by BSWCD |  | 0
| 11-2-3163, 11-2-3189, | 46 | 2007-08-13 | Multiple Invoices | 11030.31 | 11030.31 | 3.1 |  | Labor Finders | 1645 |  | 11030.31 | OK | OK | 11030.31
|  | 47 | 2007-08-15 | 81507 | 331.8 | 293.4 | 3.1 |  | Ernest Statkus | 1657 |  | 293.4 | Invoice needs to be signed by BSWCD |  | 0
|  | 48 | 2007-08-15 | 81407 | 1711.46 | 1711.46 | 3.1 |  | Richard Naedele | 1660 |  | 1711.46 | Invoice needs to be signed by BSWCD |  | 0
|  | 49 | 2007-08-27 | 82707 | 468.9 | 406.8 | 3.1 |  | Ernest Statkus | 1666 |  | 406.8 | Invoice needs to be signed by BSWCD |  | 0
|  | 50 | 2007-09-04 | 91507 | 100 | 100 | 3.1 |  | Ernest Statkus | 1673 |  | 100 | no invoice |  | 0
|  | 51 | 2007-09-04 | 83007 | 1522.25 | 1522.25 | 3.1 |  | Richard Naedele | 1675 |  | 1522.25 | Invoice needs to be signed by BSWCD |  | 0
|  | 52 | 2007-09-11 | 91107 | 406.03 | 406.03 | 3.1 |  | Ernest Statkus | 1682 |  | 406.03 | no invoice |  | 0
|  | 53 | 2007-10-18 | 092807 | 130.07 | 130.07 | 3.1 |  | Ernest Statkus | 1705 | FDEP - City of Hallandale Beach | 130.07 | Invoice needs to be signed by BSWCD |  | 0
|  | 54 | 2007-10-18 | 090707 | 12000 | 12000 | 3.1 |  | Labor Finders | 1712 | FDEP - City of Hallandale Beach | 12000 | OK | OK | 12000
|  | 55 | 2007-11-16 | 090707 | 3239.69 | 3239.69 | 3.1 |  | Labor Finders | 1727 | FDEP - City of Hallandale Beach | 3239.69 | OK | OK | 3239.69
|  | 56 | 2008-12-12 | 121208 | 80 | 80 | 3.1 |  | Ernest Statkus | 1991 | FDEP - City of Hallandale Beach | 80 | OK | OK | 80
|  | 57 | 2008-12-23 | 32985 | 15380 | 630 | 3.1 |  | Earth Balance | 2068 | FDEP - City of Hallandale Beach | 630 | OK | OK | 630
|  | 58 | 2008-12-31 | 123108 | 1008.75 | 727.5 | 3.1 |  | Richard Naedele | 2000 | FDEP - City of Hallandale Beach | 727.5 | Invoice needs to be signed by BSWCD |  | 0
|  | 87 | 2007-12-31 |  | 34211.09 | 22922.36 | 3.1 |  | City of Hallandale Beach | In Kind Credit |  | 22922.36 | OK | OK | 22922.36
| Maintenance | 59 | 2008-12-31 | 123108 | 19460 | 2310 | 3.1 |  | Earth Balance | 2005 |  | 2310 |  |  | 0
| Total 70-110 |  |  |  | 109940.4 | 81668.84 | [5 empty] | 81668.84
70-111 · Equipment Rental-Water Tank
|  | 60 | 2007-02-28 | Multiple Invoices | 370.66 | 370.66 | 3.1 |  | Russell M. Setti | 1637 | FDEP - City of Hallandale Beach | 370.66 | Separate and summarize rental charges |  | 0
|  | 87 | 2007-12-31 |  | 34211.09 | 3568 | 3.1 |  | City of Hallandale Beach | In Kind Credit |  | 3568 | OK | OK | 3568
| Total 70-111 |  |  |  | 370.66 | 3938.66 | [5 empty] | 3938.66
70-113 · Transportation
|  | 40 | 2007-03-20 | 030207 | 1029.08 | 20 | 3.1 |  | Richard Naedele | 1534 | FDEP - City of Hallandale Beach | 20 | No reciept |  | 0
|  | 43 | 2007-07-24 | 72407 | 303.9 | 10.5 | 3.1 |  | Ernest Statkus | 1627 |  | 10.5 | Need travel reimbursement, not authorization forms |  | 0
|  | 45 | 2007-08-03 | 80307 | 203.79 | 24 | 3.1 |  | Ernest Statkus | 1642 |  | 24 | Need travel reimbursement, not authorization forms |  | 0
|  | 47 | 2007-08-15 | 81507 | 331.8 | 38.4 | 3.1 |  | Ernest Statkus | 1657 |  | 38.4 | Need travel reimbursement, not authorization forms |  | 0
|  | 49 | 2007-08-27 | 82707 | 468.9 | 62.1 | 3.1 |  | Ernest Statkus | 1666 |  | 62.1 | Need travel reimbursement, not authorization forms |  | 0
| Total 70-113 · |  |  |  | 2337.47 | 155 | [5 empty] | 155
70-115 · Sea Oats
|  | 61 | 2007-07-17 | 21503 | 860 | 356 | 3.1 |  | Horticultural Systems | 1695 | FDEP - City of Hallandale Beach | 356 | Why is this bill paid with a check to Horticultural systems when invoice is from EPR, Inc.? |  | 0
|  | 62 | 2007-07-17 | 21425 | 12180 | 12180 | 3.1 |  | Horticultural Systems | 1695 |  | 12180 | OK | OK | 12180
|  | 63 | 2007-08-01 | 2274 | 4250 | 4250 | 3.1 |  | Earth Balance | 1644 | FDEP - City of Hallandale Beach | 4250 | OK | OK | 4250
|  | 64 | 2007-08-10 | 2302 | 2700 | 2700 | 3.1 |  | Earth Balance | 1743 | FDEP - City of Hallandale Beach | 2700 | OK | OK | 2700
|  | 65 | 2007-08-31 | 083107 | 790 | 395 | 3.1 |  | Earth Balance | 1743 | FDEP - City of Hallandale Beach | 395 | OK | OK | 395
|  | 66 | 2008-08-20 | 2328 | 3150 | 3150 | 3.1 |  | Earth Balance | 1743 | FDEP - City of Hallandale Beach | 3150 | OK | OK | 3150
|  | 67 | 2008-08-24 | 2340 | 3600 | 3600 | 3.1 |  | Earth Balance | 1743 | FDEP - City of Hallandale Beach | 3600 | OK | OK | 3600
|  | 57 | 2008-12-23 | 32985 | 15380 | 14750 | 3.1 |  | Earth Balance | 2068 |  | 14750 | OK | OK | 14750
| Maintenance | 59 | 2008-12-31 | 123108 | 19460 | 14750 | 3.1 |  | Earth Balance | 2005 | FDEP - City of Hallandale Beach | 14750 | Not purchased. Not eligible.
| Total 70-115 |  |  |  | 42910 | 41381 | [5 empty] | 41381
70-116 · Posts
|  | 68 | 2007-03-02 | 030207 | 2178.3 | 835.17 | 3.1 |  | Home Depot | 1513 | FDEP - City of Hallandale Beach | 835.17 | OK | OK | 835.17
|  | 69 | 2007-03-29 | 5283723 | 1568.23 | 1568.23 | 3.1 |  | Home Depot | 1549 | FDEP - City of Hallandale Beach | 1568.23 | OK | OK | 1568.23
|  | 70 | 2007-05-09 | 3332436 | 320 | 276.69 | 3.1 |  | Home Depot | 1598 | FDEP - City of Hallandale Beach | 276.69 | OK | OK | 276.69
|  | 71 | 2007-10-18 | 090607 | 379.06 | 371.22 | 3.1 |  | Home Depot | 1707 | FDEP - City of Hallandale Beach | 371.22 | $60 refund subtracted from invoice |  | 309.22
|  | 72 | 2007-10-25 | 121007 | 379.06 | 292.35 | 3.1 |  | Home Depot | 1715 | FDEP - City of Hallandale Beach | 292.35 | Invoice number and date wrong |  | 0
| Total 70-116 |  |  |  | 4824.65 | 3343.66 | [5 empty] | 3343.66
70-117 · Rope
|  | 88 | 2007-03-12 | 234585 | 5524.74 | 1827 | 3.1 |  | Miami Cordage | 1525 |  | 1827 | OK | OK | 1827
|  | 74 | 2007-04-12 | 234681 | 2131.5 | 2131.5 | 3.1 |  | Miami Cordage | 1557 | FDEP - City of Hallandale Beach | 2131.5 | OK | OK | 2131.5
|  | 75 | 2008-12-17 | 254416 | 744.72 | 744.72 | 3.1 |  | Miami Cordage | 2017 | FDEP - City of Hallandale Beach | 744.72 | OK | OK | 744.72
| Maintenance | 76 | 2008-12-31 | 142421 | 8038 | 8038 | 3.1 |  | Miami Cordage | 2004 |  | 8038 | Crossed out by BSWCD |  | 0
| Total 70-117 |  |  |  | 8400.96 | 4703.22 | [5 empty] | 4703.22
70-118 Irrigation Supplies
|  | 87 | 2007-12-31 |  | 34211.09 | 7650.73 |  |  | City of Hallandale Beach | In Kind Credit |  | 7650.73 | OK | OK | 7650.73
| Total 70-118 |  |  |  | 34211.09 | 7650.73 | [5 empty] | 7650.73
70-123 · Fertilizers
|  | 77 | 2007-02-02 | 103234 | 792 | 372 | 3.1 |  | Universal Enterprises Supply Corp. | 1483 | Osmocote and Horti-Sorb | 372 | OK | OK | 372
| Maintenance | 78 | 2008-12-31 | 475720 | 2286 | 996 | 3.1 |  | Universal Enterprises Supply Corp. | 2003 |  | 996 | OK | OK | 996
| Total 70-123 |  |  |  | 3078 | 1368 | [5 empty] | 1368
70-124 · Miscellaneous Supplies
|  | 68 | 2007-03-02 | 030207 | 2178.3 | 511.5 | 3.1 |  | Home Depot | 1513 | FDEP - City of Hallandale Beach | 511.5 | OK | OK | 511.5
|  | 79 | 2007-03-20 | 030207 | 1029.08 | 56.58 | 3.1 |  | Richard Naedele | 1534 | FDEP - City of Hallandale Beach | 56.58 | No reciept |  | 0
|  | 72 | 2007-05-09 | 6310-296274 | 320 | 43.31 | 3.1 |  | Home Depot | 1598 | FDEP - City of Hallandale Beach | 43.31 | OK | OK | 43.31
|  | 81 | 2007-07-26 | 6310-300803 | 210.61 | 210.61 | 3.1 |  | Home Depot | 1630 | FDEP - City of Hallandale Beach | 210.61 | No invoice |  | 0
|  | 84 | 2008-12-22 | 122208 | 8.44 | 8.44 | 3.1 |  | Richard Naedele/Walgreens | 1996 | FDEP - City of Hallandale Beach | 8.44 | Check made out for $4.18 |  | 4.18
| On Order for maintenance | 73 | 2008-12-31 | 6310-346380 | 4172.17 | 758.37 | 3.1 |  | Home Depot | 2002 |  | 758.37 | OK | OK | 758.37
| Sand Fencing | 59 | 2008-12-31 | 123108 | 19460 | 2400 | 3.1 |  | Earth Balance | 2005 |  | 2400 | Crossed out by BSWCD |  | 0
| Total 70-124 |  |  |  | 7918.6 | 1588.81 | [5 empty] | 1588.81
70-125 · Water Absorption Additives
|  | 77 | 2007-01-31 | 103234 | 792 | 420 | 3.1 |  | Universal Enterprises Supply Corp. | 1483 |  | 420 | OK | OK | 420
| On Order for maintenance | 78 | 2008-12-31 | 475720 | 2286 | 1290 | 3.1 |  | Universal Enterprises Supply Corp. | 2003 |  | 1290 | OK | OK | 1290
| Total 70-125 |  |  |  | 3078 | 1710 | [5 empty] | 1710
70-126 · Signage - Statutory
|  | 85 | 2007-03-29 | 103721 | 1225 | 600 | 3.1 |  | Designed Advertising, Inc. | 1541 | FDEP - City of Hallandale Beach | 600 | OK | OK | 600
|  | 86 | 2009-01-12 | 104642-01 | 2785 | 2785 | 3.1 |  | Designed Advertising, Inc. | 2015 | FDEP - City of Hallandale Beach | 2785 | OK | OK | 2785
| Total 70-126 |  |  |  | 4010 | 3385 | [5 empty] | 3385
Total 7000 · Project Expense |  |  |  |  | 349892.92 | 228939.44 | [5 empty] | 228939.44 |  |  | 145971.94