
AMENDMENT TO THE FACT SHEET AT

THE TIME OF FINAL PERMIT ISSUANCE

DATE:

July 12, 2006 
PERMIT NUMBER:
FL0021270  (PA File No. FL0021270-010-DW1P)

NAME OF APPLICANT:
City of Fort Myers

FACILITY NAME:
City of Fort Myers South Wastewater Treatment Plant 

I.
CHANGES TO PERMIT FROM DRAFT PERMIT TO FINAL PERMIT STAGE:
A.
Comments in the City of Fort Myers’ & CDM’s e-mail of March 28, 2006: 

Comment 1:  Specific Conditions I.C.12, 13 & 14 (page 14 of 31) are all conditions imposed on a facility with an active Reclaimed Water or land application system. I would like confirmation from the Department that these conditions will only become effective upon start up of the South Plant’s reclaimed water production system.
Response:  Specific Condition Nos. I.C.12, 13 & 14 of the permit were revised to clarify that these conditions become effective upon start up of the South Plant’s reclaimed water production system.
Comment 2:
Conditions VI.(2) 5, 6, 7, & 8 all refer to construction deadlines for the reclaimed water production system. Please check back on your notes from our final meeting with the FDEP when we clarified these dates. The dates in the draft permit do not match what I recall the City committing to. I believe we committed only to beginning construction of the production facility prior to the expiration of this permit. The operating protocol, construction completion, and reuse start up dates were never agreed upon as conditions of this operating permit.

Response:  :  Specific Condition Nos. VI.2. 7 &  VI.2. 8 were deleted. Specific Condition Nos. VI.2. 5 and VI.2.6 were revised as follows:
	5
	Begin Construction of 9.0 mgd plant modification.
	May 15, 2011

	6
	Submit a complete reuse operating protocol for the WWTP modifications associated with reclaimed water production facilities at this plant, in accordance with Rules 62-610.320(6)(c),FAC, 62-610.320(6)(f), FAC, and 62-610.320.463(2), FAC.
	At least 90 days before submitting the certification of completion of construction for the reclaimed water treatment facilities or

with the application for permit renewal, whichever is sooner.


B.
Comments in the City of Fort Myers’ engineering consultant’s (CDM’s) e-mail of March 31, 2006:

Comment 1: Administrative order first page I believe contains the Central plant address in the write up, not the South plant address. 
 

Response: The site address was revised in item No. II.2. 

Comment 2: Item 9 of the administrative order states that the City shall be in full compliance with the effluent limitations for Copper by a certain date. However then items 10 and 12 states that if the City is not in compliance the surface water discharge needs to be abandoned. Item No. 9 seems to be redundant.
Response: The segment of the Caloosahatchee River that the outfall discharges to is on the 303(d) list of impaired waters for Copper.  No change was made to this portion of the administrative order.

Comment 3: The administrative order gives the City 12 months to apply for, construct and put into operation an injection well (or alternative disposal) if the effluent limitations for copper cannot be met. This seems to be a very short time frame and should be at least 18 months based on my experience.

Response: The administrative order gives the City until October 30, 2008 (approximately 2 ½ years) to abandon the surface water discharge (i.e., apply for, construct and put into operation an injection well or alternative disposal) and 17 months from May 30, 2007 date referenced in III.1.9 of the administrative order to construct and put into operation an injection well (or alternative disposal) if the effluent limitations for copper cannot be met by May 30, 2007. No change was made to this portion of the administrative order.
Please note that the permit number was corrected in Item No. II.4 of the administrative order, (copy attached).

C. Canges after the Intent to Issue permit was execiuted:

1. The list of Department established analytical methods, and corresponding MDLs (method detection limits) and PQLs (practical quantification limits), which is titled “Florida Department of Environmental Protection Table as Required By Rule 62-4.246(4) Testing Methods for Discharges to Surface Water” was revised in April 2006. Specific Condition No. I.C.9 of the permit was revised to not reference the June 21, 1996 table.  The new list of Department established analytical methods, and corresponding MDLs (method detection limits) and PQLs (practical quantification limits), which is titled “Florida Department of Environmental Protection Table as Required By Rule 62-4.246(4) Testing Methods for Discharges to Surface Water” is available at http://www.dep.state.fl.us/labs/library/index.htm. The 1996 list included an approved test method for total recoverable bromine. The 2006 list does not include an approved test method for total recoverable bromine.  Accordingly, total recoverable bromine was removed from Part II.1.7 of the administrative order and replaced with Chlorodibromomethane  Dichlorobromomethane, and associated precursors to Chlorodibromomethane  and Dichlorobromomethane.

2. The completion dates in Part III.1 & 2 of the administrative order were extended four months.

II.
PUBLIC COMMENTS:

a.
Public Comments to the Notice of Draft Permit:

- Public Comments - None

- Comments from the Permittee (Received 3/28/06)



- Notice of Draft Permit Issued (03/23/06).



- Public Notice of Draft Permit (03/28/06)



- End of Public Comment Period to Draft Permit (04/27/06) .


b.
Public Comments to the Intent to Issue:

- Public Comments None



- Notice of intent (Issued on May 10, 2006 )

- Public Notice of Intent to Issue Permit (Advertised on May 26, 2006 )

· Received proof of publication (June 12, 2006)

· End of Period to Petition for an Administrative Hearing ( June 12, 2006)

III.
EPA CONCURRENCE:



EPA concurred in a letter of April 13, 2006.
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