|  | Implementation Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Solution # |  |  | EXAMPLE |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 1 | OGC will update enforcement manual with more examples of NOVs that have been approved. But make it clear that all NOVSs must be reviewed by OGC. | 62, h25 | make list of desired NOV templates | Alissa | 5/1/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | assign staff to draft templates | Allissa | 5/7/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | draft templates | OGC staff | 6/1/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | review and approve templates | Alissa, Sandra | 6/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | provide to districts via email notification, ERPA announcement, and | Alissa | 6/20/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | post on team website and in Enforcement Manual | Jodi, OGC clerical | 6/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 1 EM | OGC will update enforcement manual with more examples of NOVs that have been approved. But all NOVS's must still be reviewed by OGC. | 62, h25 | Get examples from districts like for expanded structure, vessel moored outside area, unauthorized structures, etc. For proprietary only | Ryan | 9/22/10 | complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Districts tell OGC what type of templates they want | Greg | 5/15/10 | complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | OGC review District Needs | Alissa | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Provide approved list to team | Alissa | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Draft appropriate templates | Alissa | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Internal OGC Review | Alissa | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post on enforcement Manual | Alissa | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 2 Opm | Permit or Order Compliance Inspection. Staff shall review task deadline checklist (permit requirements) prior to the site inspection. Review judgment/order prior to and post inspection to confirm everything is completed per the order. Write inspection report within in 1 week of inspection. Create a standardized statewide C&E inspection report. Supervisor shall review report to confirm all actions were completed and must sign off on the case closure. Need to include caveats regarding the use of the checklist as an aid. Transmit inspection report as soon as it is completed to DSL. | 90 | Refine inspection report template to team for review | Jim | 4/15/10 | 4/12/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Team comments to Jim Sent to Tim for approval 4/28/10 | Jim | 4/30/10 | 4/23/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Proposed draft for Program review/approval | Donna/Tim | 5/15/10 | 5/17/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Finalize draft and post to website and OPM | Jim/Jodi/Kate | 6/1/10 | complete |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 3 EM Opm | Districts shall prioritize cases on a monthly basis with ERPA. The ERPA will then communicate with OGC regarding the District's priorities on a monthly basis. Add to Legal Case Tracking (LCT) form a required Low, Medium, High priority box with comments. Supervisor shall initial that the document has been proof read and the property address and responsible party was identified/verified. State Lands Inspector (SLI) will include a copy of the deed, property appraiser information, and Sunbiz info if applicable. OGC will look at substance instead of style and will include standardized language in email communicating that the draft document has been approved by OGC. Aliki will send out a consolidated case list every month and ask districts to prioritize top five. | 81, h40, h29, 82, h15 | Type paragraph on procedure | Jen | 7/1/10 | 7/30/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Communicate this to PAs | Jen | Next ERPA after 9/30 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Districts provide any additional feedback for LCT form | Jen | 9/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add Low, Med, Hi Priority box with comments section to LCT form | Alissa | 6/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Put form and procedure in OPM (form in Enforcement Manual) - State Lands component | Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | OGC meet with Attorney's to discuss review of documents | Alissa/Ryan | 6/15/10 | 4/30/10 |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 4 | A point of contact (POC) in district for SSL compliance and enforcement policies will be identified. Policy discussion/changes and summaries discussed with ERPAs will be sent to the POCs. OGC topics will be grouped on ERPA teleconferences or with OSLER conversations. Create a repository of these policy decisions. | 41, h23, 45, h22, 39, h30, h31 | Get with Kate prior to next ERPA for repository search webinar | Aaron | 5/31/10 | 5/13/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Get with each district to create list with POC | Aaron | 4/26/10 | 4/26/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Give list to OGC, OSLER | Aaron | 4/26/10 | 4/26/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Create expectations for POC and share with POCs | Aaron | 4/26/10 | 4/26/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to team for comments/revisions | Aaron | 4/30/10 | 4/30/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send memo out to Districts/POCs | Tim | 6/30/10 | 6/22/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Group topics in ERPA teleconference into like topics (specific time for OGC) - communicate this time to OGC (work with Kate G.) | Aaron | 4/26/10 | 5/27/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Inform OGC staff of the time portions | Aaron | 4/28/10 | 5/27/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Create procedure for repository of OSLER discussion topics (email back response and distribute to point of contacts) | Aaron - Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 5 opm | Develop a contact list for OSLER and OGC to address specific questions (stating their specialization). | 42, 37, 38 | Draft the contact list for OSLER/DSL | Jen | 6/1/10 | 6/18/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Draft the contact list for OGC | Ryan | 6/1/10 | 6/15/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Provide list to team for review | Ryan & Jen | 6/1/10 | 6/18/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | OSLER approves list | Tim | 6/30/10 | 7/29/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post lists on website and OPM | Jodi, Kate Grosmaire | 9/15/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 6 opm | The Districts will generate a list of division of responsibilities and send to DSL for concurrence concerning assignments. Post on Operations & Procedures Manual (OPM). The draft will be sent to the Districts and DSL. [District duties versus DSL duties, to aid in the clear understanding of division of duties (invoice delivery/collection, reassignments, Notice to Correct letter, etc.)]. | h17 | Create responsibility table | Aaron, Russell, | 6/25/10 | 7/06/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Coordinate revisions with Team | Aaron, Russell, Scott/Jeff/Tim | 7/16/10 | 7/28/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Coordinate table with DSL and OSLER | Aaron, Russell | 7/31/10 | complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Revise and re-send | Aaron | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post table on OPM | Kate Grosmaire | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 7 | Within 20 days of identifying deficiencies in the Delegation of Authority (DOA) package, DSL will contact the district processor via email about the deficiency stating what is needed. If there is a re-occurring problem DSL will contact the ERPA in the District. District staff will develop a tickler system to get reminders to checkup on status of DOA. DSL will copy District on correspondence with lessee, so the District is aware of any problems or holdups. | 112, 113 | Draft protocol Memo for Jeff Gentry re (20 days-lessee corr) discuss with Ann Lazar ILMS changes | Aaron/Russell | 7/12/10 | 7/29/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Coordinate-Implement memo | Aaron/Russell/Jeff G | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Develop Procedure for checking on lease (tickler-ILMS?) | Aaron/Russell | 5/26/10 | 6/1/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Inform SLI’s of checkup procedure at quarterly SSL mtg | Aaron | 2nd qrtr mtg. |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 8 | Create a task deadline checklist (related to permit conditions or consent order requirements) to send to the respondent that includes a summary of each action and due dates. A site inspection will take place to confirm that what respondent tells you is accurate. | 56, 58 | Draft task deadline checklist for respondent | Tanya | 05/14/2010 | done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to team for review | Tanya | 5/21/10 | 5/18/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review and implementation of memo | Tim Rach | 7/9/10 | 7/19/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add to SSL website | Jodi? | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add to New employee checklist | Tanya | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Inform SLI’s of procedure for implementation task deadline checklist at quarterly SSL mtg. | Tanya | 2nd qrtr meeting |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 9 opm | District enforcement staff will communicate time constraints to the DSL - Title Section so that Title Section understands priorities. Add deadline field to Title Determination request form. | 2 | Change Title Form to include time frame | Aaron | 5/26/10 | 6-9-10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | OSLER approval | Tim | 6/11/10 | 6/11/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post new form to OPM/Districts/Title | Kate Grosmaire | 9/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Inform staff at quarterly SSL mtg to convey time constraints to title | Aaron | 2nd qrtr mtg. |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 10 EM opm | The SLI needs to organize the file and Case Report (CR), before sending to OGC. Include Case summary (story) with CR. OGC will re-review current CR model to determine whether any changes are necessary. | h34, h42, 64, 77, 78, 79, 83 | Draft memo on file organization. | Tanya | 05/14/2010 | 5/14/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | OGC will review | Alissa | 7/18/10 | 7/19/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to team for review | Tanya | 7/25/10 | complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review and implementation of organization memo | Tim | 9/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Re-review CR model and make improvements where necessary | Alissa? | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add to SSL website | Jodi? | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add memo on file organization to New employee checklist | Tanya | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Update OPM and Enforcement Manual with updated CR model. | Kate Grosmaire/paralegal-OGC | ? |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 11 opm | Districts to have weekly meetings with manager/supervisor to go over important issues with the SLI. Management must have meeting agenda placed on common drive so any SLI can add to the agenda. SLI must have penalty calculations, site inspections report and case summary available for the meeting. This can later be used as preparation for the meeting with the respondent. | 65, 67, 68, 24, 70, h39, 103 | Submit draft agenda to team | Eric | 5/14/10 | done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Team comments to Eric |  | 5/28/10 | Done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Finalize draft |  | 6/4/10 | Done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | get approval from Donna | donna | 6/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post to OPM | Kate G | 7/15/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 12 | Reductions of lease fees in arrears, including interest, will not be considered unless it’s been reviewed by DSL. Reductions in regulatory penalties will be considered if respondent agrees to the findings of violation in the consent order. SLI can consider financial ability. Consider restoration as a priority; see video teleconference with John Alden and Larry Morgan for more information on ability to pay determination. Provide web link with training list to staff. **Team needs to discuss this more before we seek Champion approval | 105 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Meet with Bob Ballard to discuss | Ryan | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Report back to team | Ryan | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Memo of state lands penalty guidelines to be drafted | Donna |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 13 | When the respondent has an attorney or consultant involved in the resolution, require that all comments/changes to the draft consent order (CO) be submitted in revisions mode 5 business days prior to the meeting for efficiency and discussion purposes. Cancel the meeting if they do not comply and go to NOV or Case Report (CR). If the respondent is acting on their own behalf provide them with 90 days from the date of the proposed CO to reach an agreement (signed CO). If the respondent is unresponsive, wait 30 days from the date of the Chapter 18-14 letter (call after 20 days) and initiate a NOV or CR. | H26, 57, h43,h37, 87, 101, 98 | Draft a memo to districts | Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to Alissa for comment |  | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to Tim for approval |  | 11/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to districts |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 14 opm | Include name of party in signature line on Consent Order (CO) and resend the entire CO if the wrong party signs it. Put on the Internet Model. | 86 | put in OPM to Include the name of the party in the signature line (name of respondent) | Donna | 7/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send email to Mary and Aliki to add to website | Donna | 9/8/10 | done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | add to the model with embedded directions to spell out respondent’s name | Alissa | 9/8/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 15 opm | After receiving the signed consent order from the respondent, the SLI will review the document prior to execution by the Department to determine whether the respondent changed and language in the consent order; any changes that are made by the respondent must be reviewed by OGC prior to final execution. | 89 | Put direction in the OPM | Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 16 EM | OGC shall outline expectations for writing style and substance depth. OGC will let the District manager or supervisor know if they are constantly having issues with draft documents. As an interim measure, OGC shall provide a library of NOV examples [see solution no. 1]. OGC will finish updating the enforcement document forms (templates) in the enforcement manual. | h19, h34, h38, h42, 66, 80 | Make sure link to writing style is active and working. | Alissa | 5/15/10 | Done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Meet with enforcement attorneys and advise them to let manager and supervisor know if we are constantly having issues with draft documents. | Alissa | Completed | 4/26/2010 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Inform SLI’s they can use oculus to see a “library of NOV’s”. (find out how they can get access) | Alissa | After 9/30 ERPA |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Finalize updating forms in enforcement manual | Alissa | 12/01/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 17 | Revise the OPM guidance and TUA template to allow for flexibility regarding six month to 12 month term considering cooperation by the lessee, AP/ public interest, and timeframes for corrective actions. 12 month should be the standard term. Revise the TUA template to include approved optional language. TUA fees will be locked into rate at the time of execution. | h35 | Teleconference to discuss topic. | JJ, Jim, Ryan and Susan | 4/22/10 | 4/22/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Draft revised language for OPM and TUA preparation guidance and forward to Susan and Jim for comments. | JJ and Ryan | 4/26/10 | 4/26/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Address/implement/discuss comments on drafts. | JJ, Jim, Ryan and Susan | 5/7/10 | Done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Submit final revised TUA and revised TUA preparation guidance to Tim, (Donna?) and Alissa for comments. | JJ | 7/15/10 | done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post updated TUA template and guidance (1720) to OPM (link to EM) and on OGC Enforcement site | Kate, Aliki | 9/20/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 18 opm | Develop a proprietary penalty matrix when Chapter 18-14 revisions are approved. Include categorization of common violations and good faith adjustments (as guidance not rule). Include instructions on how to use the Matrix. | 44, 17, 31, 61, 26, 32, 29,30 | Contact SLIs to develop list of appropriate common violations | Donna, Scott W, Ryan, Terri | 5/15/10 | complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Draft matrix | Donna, Ryan | 10/01/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Get team review of draft | Donna | 10/08/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Get OGC approval | Alissa, Ryan -Larry | 10/29/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post in OPM | Kate G | 01/3/11 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 19 EM | Once the new rule (Chapter 18-14) is adopted, two warning letters will be developed; one mixed and one proprietary only. | 46, 47 | Draft mixed regulatory and proprietary WL | Alissa, Ryan | When rule is adopted 11/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Draft proprietary only WL | Ryan | When rule is adopted 11/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Get OGC approval (Larry) | Alissa, Ryan |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Once approved and adopted, post in Enforcement Manual | Laurie Roughton | When rule is adopted |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 20 EM | OGC will develop a Default Final Order for 18-14 cases. | 96 | Draft a model DFO proprietary only | Ryan, Chris Byrd | 9/01/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review draft by OGC | Alissa, Larry, Sandra | 9/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Include in Enforcement Manual |  | After rule adoption |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 21 opm | Refer to the enforcement manual regarding how to get legal access to a site. Try waterside access (look to CAMA and Parks for cooperation). Access water side via neighboring property. | 60 | Send email to team requesting favorite websites used to id property owners | Donna | 6/18/10 | Done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Draft paragraph explaining where information is located | Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to Alissa for review | Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post in OPM | Kate G | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | See solution #41 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 22 | OGC will look at providing more specific guidance in the enforcement manual such as using an actual Case Report as an example explaining why various elements are needed or helpful. Put this information in the re-write of SLER 1710 (or in the SLER appendix of the Enforcement Manual) and discuss in upcoming ERPA teleconferences. | 94, 95 | OGC to re-review current case report to see if there need to be revisions and will consider questionnaire in lieu of case report model | Alissa and Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Jim send File Summary form to Mike | Jim | 5/1/10 | done |  |  |  |  |  |  |  |  |  |  |
| 23 | Obtain clear understanding of site history via use of: checklist/ SLERC form. | 9, 25, 36 | Send SLERC form to Tim and Donna for review and comment | Mike S | 4/9/10 | 4/9/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Tim and Donna send comments back to Mike | Tim, Donna | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to team for comment | Mike | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Finalize and implement | Mike | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 24 opm | Clearly communicate the expectations of the enforcement/settlement meeting with the respondent. Provide respondent with a checklist of items to bring to meeting and be prepared to discuss. | 102 | Develop expectations (one for SL and one for Regulatory) | Greg// | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Get comments from team | Greg | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Compile comments send to OSLER | Greg | 11/1/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | post to OPM | Kate G | 11/15/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 25 | Attorneys must inform SLI of any petitions and if SLI is repeatedly not being made aware of the status of cases, the SLI will inform either the deputy or lead attorney. | 107, 115 | Meet with Enforcement Attorneys and told them they must inform the SLI of petition. | Alissa | Complete | 4/26/2010 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Tell SL attorneys the same thing as above | Ryan | complete |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 26 | All attorneys will use standard responses when responding to the Districts and include their direct phone number requesting the SLI to contact that attorney if there are any further questions. | 84 | Enforcement Section created standard language that will be used when returning reviewed documents to the district. | Alissa | complete | 4/28/2010 |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 27 opm | SLI will look in LCT to determine which OGC attorney is handling the case. Anyone who needs to have access to LCT can get their own password and login. | 92 | Put guidance in OPM | Donna, Kate G | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Ask Mary about a generic log in and password | Donna | 6/18/10 | done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add ‘get LCT access’ to new hire checklist | Tanya | 10/15/30 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 28 | Establish a process improvement event for eviction and trespass. | h41 | SEPARATE PROJECT: task assigned to Mike Long as a follow-up from projects #1- |  | 5/14/10 | Done |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 29 opm | SLIs will use "Accurint", law enforcement, or will contact Laurie Roughton (OGC) if they are having trouble determining the correct name/address of responsible party. | 15, 16 | Write guidance, send to Donna | Jim and Greg | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review and approve | Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Put guidance in OPM | Kate G | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 30 EM | Revise and update the enforcement manual guidance including more case specific examples so cost & expenses fees can be calculated. Further discuss with OGC. | 35 | Ask district what for input regarding what type of models they want | Alissa | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review what kind of models district wants | Alissa |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Draft Models |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add Models to OGC Enforcement Manual |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 31 | Include OGC link to flowchart in SLI new employee checklist and inform current SLIs of that link. | h14 | Update SLI new employee checklist with link to OGC flowchart | Tanya | 7/9/10 | done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Inform SLI’s of new and existing link to OGC flowchart at quarterly SSL mtg. | Tanya | 2nd qrtr meeting |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 32 opm | For tricky history questions contact OGC. OGC will include a box in the Legal Case Tracking (LCT) form for assistance. SLI must include case history summary with the LCT form so the correct attorney can be assigned. If there has already been some involvement by OGC staff, the SLI will put the attorney's name on the LCT form when it is sent up for OGC review and assignment. | 40 | Add assistance box to LCT form and request for summary of case history. | Alissa | 6/1/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | add question blank about consulting attorney name on LCT | Alissa | 6/1/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add to enforcement manual and SLERP OPM | Alissa/Donna | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 33 | Bring up problem trends with cases processed by the WMDs at upcoming Anti-drift meetings. | 6 | Remind WMDs at next Anti-Drift meeting that they need to seek guidance/assistance from DEP for Proprietary projects | Tim | 6/2/10 | 6/2/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Follow up discussion with WMDs regarding specific cases and discuss resolutions, possibly schedule other webinars | Tim, Lucy Blair | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Schedule specific webinars regarding rule implementation/ training for WMDs | Jennifer Butler, Ann Lazar | 8/30/10 | done |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 34 EM | Put guidance in the Enforcement Manual as to when to do a Case Report versus a Notice of Violation. Call OGC with questions regarding which path to choose. | h27, h28 | Review guidance in enforcement manual and improve the guidance if necessary | Alissa | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 35 | Contact Gary Kekelis in OTIS to see if accuracy issues can be addressed. Also someone in SL to address GIS layer. **consider combining this with 36; what layers are staff considered with? | 7 | dropped |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 36 | Develop a tutorial to help staff find the information available on existing easements, leases, permits, and TIITF deeds using Map Direct and BTLDS if they have a location for the activity. Give a webinar or GoTo Meeting to demonstrate use of the tutorial. | 4, 8 | Solicit problems from team and Develop draft tutorial | Allyson Grosmaire | 7/15/10 | done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review draft tutorial | Ann Lazar and Donna Kendall | 7/21/10 | Done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Finalize tutorial | Allyson Grosmaire | 7/31/10 | Done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Give Webinar on tutorial | Kate Grosmaire, Jennifer Butler, Ann Lazar | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Put tutorial on depnet | Kate Grosmaire |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add to new employee training checklist | Tanya | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 37 opm | The Districts need to get to access to title determinations contained in OCULUS. Title will email when determination is complete. Copies of title and records determinations can be obtained on the DEPnet, destination state lands, scroll down select Title Determination Worksheets. The direct web address is http://199.73.242.56/title.asp | 3 | Inform the District Offices via ERPA telecon regarding the DSL website to access title determinations. | Ann Lazar | 04/29/10 | 4/29/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Provide web link information in OPM | Ann Lazar | 06/30/10 | Done |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 38 opm | Develop easement inspection report form with assistance from Susan Riggs (Kathy Griffin); utilize the existing lease inspection report during the development. | 18 | develop report | Aaron | 7/30/10 | 7/29/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Coordinate with Kathy to finalize | Kathy | 9/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send draft to Tim | Aaron | 9/22/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post to OPM | Kate | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Announce at quarterly meeting | Aaron | TBD, 3rd qrtr |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 39 opm | Provide guidance to staff on how to deal with situations when multiple site numbers are identified in PA with the same property; plan is to link each site number for future searches in PA or ERPce (correct inaccurate information). | 5, 1, 21 | Draft guidance with Linda | Linda Hodges, Jen | 6/25/10 | 6/28/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Provide guidance to ERPA’s | Jen | 7/1/10 | 7/1/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Discuss at the next ERPA teleconference | Jen | 7/1/10 | 7/1/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post to the OPM | kate | 9/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 40 | Coordinate with Linda Hodges to discuss feasibility to update lat/longs in PATS database. Submit in batch files in excel spreadsheet quarterly.—Lat/longs cannot be updated | 5,1,21 | DROP |  |  | DROP |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Establish procedure for updating PATS lat/longs | Linda Hodges | 8/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to POCs in districts | Tim | 8/31/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 41 opm | Create a list in the OPM manual that identifies the available databases/websites (property appraisers, aerials, Sunbiz, etc.) so everyone has knowledge of all available databases/websites (Internal and external sources). | 10, 53 | See solution #21 | Jim/Donna |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 42 | Incorporate State Lands lease inspection form into existing PDAs | h12, 19 | Work with IT to put several forms on the PDAs | Donna, Calvin | Long-term |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Acquire PDAs | Calvin | Long-term |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 43 Opm, em | Ensure OPM is accurate for process of closing cases and is being implemented by SLI. | 91 | Review closure form /memo and guidance in Enforcement Manual | Alissa | complete |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Write guidance if needed | Aliki | January 2011 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Collect and Ensure the District closure forms are consistent with Enforcement manual | Alissa | Aug 13, 2010 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Ask Mary (Aliki) if she’s getting the same info from every District | Alissa | complete |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Link OPM to EM for closure forms and guidance | Kate Grosamire/Donna | Jan 2011 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 44 | Under new rule, memo to file granting extension and update to ERPce and written notification (email) to respondent- to tickle staff of new time extensions. See event notes. Extension is for time for 18-14 letter. Create procedure for short extensions and ERPce tickler for time extension. Write standard language with memo template to reply with when asked for extension | 97 | Write language and memo template | Greg | 9/1/10 | done |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Send to Alissa and Tim for review | Greg | 9/1/10 | 8/3/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review and approve | Tim & Alissa | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Distribute template to Districts, post on OPM | Donna/Kate | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Set up a ERPce tickler for 18-14 letter extensions | Linda Hodges | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 45 | Ensure correct email/physical address by including property appraiser print out or email print out. (so AA confirms address) | 73 | Draft email directing staff to include the Prop. Appraiser print out and send to Tim & ERPA’s | Jen | 8/1/10 | DROP |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 46 | Attorney will use standard approval language in email returning CO/NOV. | 85 | Create standard language for emails returning unapproved NOV/CO , approved NOV, and approved CO. | Alissa | Complete | 4/28/2010 |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 47 | Design determination procedures for DSL for single issues versus large areas (14). DSL give SLI the lines/overlays at the beginning, when specifically requested by SLI for special cases. Make better use of form and use comments section to explain what we need. | 13, 14 |  | Jim | 5/15/10 | complete |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 48 | Have DSL send the C&E report to OGC. SLI can enter OGC attorney and case status in the C&E spreadsheet. | 117 | Add Ryan Osborne to distribution list | Kathy Griffin | COMPLETE | 7/1/10 |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 49 | Ensure Admin staff and Department staff are consistently using enforcement flow chart to determine which enforcement documents go to which OGC staff. | 74, 75 | Put in new employee training | Alissa Tanya | complete |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Ensure Paper flow chart is on Enforcement manual | Alissa | Complete | n/a |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 50 | solution from first event = Memo from Mimi (Memo from Deputy Secretary Drew establishing guidance on State Lands formal enforcement procedures and timelines, including accountability and timeframes to achieve a timely resolution) Memo will be updated with realistic and valid process. | KAIZEN #s 5,12,14 | Memo to be updated after new 18-14 rule is adopted | OGC | Will begin revisions after rule is adopted |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 51 | Contact Jonathan Watson to find out if other available materials fromother websites can be incorporated into MapDirect. Or make website available. Make lists of what sites are available | 11 | Kate to contact Jonathan | Kate | 9/24/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 52 | SLI shall not give verbal extensions to Respondent, concerning NOVs and complaints; OGC needs to be involved and grant or deny extension. Include in OPM and Enforcement manual | 111 | Draft Guidance | Alissa | Jan 2011 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Have Aliki review guidance |  | Jan 2011 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post in Enforcement manual |  | Jan 2011 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 53 | No change proposed, review OPM and Enf Manual to ensure that $25k is for regulatory. | 28 | Review Enforcement Manual and Directive 923. | Alissa | complete | 7/29/10 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Confirm guidance is in 923 (paragraph 11) and CPAM is in enforcement manual | Alissa | complete | 7/29/10 |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 54 | Require staff to give both the hard copy file & electronic file to Supervisor/EM for proper review (map change) | 63 |  | Solved somewhere else |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 55 | Staff should ensure OGC field has been added to include OGC processor and status field to existing C&E report. (map change) See solution #48 | 116 |  |  | complete |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When to check on status? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 56 | If SLI refers a case closure memo to OGC and OGC does not close the case, then OGC clerical will inform SLI why its not being closed. | 114 | Advise OGC clerical to let SLI know why a case cannot be closed if they sent a closure memo | Alissa | Complete | Complete |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 57 | Provide guidance to staff to capture most important elements of inspections. (?) in review at district level should resolve its inconsistencies in language. (20) Comment field is left blank or insuffuceint in ERPce -include manadatory fields to fill out ERPce. Should be consistent with language in 18-20 and 18-21 (barrier #23) | 20, 23 | Write and send the guidance to team for comment | Eric Shea | 8/13/10 | complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Compile comments and send to Donna and Tim for approval | Eric | 8/30/10 | complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Draft a memo to outline procedure | Tim |  | complete |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Post in OPM | Kate |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 58 | previously used does not equal 'model' in terms of OGC review | 93 | guidance needs to be put in EM | Alissa | 1/1/11 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | additional language to some of the models also addresses appropriate model usage | being done in another solution |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 59 | Staff should only utilize over due function when there are backlog issues. Staff should pull the weekly reports from the activities due function (Can ERPce send the activities report automatically? Can we change it so there aren't two different places?) | 54, 55 | check with Linda to see if it can be done | Donna | 8/2/10 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | DROP |  | Dropped |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 60 | Check with Pat Davis on how documents were copied for Mount Royal HOA case. Develop OPM guidance for procedure. | 12 | Already resolved |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 61 | Bring historic problem to new PL Deputy for consideration as task for lead attorney or other ideas. Resolved with new procedure to copy Sandra and Yolanda. | 76 | check on discussion between Aliki and Sandra | Alissa | 8/30/2010 | Done |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 62 | Utilize clerical staff to review site at least twice a week and print out results and provide to appropriate staff. | 49 | each district PA will decided whether to implement solution- Communicate this solution to the PA and propose the solution | Aaron | 8/30/2010 | done |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 63 | Have OGC (Alissa) double check list (list: NOV + 18-14 letter req. cert. mail; all other docs do not); put as reminder item on next ERPA | 71 | remind ERPAs on next call | Alissa | 8/30/10 | 8/26/10 |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 64 | 1- Use existing ERPce framework to create 'activity due' tickler to alert green card/date status. 2-instruct staff on utilization of 'activity due' procedures (link with OPM Indexing update). –tickler can’t be done right now, SLI must pull weekly reports | 48 | set up tickler in ERPce | Linda/ Donna |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | write guidance for staff to utilize the field and reminder | Donna |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | post in OPM | Kate |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Add guidance to pull weekly reports for new employee checklist | Tanya | 10/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 65 | Instruct clerical staff to write SLI's name on bottom of green card. When card is returned to clerical they deliver to SLI | 50, 72 | instruct district clerical staff | Jen | 8/30/10 | Done |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 66 | Janet discuss priority with DLE to convey with local LE staff | 51 | Tim discuss with Janet | Tim | 9/30/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 67 | staff should ensure recipients info is correct by utilizing OPM resources that identify the websites used to name property owners (Does this change the exisiting process? Why is it happening? See solution #45) | 52 | See solution #45 | Jen |  | drop |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 68 | OGC to review Notice of Rights and consider revising where able (99, 100 & 108-Can we have a Lessee tell us what part they don't understand and what Would make sense to them? 106-Didn't someone suggest a pre-addressed envelope? 109-How can we change the process so that the Respondent doesn't have to write down the request?) | 99, 100, 106, 108, 109 | Review and consider | Alissa | 10/15/10 |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 69 | A. when contact is made, provide at least 3 dates for meeting. B. SLI use DEP staff Outlook to organize and set up meetings with Department staff | 104 | DROP |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 70 | Only people delegated by clerk (Lea Crandall) can clerk document. If you need to have authority, contact Lea Crandall. (This may require individual district process anaylsis. Find out what the problem is, if it's a problem, and remove the cause) | 110 | discuss at next ERPA call | Alissa | 8/30/10 | 8/26/10 |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 71 | already resolved, all LCT's forms must go to Reg. Dep. G.C. of Enf. for review and assignment (map change?) | h32 | Check if it’s changed—It has | Alissa | 8/30/10 | 8/26/10 |  |  |  |  |  |  |  |  |  |  |
| # | Solution to be Implemented | Barrier Numbers | Action Step - What is to be Done? | Who is Responsible | When will it be Done? | Date Complete |  |  |  |  |  |  |  |  |  |  |
| 72 | 1. Ensure district staff is organizing files better. (Is lack of organization why it takes time to review?) 2. Create standardized C&E Inspection form. | 59, h24 | Already solved |  | Complete |  |  |  |  |  |  |  |  |  |  |  |