| SCHEDULE FOR REVIEW OF. CORRIDOR CERTIFICATION APPLICATION. FOR FLORIDA POWER & LIGHT. DUVAL-RAVEN 230 kV. SITING CASE NO. TA16-17. OGC CASE NO. 16-0012. DOAH CASE NO. Xxxxxx. |
| --- |
| Day/Date | Requirement | Statute |
| Monday, January 11, 2016 | FPL files Transmission Line Corridor Certification Application with the Department of Environmental Protection (DEP) and with other agencies identified in 403.526(2), F.S. | 403.5251(1)(a) |
| Tuesday, January 19, 2016 (Monday is a Holiday) | Deadline for DEP to request an Administrative Law Judge (ALJ), and file list of those affected or other agencies entitled to notice. | 403.525(1)(a), 403.5251(1)(a)1 |
| Tuesday, January 26, 2016 | Deadline for appointment of an ALJ. | 403.525(1)(b) |
| Tuesday, January 26, 2016 | DEP files a copy of the Application with the Division of Administrative Hearings (DOAH), and DEP files a copy of the proposed schedule with Administrative Law Judge, FPL, and affected agencies. | 403.525(1)(c), 403.5251(2). |
| Monday, February, 1, 2016 | Deadline for DEP to publish FAR Notice of Application Filing. | 403.5251(4), 403.5363(1)(b)1 403.5363(3)(a) |
| Monday, February, 1, 2016 | Deadline for FPL to publish newspaper notice of Application filing. | 403.5251(4), 403.5363(1)(b)1, 403.5363(3)(a) |
| Tuesday, February, 2, 2016 | Deadline for ALJ to issue an Order on the proposed schedule. | 403.5251(2) |
| Wednesday, February 10, 2016 | Deadline for agencies to submit completeness questions to DEP. | 403.5252(1)(a) |
| Wednesday, February 17, 2016 | Deadline for DEP to issue completeness determination on Application. (Schedule assumes application incomplete at this point) | 403.5252(1)(b) |
| Monday, February 22, 2016 | Deadline for Notice to Parties regarding the Informational Public Meeting, assuming that the Meeting is held on the deadline-date. Notice provided by hosting agency: Local Government or Regional Planning Council. | 403.5272(3) |
| Thursday, February 25. 2016 | Deadline for Direct Notice to be provided by FPL regarding Filing of the Application, via US mail or hand-delivery. | 403.5363(5)(a) |
| Monday, February 29, 2016 | Deadline for Newspaper Notice to regarding the Informational Public Meeting, assuming that the Meeting is held on the deadline-date. Notice arranged by hosting agency: Local Government or Regional Planning Council. | 403.5272(3) |
| Tuesday, March 1, 2016 | Deadline for Local Governments to advise the ALJ and parties regarding wanting a public hearing supplementing the certification hearing. | 403.527(4)(a) 403.527(4)(e) |
| Wednesday, March 2, 2016 | Deadline for FPL to file additional information in response to DEP determination of incompleteness. | 403.5252(2) |
| Monday, March 7, 2016 | Deadline for Informational Public Meeting (if held). | 403.5272(1) |
| Monday, March 7, 2016 | Deadline for ALJ to schedule any supplemental public hearings of the Certification Hearing | 403.527(4)(b) 403.527(4)(d) |
| Friday, March 11, 2016 | Deadline for FPL to provide DEP's Siting Coordination Office with list of Direct-notice recipients. | 403.5363(5)(b) |
| Wednesday, March 16, 2016 | Deadline for agencies to submit second completeness questions to DEP. | 403.5252(4) |
| Wednesday, March 16, 2016 | Deadline for affected agencies to issue Preliminary Statements of Issues. | 403.526(1) |
| Wednesday, March 23, 2016 | Deadline for DEP to issue second Determination on Application completeness. (Assume Complete) | 403.5252(4) |
| Friday, April 1, 2016 | Deadline for DEP to publish FAR Notice of Certification Hearing. | 403.527(1)(b) 403.5363(1)(a)2. 403.5363(3)(b) |
| Friday, April 1, 2016 | Deadline for FPL to publish newspaper Notice of Certification Hearing. | 403.527(1)(b), 403.5363(1)(a)2. 403.5363(3)(b) |
| Monday, April 11, 2016 | Deadline for Agencies to submit reports to DEP. (Agencies with Collegial Bodies as heads file draft reports). | 403.526(2)(a) |
| Monday, April 11, 2016 | Affirmative Finding of Need from PSC is a condition precedent to further processing of the Application. | 403.526(2)(e) |
| Friday, April 22, 2016 | Deadline for the filing of Alternate Corridor proposals. | 403.5271(1) |
| Tuesday, April 26, 2016 | Deadline for Agencies with Collegial Bodies as heads to submit Final version of Agency Reports | 403.526(2)(d) |
| Friday, April 29, 2016 | If alternate corridor filed, DEP and FPL issue notices of acceptance or rejection of Alternate Corridor proposal(s), assuming proposals were filed and filed on deadline-date. If accepted, Certification Hearing must be rescheduled and Alternates schedule prescribed. | 403.5271(1)(b)1. |
| Thursday, May 5, 2016 | Deadline for DEP to issue Project Analysis. | 403.526(3) |
| Monday, May 9, 2016 | Deadline for becoming Party to proceeding. | 403.527(2)(b) & (c) |
| Tuesday, May 10, 2016 | Deadline for requesting ALJ to cancel the Certification Hearing if parties stipulate that there are no disputed issues of facts or law. | 403.527(6)(b) |
| Friday, May 13, 2016 | Deadline for ALJ to relinquish jurisdiction based on request to cancel Hearing & Stipulation. | 403.527(6)(a) |
| Monday, May 23, 2016 | Deadline for Parties to submit proposed Recommended Orders to DEP if ALJ relinquishes jurisdiction. | 403.527(6)(d)2 |
| Friday, May 27, 2016 | Deadline for DEP to have published FAR Notice of Cancellation of Certification hearing published if ALJ relinquishes jurisdiction. | 403.5363(3)(c) |
| Friday, June 3, 2016 | Deadline for FPL to have Newspaper Notice of Cancellation of Certification hearing published if ALJ relinquishes jurisdiction. | 403.5363(1)(b)3. |
| Monday, June 6, 2016 | Certification Hearing before ALJ in Baker County. | 403.527(1)(a) |
| Friday, June 24, 2016 | Deadline for Secretary of DEP to issue Final Order of Certification if ALJ has relinquished jurisdiction | 403.529(1)(a) |
| Monday, August 1, 2016 | Anticipated date for ALJ to issue Recommended Order. | 403.527(5) |
| Tuesday, September 20, 2016 | Anticipated date for Siting Board Hearing on Certification. | 403.529(1)(b) |