## Sheet1
Gottfried Creek WTW Field Inspection Log
Date: | 2012-02-28 |  | Time: | 0900 | Surveyor(s): WTW Inspection Team
Site | Location | Location_Address | Latitude | Longitude | Photos | Comments | Findings | Action Item
#1 | Stefano's Restaurant | 401 S. Indiana Avenue | 26.9551 | -82.3526 | 1, 5 | Grease Trap, Dumpsters | Area clean; Grease trap maintained; Proper exterior wash area; No issues
#2 | Provision Eye Center | 473 S. Indiana Avenue | 26.9544 | -82.3528 | 2,3,4 | Private L/S | No lock on lid; Cracked, broken concrete covers; No Emergency sign | Letter to property owner with corrective actions.
#3 | Open Stormwater Canal | 201 Selma Avenue | 26.9555 | -82.3465 | 6,7,8 | Drains area along 776 and behind Englewood Square, Pine Hollow, and Quails Run; EWD Owned and Maintained; PID 0854-03-0001 | Mowed and maintained; Open to sunlight; Low velocity; No regular flushing; High flow during rain; Flows directly to creek; Sediments could harbor bacteria; No Issues | Check to see if old raw water lines are capped?
#4 | Open Land - PID 0494-11-0001 | N. of Arlington Cove, N. Indiana Ave. | 26.9869 | -82.3621 | 9 | 17 acres; Cattle moved around to different pastures | No cattle; No obvious cow patties; bermed; Ditch flow southerly from pasture to county ditch 36-461.14; No Issues | Follow up with Noel Marton - FDACS; Future sampling of ditch during rainy season?
#8 | County Ditch 36-461.14 | N. Indiana Avenue @Tangerine Wds. | 26.9805 | -82.3589 |  | County owned and maintained; | Ditch well maintained
#8 | FDEP Stormwater Ponds | N. Indiana Avenue @ Tangerine Wds. | 26.9805 | -82.3589 |  | FDOT Maintained | DOT ponds overgrown with cattails - over 75%; Ponds DP-35 & DP 35-8 | FDOT Rep. will report to FDOT
#8A | County Ditch 36-461.15 | Tangerine Woods Blvd. | 26.984 | -82.3549 | 10,11 | County Sampling Station | Ditch mowed and maintained; Open to sunlight; Low velocity; Heavy duckweed inhibits UV penetration; Flows through Thomas Ranch; Snake; hogs/armadillos; wildlife
#12 | Foxwood | Foxwood Blvd. |  |  |  | Subdivision clean; Proper pet waste disposal encouraged; No issue
#12 | Foxwood | Linden Dr. | 26.9741 | -82.3463 |  | Stormwater Pond | Wildlife: ducks, turtles, alligator; May feed to encourage wildlife; No Issues
#12 | Foxwood Maintenance Area Ditch | Linden Dr. | 26.9734 | -82.3464 | 12 | Ambient pet waste odor; narrow, shallow ditch with low flow- flows to larger ditch that flows to creek |  | Collected sample GOT-3 for fecal coliform @1107
#13B | Open Space with Nature Trail | Linden Dr. | 26.9763 | -82.3427 | 13-22 | Ditch flows through nature preserve | Much wildlife; many raccoon track, hogs, birds; 30-40 mullet; gar; heavy tree canopy; ditch wide, low and slow flow, flows directly to creek | Future sampling?
#15 | Sampling Station | Park Forest Blvd. | 26.9724 | -82.3443 | 23 | 21FLFTMSARABY0022FTM |  | Check sample at depths and tide stage
#16 | Englewood Sports Complex | 1300 S. River Rd. |  |  |  | Lift Stations | No Issues
#23 | Horse Pasture | Pine St. @ Park Forest Blvd. | 26.9671 | -82.3361 | 24 | 22 acres; PID 0850-04-0001 | Only 4-5 horses; Low horse/acre density; Some manure; Area well maintained; Site dry; No Issues
Date: | 2012-02-28 |  | Time: | 0900 | Surveyor(s): WTW Inspection Team
Site | Location | Location_Address | Latitude | Longitude | Photos | Comments | Findings | Action Item
#10 | Undev. Property/Cattle | Elm St., Artists Ave. | 26.9751 | -82.3599 |  | New barbed wire fence; Dense trees and scrub; No cattle; No Issues | No Issue
#9 | County Pond 36-461.12 | N. Elm St. @ Viridian | 26.3611 | -82.979
#9 | County Ditch 36-461.13 | N. Elm St. @ Viridian | 26.9791 | -82.3609
#17 | County Ditch 36-461.6 | N. McCall Rd. North of Harvard | 26.9685 | -82.357 |  | County owned and maintained; Flows through County property
#18 | Stormwater Runoff | N. Indiana Ave. @ Elks Lodge | 26.969 | -82.351 | 25 | 776 stormwater flows to FDOT ponds DP35-6 | FDOT ponds overgrown with cattails - over 75% | FDOT Rep. will report to FDOT
#37 | Bay Heights | 300 Bay Heights Ave. | 26.9444 | -82.347 |  | Private L/S; Chickens; On Creek | Knocked on door/no one home; left property | Manure management education
#33 | Stormwater Ditch | Riverview Ave & Liberty | 26.9458 | -82.3503 |  | Unmaintained | Unmaintained ditch; Responsibility questionable | Find out who maintains and file report
#34 | Gasparilla Condo | 160 Jose Gaspar Dr. | 26.9507 | -82.346 | 26 | Private L/S On Creek | L/S Well maintained; overflow would not make it to creek; stormwater pond - alligator and wildlife; Pond overflows directly into creek <20' away.
#20A | Deer Creek MHP | E. Horton | 26.9469 | -82.3466 | 27 | EWD Lift Station | L/S Well maintained; Overflow would flow to asphalt; Emergency signage on fence in full view; No issues.
#22A | Septic Tank Area | S. Oxford |  |  |  | Large 2 acre lots; Septic tanks in front yard; No Issues |  | Property owner has 365 days to connect to sewer once it is available; EWD begins billing them after 365 days.
#35 | County Ditch DP-38-13 | S. Oxford | 26.9517 | -82.3414 | 28 | Hogs rooting and grubbing in ditch
#22 | Septic Tank Area | N. Oxford |  |  |  | Large 2 acre lots; Septic tanks in front yard; No Issues |  | Property owner has 365 days to connect to sewer once it is available; EWD begins billing them after 365 days.
#36 | Ditch | N. Oxford between 310 and 339 | 26.9669 | -82.3405 |  | Unmaintained; Orange hose not connected