## Sheet1
Phase I Watershed Management Plan
BMP # | Description | Estimated Design Costs | Estimated Land Costs | Estimated Constuction Cost | Construction Management | Total | Comments
25 | Central/Church Culvert | 3433.416 |  | 17167.08 | 3090.0744 | 23690.5704 | Elevation of road an issue
26 | Central/Main Culvert | 3433.416 |  | 17167.08 | 3090.0744 | 23690.5704 | Linked to RMP29 and RMP32
32 | Bayshore/Main St | 7478.016 |  | 37390.08 | 6730.2144 | 51598.3104 | Improve LOS from C to A
42 | Central/Culvert | 2564.576 |  | 12822.88 | 2308.1184 | 17695.5744 | Improve LOS from E to B
45 | Central Improvement Oakley/Culvert | 2564.576 |  | 12822.88 | 2308.1184 | 17695.5744 | Central Between Oakley and Parmely no drainage structure
31 | Homewood/Harper Culvert | 4317.236 |  | 21586.18 | 3885.5124 | 29788.9284 | One house flooding - Identify the house
1 | Melbourne/Culvert | 13931.4 |  | 69657 | 12538.26 | 96126.66 | Permit for new outfall to harbor
33 | Bayshore/Pinon Culvert | 8826.216 |  | 44131.08 | 7943.5944 | 60900.8904 | Permit for new outfall to harbor
7 | North Shore/culvert | 7774.6 |  | 38873 | 6997.14 | 53644.74 | Reduces flooding
| Total - Drainage Improvements | 54323.452 |  | 271617.26 | 48891.1068 | 374831.8188
49 | Harper and Church Pond Site | [5 empty] | Water Quality Improvements
50 | Treatment Pond US 41/Main | 49542.605 | 245000 | 198170.42 | 73906.9538 | 566619.9788 | Water Quality Improvements
51 | Treatment Pond US41/Shear | 113665.7525 | 500000 | 454663.01 | 160249.3144 | 1228578.0769 | Water Quality Improvements
| Total - Water Quality Improvements | 163208.3575 | 745000 | 652833.43 | 234156.2681 | 1795198.0556
217531.8095
| Total Project | 2170029.8744 |  | 924450.69 | 283047.3749
2170029.8744
|  | Design | 217532
|  | Overhead/internal (10%) | 21753.2
|  | Construction | 924451
|  | Overhead/internal - 15% | 138667.65
|  | land | 745000
|  | Overhead/internal 15% | 111750
|  | Contract monitoring | 10876.6
|  | Total | 2170030.45
|  | Year One - Design | 239285.0095
|  | Year Two | 1128367
|  | Year Three | 802377.8649
2170029.8744