## Sheet1
Town of Century
Wastewater Treatment Plant Miscellaneous Improvements

## WWTP Improvements
Town of Century | [5 empty] | TOTAL ESTIMATED CONSTRUCTION COSTS |  |  | 264000
Wastewater Treatment Plant Miscellaneous Improvements
Florida Gulf Of Mexico Restorwation Project Submittal
Opinion of Probable Costs | [5 empty] | FmHA DESIGN SERVICES FEE RATE CALCULATION
No. | Description | Unit | Quantity | Unit Cost | Extension
1 | Clarifier Improvements | EA | 2 | 35000 | 70000 | A | 200000 | 11.2 | D
2 | RAS Pump Replacement | EA | 1 | 10000 | 10000 | B | 264000 | 1 | E
3 | Effluent Pump and Electrical Replacement/Repair | EA | 1 | 20000 | 20000 | C | 300000 | 10.4 | F
4 | Replacement of Gas Chemical Feed System | EA | 1 | 10000 | 10000
5 | Chemical Feed Safety Gear (SCBA Equipment) | EA | 2 | 2000 | 4000 | B-A | 64000 | 11.2 | D*E
6 | Sidestream Wastewater Return Pump and Electrical Replacement/Repair | EA | 1 | 15000 | 15000 | C-B | 36000 | 10.4 | F*E
7 | Removal of Grit Deposits from the Plant Tankage | LS | 1 | 60000 | 60000
8 | Equalization Basin Repairs (timers, baffles, floats, and aerator replacement, rail repairs) | LS | 1 | 25000 | 25000 | (B-A)*(F*E) | 665600 | 64000 | B-A
9 | Filter Repairs (Backwash Pump and Filter Media Replacement) | LS | 1 | 16000 | 16000 | (C-B)*(D*E) | 403200 | 36000 | C-B
10 | Catwalk | LS | 1 | 10000 | 10000 |  | 1068800 | 100000 | SUM
|  |  |  | SUBTOTAL = | 240000 | E= | 10.7 | % DESIGN FEE
|  |  |  | CONTINGENCY (10%) = | 24000
|  |  |  | CONSTRUCTION TOTAL = | 264000 | FmHA INSPECTION SERVICES FEE RATE CALCULATION
|  |  |  | Design = | 28248 | A | 200000 | 6.3 | D
|  |  |  | CA/CM = | 15840 | B | 264000 | 1 | E
[6 empty] | C | 300000 | 5.8 | F
308088
|  |  |  | Project Contingency (10%) = | 30809 | B-A | 64000 | 6.3 | D*E
|  |  |  | GRAND TOTAL = | 338897 | C-B | 36000 | 5.8 | F*E
|  | Year 1 (design and half of Construction and CA/CM)= |  |  |  | (B-A)*(F*E) | 371200 | 64000 | B-A
[5 empty] | 168168 | (C-B)*(D*E) | 226800 | 36000 | C-B
|  | Year 2 (remaining half of Construction and CA/CM)= |  |  |  |  | 598000 | 100000 | SUM
[5 empty] | 170729 | E= | 6 | % INSPECTION FEE |  | 16.7

## Potable Improvements
Town of Century | [5 empty] | TOTAL ESTIMATED CONSTRUCTION COSTS |  |  | 145750
Wastewater Treatment Plant Miscellaneous Improvements
Florida Gulf Of Mexico Restorwation Project Submittal
Opinion of Probable Costs | [5 empty] | FmHA DESIGN SERVICES FEE RATE CALCULATION
No. | Description | Unit | Quantity | Unit Cost | Extension
1 | Replacement of Lime Addition Equipment (Well #1 and #2) | EA | 2 | 20000 | 40000 | A | 100000 | 12.3 | D
2 | Replacement of Chlorine Equipment (Well #2 and #3) | EA | 2 | 5500 | 11000 | B | 145750 | 1 | E
3 | Meter and Backflow Replacement at Well #3 | LS | 1 | 25000 | 25000 | C | 200000 | 11.2 | F
4 | Replacement of Pipework at Well Sites | EA | 3 | 8500 | 25500
5 | Miscellaneous Wellhouse Building Repairs (Well #1 and #2) | EA | 2 | 12500 | 25000 | B-A | 45750 | 12.3 | D*E
6 | Chemical Feed Safety Gear (SCBA Equipment) | EA | 3 | 2000 | 6000 | C-B | 54250 | 11.2 | F*E
|  |  |  | SUBTOTAL = | 132500 | (B-A)*(F*E) | 512400 | 45750 | B-A
|  |  |  | CONTINGENCY (10%) = | 13250 | (C-B)*(D*E) | 667275 | 54250 | C-B
|  |  |  | CONSTRUCTION TOTAL = | 145750 |  | 1179675 | 100000 | SUM
|  |  |  | Design = | 17199 | E= | 11.8 | % DESIGN FEE
|  |  |  | CA/CM = | 9620
FmHA INSPECTION SERVICES FEE RATE CALCULATION
172569
|  |  |  | Project Contingency (10%) = | 17257 | A | 100000 | 6.9 | D
|  |  |  | GRAND TOTAL = | 189826 | B | 145750 | 1 | E
[6 empty] | C | 200000 | 6.3 | F
Year 1 (design and half of Construction and CA/CM)=
[5 empty] | 94884 | B-A | 45750 | 6.9 | D*E
|  | Year 2 (remaining half of Construction and CA/CM)= |  |  |  | C-B | 54250 | 6.3 | F*E
94942
[6 empty] | (B-A)*(F*E) | 288225 | 45750 | B-A
[6 empty] | (C-B)*(D*E) | 374325 | 54250 | C-B
[7 empty] | 662550 | 100000 | SUM
[6 empty] | E= | 6.6 | % INSPECTION FEE |  | 18.4