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	Day/Date
	Requirement
	Statute

	Monday, January 11, 2016
	FPL files Transmission Line Corridor Certification Application with the Department of Environmental Protection (DEP) and with other agencies identified in 403.526(2), F.S. 
	403.5251(1)(a)

	Tuesday, January 19, 2016 (Monday is a Holiday)
	Deadline for DEP to request an Administrative Law Judge (ALJ), and file list of those affected or other agencies entitled to notice.  
	403.525(1)(a), 403.5251(1)(a)1

	Tuesday, January 26, 2016
	Deadline for appointment of an ALJ.   
	403.525(1)(b)

	Tuesday, January 26, 2016
	DEP files a copy of the Application with the Division of Administrative Hearings (DOAH), and DEP files a copy of the proposed schedule with Administrative Law Judge, FPL, and affected agencies. 
	403.525(1)(c),  403.5251(2).

	Monday, February, 1, 2016
	Deadline for DEP to publish FAR Notice of Application Filing.  
	403.5251(4),   403.5363(1)(b)1 403.5363(3)(a)

	Monday, February, 1, 2016
	Deadline for FPL to publish newspaper notice of Application filing.  
	403.5251(4),  403.5363(1)(b)1, 403.5363(3)(a)

	Tuesday, February, 2, 2016
	Deadline for ALJ to issue an Order on the proposed schedule.  
	403.5251(2)

	Wednesday, February 10, 2016
	Deadline for agencies to submit completeness questions to DEP. 
	403.5252(1)(a)

	Wednesday, February 17, 2016
	Deadline for DEP to issue completeness determination on Application. (Schedule assumes application incomplete at this point) 
	403.5252(1)(b)

	Monday, February 22, 2016
	Deadline for Notice to Parties regarding the Informational Public Meeting, assuming that the Meeting is held on the deadline-date.  Notice provided by hosting agency: Local Government or Regional Planning Council.    
	403.5272(3)

	Thursday, February 25. 2016
	Deadline for Direct Notice to be provided by FPL regarding Filing of the Application, via US mail or hand-delivery.    
	403.5363(5)(a)

	Monday, February 29, 2016
	Deadline for Newspaper Notice to regarding the Informational Public Meeting, assuming that the Meeting is held on the deadline-date. Notice arranged by hosting agency: Local Government or Regional Planning Council.   
	403.5272(3)

	Tuesday, March 1, 2016
	Deadline for Local Governments to advise the ALJ and parties regarding wanting a public hearing supplementing the certification hearing.  
 
	403.527(4)(a)
403.527(4)(e)

	Wednesday, March 2, 2016
	Deadline for FPL to file additional information in response to DEP determination of incompleteness.  
	403.5252(2)

	Monday, March 7, 2016
	Deadline for Informational Public Meeting (if held).  
	403.5272(1)

	Monday, March 7, 2016
	Deadline for ALJ to schedule any supplemental public hearings of the Certification Hearing  
	403.527(4)(b)
403.527(4)(d)

	Friday, March 11, 2016
	Deadline for FPL to provide DEP's Siting Coordination Office with list of Direct-notice recipients.   
	403.5363(5)(b)

	Wednesday, March 16, 2016
	Deadline for agencies to submit second completeness questions to DEP. 
	403.5252(4)

	Wednesday, March 16, 2016
	Deadline for affected agencies to issue Preliminary Statements of Issues. 
	403.526(1)

	Wednesday, March 23, 2016
	Deadline for DEP to issue second Determination on Application completeness. (Assume Complete) 
	403.5252(4)

	Friday, April 1, 2016
	Deadline for DEP to publish FAR Notice of Certification Hearing.  
	403.527(1)(b) 403.5363(1)(a)2. 403.5363(3)(b)

	Friday, April 1, 2016
	Deadline for FPL to publish newspaper Notice of Certification Hearing.  
	403.527(1)(b), 403.5363(1)(a)2. 403.5363(3)(b)

	Monday, April 11, 2016
	Deadline for Agencies to submit reports to DEP.  (Agencies with Collegial Bodies as heads file draft reports).   
	403.526(2)(a)

	Monday, April 11, 2016
	Affirmative Finding of Need from PSC is a condition precedent to further processing of the Application. 
	403.526(2)(e)

	Friday, April 22, 2016
	Deadline for the filing of Alternate Corridor proposals.  
	403.5271(1)

	Tuesday, April 26, 2016
	Deadline for Agencies with Collegial Bodies as heads to submit Final version of Agency Reports 
	403.526(2)(d)

	Friday, April 29, 2016
	If alternate corridor filed, DEP and FPL issue notices of acceptance or rejection of Alternate Corridor proposal(s), assuming proposals were filed and filed on deadline-date.  If accepted, Certification Hearing must be rescheduled and Alternates schedule prescribed. 
	403.5271(1)(b)1.

	Thursday, May 5, 2016
	Deadline for DEP to issue Project Analysis. 
	403.526(3)

	Monday, May 9, 2016
	Deadline for becoming Party to proceeding.   
	403.527(2)(b) & (c)

	Tuesday, May 10, 2016

	Deadline for requesting ALJ to cancel the Certification Hearing if parties stipulate that there are no disputed issues of facts or law.    
	403.527(6)(b)

	
Friday, May 13, 2016

	Deadline for ALJ to relinquish jurisdiction based on request to cancel Hearing & Stipulation.     
	403.527(6)(a) 

	Monday, May 23, 2016
	Deadline for Parties to submit proposed Recommended Orders to DEP if ALJ relinquishes jurisdiction.     
	403.527(6)(d)2

	Friday, May 27, 2016
	Deadline for DEP to have published FAR Notice of Cancellation of Certification hearing published if ALJ relinquishes jurisdiction.     
	403.5363(3)(c)

	Friday, June 3, 2016
	Deadline for FPL to have Newspaper Notice of Cancellation of Certification hearing published if ALJ relinquishes jurisdiction.     
	403.5363(1)(b)3.

	Monday, June 6, 2016
	Certification Hearing before ALJ in Baker County. 
	403.527(1)(a)

	Friday, June 24, 2016
	[bookmark: _GoBack]Deadline for Secretary of DEP to issue Final Order of Certification if ALJ has relinquished jurisdiction 
	403.529(1)(a)

	Monday, August 1, 2016
	Anticipated date for ALJ to issue Recommended Order. 
	403.527(5)

	Tuesday, September 20, 2016
	Anticipated date for Siting Board Hearing on Certification.  
	403.529(1)(b)
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